## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09776 | Retrofitting | Laying of HDPE Pipe by HDD Process & Open cut method including restoration work at Mohanad Bandel Road within MEGHSAR PWSS, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 09 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000377/2022-2023 | 2090/HUG | 21/09/2022 | 05/11/2022 | M/S BISWAS CONSTRUCTION | 87.34 | 70.61 | 80.85 | 80
Total | [13 empty] | 87.34 | 70.61 | 80.85