## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09777 | Retrofitting | Providing 40 nos. Functional House Hold Connection (FHTC) within the Command area of Basudebbati Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) |  | ORD/000121/2022-2023 | 461/CH | 31/05/2022 | 20/06/2022 | CREATION CONSTRUCTION | 4.3 | 4.28 | 99.51 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09777 | Retrofitting | Providing 1961 nos Functional Household Tap Connection (FHTC) within the command area of Basudebbati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000275/2021-2022 | 2129/Hug | 01/12/2021 | 20/01/2022 | CREATION CONSTRUCTION | 80.54 | 80.53 | 99.99 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09777 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion of BASUDEBBATI PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000736/2023-2024 | 28/CH | 05/01/2024 | 20/01/2024 | M/S BIMAL DAS AND CO. | 4.35 | 4.34 | 99.8 | 50
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09777 | Retrofitting | Providing Functional House hold tap connection (FHTC) under JJM within left out portion at Basudevbati PWSS under Polba Dadpur Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000459/2024-2025 | 4046/HUG | 19/12/2024 | 19/03/2025 | S.B. ENTERPRISE | 5.59 | 0 | 0 | 50
Total | [13 empty] | 94.78 | 89.15 | 94.06