## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Preparation of DPR for Augmentation of KAMARPUKUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000383/2021-2022 | 614/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.61 | 3.62 | 100.34 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Chandannagar Sub-Division Office under Chandannagar Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer (Civil) |  | ORD/000321/2021-2022 | 2110/hug | 30/11/2021 | 31/03/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer | Junior Engineer (Civill) | ORD/000327/2021-2022 | 2105/Hug | 29/11/2021 | 30/03/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2022-2023 | 79/20/Hug | 06/01/2023 |  | Resource Division | 1.78 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Repairing of Rising Main due to Construction of Box Culvert by PWD and laying D.I pipes & specials for Rising Main pipe line for KAMARPUKUR Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. [Block-Goghat-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000432/2022-2023 | 733/Arg | 29/09/2022 | 19/10/2022 | DHIRENDRA ENGINEERING & CONSTRUCTION | 4.17 | 4.15 | 99.53 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kamarpukur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000219/2022-2023 | 844/ED | 14/02/2023 | 15/05/2023 | SUTRADHAR TRADERS | 10.78 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 1385/60/Hug | 15/05/2023 |  | Resource Division | 9.22 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. |  |  | BILL/00739/2023-2024 | null | 06/11/2023 |  | GOUR KUMAR DAS | 0.76 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1124/5/HUG | 06/06/2022 |  | Resource Division | 10.98 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1773/28/Hug | 29/08/2022 |  | Resource Division | 0.69 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1590/6/Hug | 03/08/2022 |  | Resource Division | 18.45 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 12/08/2023 | SPG ENTERPRISES | 48.51 | 0 | 0 | 70
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-I) with Laying Distribution System, repairing of existing OHR, switch rooms & boundary wall and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000114/2022-2023 | 1150/Hug | 09/06/2022 | 07/09/2022 | TITAS CONSTRUCTION | 231.61 | 130.07 | 56.16 | 25
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-II) with Laying Distribution System, Construction of switch room & boundary wall at proposed 3rd TW site and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000053/2022-2023 | 853/Hug | 25/04/2022 | 09/06/2022 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 104.29 | 27.73 | 26.59 | 15
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Route survey Design drawing & DPR preparation of Kamarkundu Zone- I, II & III PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer(HQ) |  | ORD/000177/2022-2023 | 271/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.97 | 2.47 | 49.6 | 100
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Additional pipeline due to shifting of 3rd Tubewell site under Augmentation of Kamarpukur Zone-II water supply scheme under Goghat- II block of Arambagh Sub-Division, Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000744/2023-2024 | 379/HUG | 08/02/2024 | 29/08/2024 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.75 | 17.75 | 100 | 100
Total | [13 empty] | 565.39 | 185.78 | 32.86