## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Preparation of DPR for Augmentation of KAMARPUKUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000383/2021-2022 | 614/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.61 | 3.62 | 100.34 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Chandannagar Sub-Division Office under Chandannagar Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer (Civil) |  | ORD/000321/2021-2022 | 2110/hug | 30/11/2021 | 31/03/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer | Junior Engineer (Civill) | ORD/000327/2021-2022 | 2105/Hug | 29/11/2021 | 30/03/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-II) with Laying Distribution System, Construction of switch room & boundary wall at proposed 3rd TW site and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000053/2022-2023 | 853/Hug | 25/04/2022 | 09/06/2022 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 104.29 | 31.67 | 30.37 | 80
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-I) with Laying Distribution System, repairing of existing OHR, switch rooms & boundary wall and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000114/2022-2023 | 1150/Hug | 09/06/2022 | 09/10/2025 | TITAS CONSTRUCTION | 231.61 | 144.09 | 62.21 | 80
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Repairing of Rising Main due to Construction of Box Culvert by PWD and laying D.I pipes & specials for Rising Main pipe line for KAMARPUKUR Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. [Block-Goghat-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000432/2022-2023 | 733/Arg | 29/09/2022 | 19/10/2022 | DHIRENDRA ENGINEERING & CONSTRUCTION | 4.17 | 4.15 | 99.53 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Route survey Design drawing & DPR preparation of Kamarkundu Zone- I, II & III PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer(HQ) |  | ORD/000177/2022-2023 | 271/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.97 | 4.93 | 99.2 | 100
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1124/5/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 10.98 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1773/28/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1590/6/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 18.45 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kamarpukur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000219/2022-2023 | 844/ED | 14/02/2023 | 15/05/2023 | SUTRADHAR TRADERS | 10.78 | 0 | 0 | 35
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 12/08/2023 | SPG ENTERPRISES | 48.51 | 11.91 | 24.56 | 70
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2022-2023 | 79/20/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 1.78 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 1385/60/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 9.22 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. |  |  | BILL/00739/2023-2024 |  | 06/11/2023 | 06/11/2023 | GOUR KUMAR DAS | 0.76 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Resovoir of KAMARPUKUR Water Supply Scheme under Arambagh Sub - Division, P.H.E. Dte., Hooghly. | Assistant Engineer | Junior Engineer (Civill) | ORD/000308/2024-2025 | 3677/HUG | 13/11/2024 | 01/07/2026 | ZEST INFRACON | 28.14 | 0 | 0 | 50
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Additional pipeline due to shifting of 3rd Tubewell site under Augmentation of Kamarpukur Zone-II water supply scheme under Goghat- II block of Arambagh Sub-Division, Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000744/2023-2024 | 379/HUG | 08/02/2024 | 29/08/2024 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.75 | 17.75 | 100 | 100
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | SM/09790 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) BALIPUR PWSS (ZONE- II )-2nos (2) BATANAL PWSS( Zone - I)-2nos (3) BATANAL PWSS( Zone - II)-2nos (4) DAKSHIN RASULPUR PWSS- 2 nos (5) HAZIPUR PWSS- 3nos (6) KAMARPUKUR PWSS- 3nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002645/2024-2025 | 809/Arg | 23/08/2024 | 22/09/2024 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 505.14 | 218.12 | 43.18