## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Paschim Gopinathpur PWSS under Chandannagar Sub Division , PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000475/2021-2022 | 167/chan | 24/03/2022 | 13/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.77 | 3.7 | 98.24 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Augmentation of PASCHIM GOPINATHPUR Water Supply Scheme with Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS, Rising Main, Construction of Switch Room (5.40 m x 3.60 m ), FHTC Work, Repairing of 2 Nos. existing Switch Room (3.6 m x 3.0m), Boundary Wall at O.H.R Site, Boundary wall at 2nd & 3 rd Tube well at Haripal Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000047/2022-2023 | 831/Hug | 20/04/2022 | 14/02/2023 | M/S S.S. ENTERPRISE | 464.29 | 399.84 | 86.12 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at HARIPAL Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000088/2022-2023 | 220/chan | 13/04/2022 | 03/05/2022 | M/S S.G. CONSTRUCTION | 4.98 | 4.72 | 94.67 | 100
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000056/2022-2023 | 2047/ED | 01/12/2022 | 01/03/2023 | MAHADEV ENTERPRISE | 10.17 | 10.16 | 99.89 | 30
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000103/2022-2023 | 390/CMSD-II(D) | 01/08/2022 | 16/08/2022 | M/S PRACHI ENGINEERING | 2.1 | 1.76 | 83.92 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT , CDD, PHR DTE. | Driller In Charge | Junior Engineer | ORD/000106/2022-2023 | 388/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S S.K.GHOSH & CO. | 2.44 | 2.44 | 100 | 0
7 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000293/2022-2023 | 440/CMSD-II | 12/09/2022 | 27/09/2022 | M/S S.K.GHOSH & CO. | 3.06 | 1.43 | 46.61 | 0
8 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CNSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000104/2022-2023 | 389/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S S.K.GHOSH & CO. | 2.91 | 2.09 | 71.88 | 0
9 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000105/2022-2023 | 387/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S S.K.GHOSH & CO. | 3.14 | 2.97 | 94.43 | 0
10 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well(250mm x 200mm x 230 Mtrs. Depth) by utilising Departmental Machineries for Paschim Gopinathpur WS Scheme TW-I , Haripal Block under Hooghly District , CDD,PHE Dte. | Driller In Charge | Junior Engineer | ORD/000280/2022-2023 | 1130/CDD | 04/11/2022 | 04/12/2022 | M/S SAIKAT ENTERPRISE | 11.28 | 9.94 | 88.12 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2021-2022 | 157/11/Hug | 24/01/2022 | 24/01/2022 | Resource Division | 1.03 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2021-2022 | 423/4/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 25.98 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 1125/4/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 2686/9/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.34 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1370/Hug | 06/07/2022 | 06/07/2022 | Resource Division | 101.79 | 0 | 0 | 0
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Auf. of Paschim Gopinathpur W/S. Sch. TW-III |  |  | BILL/00059/2022-2023 | 121 | 28/12/2022 | 28/12/2022 | WBSEDCL | 2.54 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000254/2022-2023 | 921/ED | 22/02/2023 | 23/05/2023 | MOITRA ENGINEERING CO. | 10.68 | 10.38 | 97.19 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Laying balance LDS AND FHTC of Paschim Gopinathpur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000665/2023-2024 | 3590/HUG | 05/12/2023 | 01/06/2025 | M/S S.S. ENTERPRISE | 31.84 | 19.27 | 60.52 | 100
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Balance LDS of Paschim Gopinathpur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000671/2023-2024 | 3588/HUG | 05/12/2023 | 01/06/2025 | M/S S.S. ENTERPRISE | 32.15 | 21.1 | 65.64 | 100
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Laying additional pipeline in different mouzas of Paschim Gopinathpur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division, P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000663/2023-2024 | 3589/HUG | 05/12/2023 | 01/06/2025 | M/S S.S. ENTERPRISE | 32.46 | 14.59 | 44.93 | 100
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2022-2023 | 01/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 11.94 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 1383/15/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 2.43 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2022-2023 | 109/8/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 45.2 | 0 | 0 | 0
24 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Quotation Bill for New Service Connection at Aug. of Paschin Gopinathpur W/S. Sch. |  |  | BILL/00906/2022-2023 | 184 | 10/03/2023 | 10/03/2023 | WBSEDCL | 2.95 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Laying balance DI pipe and allied work of Paschim Gopinathpur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division, P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000749/2023-2024 | 382/HUG | 08/02/2024 | 02/06/2025 | M/S S.S. ENTERPRISE | 9.28 | 0 | 0 | 100
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well, 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of SALEPUR-DUTTAPUR ZONE-I W/S Scheme, 3rd Tube Well Site of PASCHIM GOPINATHPUR W/S Scheme & Nasibpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000254/2024-2025 | 3524/HUG | 22/10/2024 | 04/03/2025 | OSMAN SEKH | 44.34 | 11.53 | 26 | 100
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Damage road repairing at different location at Panchgachia mouza under Paschim Gopinathpur PWSS under Haripal block of the Chandannagar sub division under Chandannagar Sub division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000296/2025-2026 | 929/CHAN | 21/07/2025 | 10/08/2025 | M/S S.S. ENTERPRISE | 4.98 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Damage road repairing at different location at Mora mouza under Paschim Gopinathpur PWSS under Haripal block of Chandannagar sub division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000304/2025-2026 | 937/CHAN | 21/07/2025 | 10/08/2025 | M/S S.S. ENTERPRISE | 4.97 | 0 | 0 | 0
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | SM/09791 | Augmentation | Damage road repairing at different location at Sodpur mouza under Paschim Gopinathpur PWSS under Haripal block of Chandannagar sub division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000303/2025-2026 | 936/CHAN | 21/07/2025 | 10/08/2025 | M/S S.S. ENTERPRISE | 4.96 | 0 | 0 | 0
Total | [13 empty] | 890.33 | 515.91 | 57.95