## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Construction of Protection Wall at O.H.R. Site from Flood Water for Bilaspur Zone-I Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000111/2022-2023 | 449/SER | 31/05/2022 | 15/07/2022 | PRADIP KUMAR ADHYA | 4.99 | 4.97 | 99.66 | 0
2 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY JOHN-1500-III RIG MACHINE UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000173/2021-2022 | 476 /CDD | 06/09/2021 | 06/10/2021 | PADMA ENGINEERING & CO. | 14.74 | 11.18 | 75.89 | 0
3 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III UNDER CDD, PHE DTE. |  |  | ORD/000174/2021-2022 | 1015/CDD | 15/12/2021 | 14/01/2022 | PADMA ENGINEERING & CO. | 12.61 | 11.16 | 88.47 | 0
4 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | ADDITIONAL DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III AT BILASPUR ZONE-I, TW-I WITHIN JANGIPARA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000175/2021-2022 | 07/CMSD-I | 04/01/2022 | 14/01/2022 | PADMA ENGINEERING & CO. | 0.76 | 0.58 | 76.14 | 0
5 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE WITHIN JANGIPARA BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000171/2021-2022 | 1013/CDD | 15/12/2021 | 14/01/2022 | PADMA ENGINEERING & CO. | 12.61 | 10.54 | 83.56 | 0
6 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY WITHIN GHATAL BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000172/2021-2022 | 479/ CDD | 07/09/2021 | 07/10/2021 | PADMA ENGINEERING & CO. | 14.74 | 11.14 | 75.61 | 0
7 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | BIG DIA TUBE WELL |  |  | VCH/001841/2021-2022 |  | 19/01/2022 | 19/01/2022 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | BIG DIA TUBE WELL |  |  | VCH/001840/2021-2022 |  | 19/01/2022 | 19/01/2022 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0 | 0
9 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Electric Supply |  |  | VCH/001992/2022-2023 | 13 | 04/07/2022 | 04/07/2022 | WBSEDCL | 19.89 | 0 | 0 | 0
10 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Central Drilling Payment |  |  | VCH/002416/2021-2022 | C022228292462 | 09/02/2022 | 09/02/2022 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0 | 0
11 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of S/P/M & other E/M allied works for Bilaspur W/S. Sch. Hooghly Z-II, TW-II |  |  | ORD/000361/2022-2023 | 780/,ED | 05/05/2022 | 03/08/2022 | TAMAL ENTERPRISE | 10.55 | 10.51 | 99.67 | 5
12 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-II, TW-I, Dist- Hooghly |  |  | ORD/000096/2022-2023 | 779/ED | 05/05/2022 | 03/08/2022 | H.K.DAS & CO. | 10.5 | 10.5 | 99.95 | 0
13 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-I, TW-I, Dist- Hooghly |  |  | ORD/001165/2021-2022 | 778/ED | 05/02/2022 | 06/05/2022 | M/S DAS ENTERPRISE | 10.52 | 10.26 | 97.55 | 0
14 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply & installation of LED board and outside display board for depicting details of pump/valve operators at Zone-I, P.H. No.I & II of Bilashpur w/s scheme, Dist.-Hooghly under ED, PHE Dte. |  |  | ORD/000362/2022-2023 | 2410/HMSD | 30/12/2022 | 09/01/2023 | DIPA CHHETRI | 0.84 | 0.84 | 100 | 0
15 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Bilaspur W/S. Sch. TW- II, Z-I, Hooghly |  |  | ORD/000862/2022-2023 | 913 /ED | 07/06/2022 | 05/09/2022 | A.S. ENTERPRISE | 10.48 | 10.23 | 97.55 | 0
16 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 986/Hug | 19/05/2022 | 19/05/2022 | Resource Division | 33.77 | 0 | 0 | 0
17 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 987/Hug | 19/05/2022 | 19/05/2022 | Resource Division | 9.33 | 0 | 0 | 0
18 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1107/3/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 6.16 | 0 | 0 | 0
19 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000261/2022-2023 | 610/Hug | 02/03/2023 | 02/03/2023 | Resource Division | 39.18 | 0 | 0 | 0
20 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000313/2023-2024 | 1384/10/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 38.51 | 0 | 0 | 0
21 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | car hire charges |  |  | BILL/00785/2022-2023 | 157 | 10/02/2023 | 10/02/2023 | DEBASHISH GHOSH | 0.15 | 0 | 0 | 0
22 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Fuel Charge |  |  | BILL/00784/2022-2023 | 158 | 10/02/2023 | 10/02/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0 | 0
23 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Fuel Charges |  |  | BILL/00788/2022-2023 | 158 | 10/02/2023 | 10/02/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
24 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | fuel charges |  |  | BILL/00786/2022-2023 | 158 | 10/02/2023 | 10/02/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 0.07 | 0 | 0 | 0
25 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Fuel Charge |  |  | BILL/00783/2022-2023 | 157 | 10/02/2023 | 10/02/2023 | DEBASHISH GHOSH | 0.17 | 0 | 0 | 0
26 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bilaspur water supply scheme Zone-I, T.W. No. II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00856/2022-2023 |  | 27/02/2023 | 27/02/2023 | A.S. ENTERPRISE | 10.23 | 0 | 0 | 0
27 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Hire Charges |  |  | BILL/00787/2022-2023 | 157 | 10/02/2023 | 10/02/2023 | DEBASHISH GHOSH | 0.18 | 0 | 0 | 0
28 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Protection works and other allied works at Head Work Site & 2nd Tube Well Site of Bilaspur Zone-II under Serampore Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000442/2024-2025 | 4044/HUG | 19/12/2024 | 19/03/2025 | M/S. S.G. CONSTRUCTION | 30.66 | 0 | 0 | 0
29 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Laying of leftout pipeline and providing leftout FHTC and construction of Drain connecting to nearest Drain Culvert at Head work site,Land Development at 3rd Tubwell Site,Construction of Toilet ,Septic tank,soak well ,Plumbing work at 2nd Tubewell site at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. |  |  | ORD/000465/2024-2025 | 4047/HUG | 19/12/2024 | 19/03/2025 | PRADIP KUMAR ADHYA | 40.81 | 0 | 0 | 0
30 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Bilaspur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (New Scheme) (2nd Call) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2022-2023 | 755/Hug | 11/04/2022 | 23/04/2022 | S. HATI | 507.65 | 507.48 | 99.97 | 99
31 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Construction of balance portion of Boundary Wall, Land Development, Pathway, Drain at H/W Site & 2nd T/W Site and Other allied works at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000662/2023-2024 | 3561/HUG | 06/12/2023 | 04/02/2024 | PRADIP KUMAR ADHYA | 51.59 | 50.49 | 97.87 | 80
32 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000780/2023-2024 | 537/HUG | 20/02/2024 | 01/12/2024 | SRI KRISHNA ENTERPRISE | 12.1 | 6.3 | 52.1 | 60
33 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Laying of Balance portion of Additional Pipeline including other allied works at Borhal Mouza in Bilaspur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000806/2023-2024 | 590/HUG | 22/02/2024 | 21/06/2024 | BAKSHI ENTERPRISE | 17.55 | 10.02 | 57.11 | 75
34 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Balance LDS and Other works within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000784/2023-2024 | 531/HUG | 20/02/2024 | 06/03/2024 | GOURI ENTERPRISE | 13.52 | 13.35 | 98.7 | 99
35 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Borhal Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000852/2023-2024 | 734/HUG | 05/03/2024 | 03/07/2024 | SRI KRISHNA ENTERPRISE | 18.31 | 16.73 | 91.39 | 90
36 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Bilaspur & Guti-Atra mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000191/2024-2025 | 534/SER | 17/09/2024 | 24/09/2024 | ASHA ENTERPRISE | 4.97 | 4.95 | 99.51 | 99
37 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Guti-Atra & Singti mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000194/2024-2025 | 537/SER | 17/09/2024 | 24/09/2024 | ASHA ENTERPRISE | 4.97 | 4.97 | 99.96 | 99
38 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Quotation bill for new service connection charges at Bilaspur PWSS Zone-II, P.H. No.-III, Hooghly. Application No. 5004065667 Ref ID: 503592945 |  |  | BILL/00111/2024-2025 | 45 | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
39 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution at Paschim Gobindapur mouza of Bilaspur Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000858/2023-2024 | 740/HUG | 05/03/2024 | 04/05/2024 | RAJU CONSTRUCTION | 32.26 | 0 | 0 | 20
40 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 2 nos. 300 X200 mm dia Tube Well, 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 5th Tube Well Site of BILASPUR W/S Scheme & 3rd Tube Well Site of JANAI W/S Scheme(ZONE-I) under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000252/2024-2025 | 3523/HUG | 22/10/2024 | 01/02/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 29.4 | 3.74 | 12.72 | 50
41 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Bilaspur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House, 450 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, DiSt- Hooghly under Hooghly Divn.PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2022-2023 | 639/Hug | 01/04/2022 | 22/04/2025 | PRADIP KUMAR ADHYA | 447.88 | 421.2 | 94.04 | 90
42 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BILASPUR (ZONE-II) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000753/2023-2024 | 388/HUG | 08/02/2024 | 01/11/2024 | PRADIP KUMAR ADHYA | 31.66 | 0 | 0 | 99
43 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall, and rising main with interconnection and left out repairing of Concrete Road at Bilaspur W/s Scheme(Zone-I), Jangipara Block under Hooghly Division PHE Dte. Source Augmentation. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000890/2023-2024 | 814/HUG | 11/03/2024 | 09/09/2024 | PRADIP KUMAR ADHYA | 64 | 0 | 0 | 90
44 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Shifting of existing water supply pipeline due to widening & strengthening of existing culvert at near Rahimpur Paschimpara & Bilaspur Flood Shelter Block- Jangipara under Bilaspur Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001299/2024-2025 | 71/SER | 20/01/2025 | 27/01/2025 | ROY ENTERPRISE | 2.06 | 0 | 0 | 99
45 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Laying of pipeline and allied work within left out habitation of Singti Mouza in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000337/2024-2025 | 629/SER | 30/10/2024 | 31/12/2024 | M/S.S.HATI | 5 | 0 | 0 | 99
46 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001253/2024-2025 | 53/SER | 20/01/2025 | 27/01/2025 | SRI KRISHNA ENTERPRISE | 5 | 2.89 | 57.86 | 99
47 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of Akna Mouzas in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001254/2024-2025 | 54/SER | 20/01/2025 | 27/01/2025 | SRI KRISHNA ENTERPRISE | 4.99 | 0 | 0 | 99
48 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BILASPUR ZONE II Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000884/2023-2024 | 808/HUG | 11/03/2024 | 01/12/2024 | RAJU CONSTRUCTION | 31.46 | 0 | 0 | 99
49 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Pashpur & Bira Chak mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2024-2025 | 548/SER | 19/09/2024 | 26/09/2024 | MAA TARA CONSTRUCTION | 4.96 | 0 | 0 | 99
50 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Ranjapur mouza of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000205/2024-2025 | 550/SER | 19/09/2024 | 26/09/2024 | MAA TARA CONSTRUCTION | 4.97 | 0 | 0 | 99
51 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Senpur & Khanda Kshetra mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000020/2025-2026 | 291/SER | 17/04/2025 | 27/04/2025 | ASHA ENTERPRISE | 4.99 | 0 | 0 | 99
52 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Quotation money deposition for new service connection at Bilashpur w/s scheme, Zone- II, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004304186 Reference ID- 503697845 SM Code- 09825 |  |  | BILL/00969/2024-2025 | BP-2024-25-637 | 13/11/2024 | 13/11/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
53 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Quotation money deposition for new service connection at Bilashpur w/s scheme, Zone- I, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004314769 Reference ID- 503702944 SM Code- 09825 |  |  | BILL/00970/2024-2025 | BP-2024-25-636 | 13/11/2024 | 13/11/2024 | WBSEDCL | 5.24 | 0 | 0 | 0
54 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PAYMENT TO ROAD RESTORATION TO PWD RAHIMPUR JANGIPARA ROAD |  |  | BILL/00681/2024-2025 | BP-2024-25-500 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 47.62 | 0 | 0 | 0
55 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PAYMENT TO ROAD RESTORATION TO PWD FOR BOKPOTAGHAT ROAD |  |  | BILL/00679/2024-2025 | BP-2024-25-500 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 20.7 | 0 | 0 | 0
56 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of Pashpur Mouza in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001255/2024-2025 | 55/SER | 20/01/2025 | 27/01/2025 | ROY ENTERPRISE | 5 | 0 | 0 | 90
57 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of Ranjapur Mouza in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001256/2024-2025 | 56/SER | 20/01/2025 | 27/01/2025 | ROY ENTERPRISE | 5 | 0 | 0 | 90
58 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000805/2023-2024 | 589/HUG | 22/02/2024 | 01/12/2025 | ROY ENTERPRISE | 13.53 | 6.72 | 49.71 | 99
59 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone-II, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002578/2023-2024 | 454/ED | 05/03/2024 | 24/05/2026 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
Total | [13 empty] | 1890.48 | 1147.7 | 60.71