## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | BIG DIA TUBE WELL |  |  | VCH/001840/2021-2022 | null | 19/01/2022 |  | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0 | 0
2 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | BIG DIA TUBE WELL |  |  | VCH/001841/2021-2022 | null | 19/01/2022 |  | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0 | 0
3 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Central Drilling Payment |  |  | VCH/002416/2021-2022 | C022228292462 | 09/02/2022 |  | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY JOHN-1500-III RIG MACHINE UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000173/2021-2022 | 476 /CDD | 06/09/2021 | 06/10/2021 | PADMA ENGINEERING & CO. | 14.74 | 11.18 | 75.89 | 0
5 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III UNDER CDD, PHE DTE. |  |  | ORD/000174/2021-2022 | 1015/CDD | 15/12/2021 | 14/01/2022 | PADMA ENGINEERING & CO. | 12.61 | 11.16 | 88.47 | 0
6 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | ADDITIONAL DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III AT BILASPUR ZONE-I, TW-I WITHIN JANGIPARA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000175/2021-2022 | 07/CMSD-I | 04/01/2022 | 14/01/2022 | PADMA ENGINEERING & CO. | 0.76 | 0.58 | 76.14 | 0
7 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE WITHIN JANGIPARA BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000171/2021-2022 | 1013/CDD | 15/12/2021 | 14/01/2022 | PADMA ENGINEERING & CO. | 12.61 | 10.54 | 83.56 | 0
8 | HOOGHLY | Jangipara | Central Drilling | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY WITHIN GHATAL BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000172/2021-2022 | 479/ CDD | 07/09/2021 | 07/10/2021 | PADMA ENGINEERING & CO. | 14.74 | 11.14 | 75.61 | 0
9 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Electric Supply |  |  | VCH/001992/2022-2023 | 13 | 04/07/2022 |  | WBSEDCL | 19.89 | 0 | 0 | 0
10 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Construction of Protection Wall at O.H.R. Site from Flood Water for Bilaspur Zone-I Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000111/2022-2023 | 449/SER | 31/05/2022 | 15/07/2022 | PRADIP KUMAR ADHYA | 4.99 | 4.97 | 99.66 | 0
11 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-II, TW-I, Dist- Hooghly |  |  | ORD/000096/2022-2023 | 779/ED | 05/05/2022 | 03/08/2022 | H.K.DAS & CO. | 10.5 | 10.5 | 99.95 | 0
12 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-I, TW-I, Dist- Hooghly |  |  | ORD/001165/2021-2022 | 778/ED | 05/02/2022 | 06/05/2022 | M/S DAS ENTERPRISE | 10.52 | 10.26 | 97.55 | 0
13 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Fuel Charge |  |  | BILL/00783/2022-2023 | 157 | 10/02/2023 |  | DEBASHISH GHOSH | 0.17 | 0 | 0 | 0
14 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Fuel Charge |  |  | BILL/00784/2022-2023 | 158 | 10/02/2023 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0 | 0
15 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | car hire charges |  |  | BILL/00785/2022-2023 | 157 | 10/02/2023 |  | DEBASHISH GHOSH | 0.15 | 0 | 0 | 0
16 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | fuel charges |  |  | BILL/00786/2022-2023 | 158 | 10/02/2023 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.07 | 0 | 0 | 0
17 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Hire Charges |  |  | BILL/00787/2022-2023 | 157 | 10/02/2023 |  | DEBASHISH GHOSH | 0.18 | 0 | 0 | 0
18 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Fuel Charges |  |  | BILL/00788/2022-2023 | 158 | 10/02/2023 |  | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
19 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bilaspur water supply scheme Zone-I, T.W. No. II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00856/2022-2023 | null | 27/02/2023 |  | A.S. ENTERPRISE | 10.23 | 0 | 0 | 0
20 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000261/2022-2023 | 610/Hug | 02/03/2023 |  | Resource Division | 39.18 | 0 | 0 | 0
21 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply & installation of LED board and outside display board for depicting details of pump/valve operators at Zone-I, P.H. No.I & II of Bilashpur w/s scheme, Dist.-Hooghly under ED, PHE Dte. |  |  | ORD/000362/2022-2023 | 2410/HMSD | 30/12/2022 | 09/01/2023 | DIPA CHHETRI | 0.84 | 0.84 | 100 | 0
22 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Bilaspur W/S. Sch. TW- II, Z-I, Hooghly |  |  | ORD/000862/2022-2023 | 913 /ED | 07/06/2022 | 05/09/2022 | A.S. ENTERPRISE | 10.48 | 10.23 | 97.55 | 0
23 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1107/3/HUG | 17/04/2023 |  | Resource Division | 6.16 | 0 | 0 | 0
24 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000313/2023-2024 | 1384/10/Hug | 15/05/2023 |  | Resource Division | 38.51 | 0 | 0 | 0
25 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, Delivery & Installation of S/P/M & other E/M allied works for Bilaspur W/S. Sch. Hooghly Z-II, TW-II |  |  | ORD/000361/2022-2023 | 780/,ED | 05/05/2022 | 03/08/2022 | TAMAL ENTERPRISE | 10.55 | 10.51 | 99.67 | 5
26 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Bilaspur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House, 450 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, DiSt- Hooghly under Hooghly Divn.PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2022-2023 | 639/Hug | 01/04/2022 | 13/04/2022 | PRADIP KUMAR ADHYA | 447.88 | 383.81 | 85.7 | 25
27 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 986/Hug | 19/05/2022 |  | Resource Division | 33.77 | 0 | 0 | 0
28 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 987/Hug | 19/05/2022 |  | Resource Division | 9.33 | 0 | 0 | 0
29 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BORHAL ZONE I Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000858/2023-2024 | 740/HUG | 05/03/2024 | 04/05/2024 | RAJU CONSTRUCTION | 32.26 | 0 | 0 | 0
30 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BILASPUR (ZONE-II) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000753/2023-2024 | 388/HUG | 08/02/2024 | 08/04/2024 | PRADIP KUMAR ADHYA | 31.66 | 0 | 0 | 0
31 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall, and rising main with interconnection and left out repairing of Concrete Road at Bilaspur W/s Scheme(Zone-I), Jangipara Block under Hooghly Division PHE Dte. Source Augmentation. |  |  | ORD/000890/2023-2024 | 814/HUG | 11/03/2024 | 09/06/2024 | PRADIP KUMAR ADHYA | 64 | 0 | 0 | 0
32 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BILASPUR ZONE II Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000884/2023-2024 | 808/HUG | 11/03/2024 | 10/05/2024 | RAJU CONSTRUCTION | 31.46 | 0 | 0 | 0
33 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000780/2023-2024 | 537/HUG | 20/02/2024 | 06/03/2024 | SRI KRISHNA ENTERPRISE | 12.1 | 3.15 | 26.05 | 60
34 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Quotation bill for new service connection charges at Bilaspur PWSS Zone-II, P.H. No.-III, Hooghly. Application No. 5004065667 Ref ID: 503592945 |  |  | BILL/00111/2024-2025 | 45 | 09/04/2024 |  | WBSEDCL | 3.62 | 0 | 0 | null
35 | HOOGHLY | Jangipara | Electrical | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone-II, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002578/2023-2024 | 454/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
36 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Borhal Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000852/2023-2024 | 734/HUG | 05/03/2024 | 03/07/2024 | SRI KRISHNA ENTERPRISE | 18.31 | 16.73 | 91.39 | 90
37 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Bilaspur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (New Scheme) (2nd Call) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000011/2022-2023 | 755/Hug | 11/04/2022 | 23/04/2022 | S. HATI | 507.65 | 507.48 | 99.97 | 99
38 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Balance LDS and Other works within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000784/2023-2024 | 531/HUG | 20/02/2024 | 06/03/2024 | GOURI ENTERPRISE | 13.52 | 13.35 | 98.7 | 99
39 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000805/2023-2024 | 589/HUG | 22/02/2024 | 23/03/2024 | ROY ENTERPRISE | 13.53 | 6.72 | 49.71 | 50
40 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Laying of Balance portion of Additional Pipeline including other allied works at Borhal Mouza in Bilaspur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000806/2023-2024 | 590/HUG | 22/02/2024 | 21/06/2024 | BAKSHI ENTERPRISE | 17.55 | 10.02 | 57.11 | 75
41 | HOOGHLY | Jangipara | Hooghly Division | Bilaspur Piped Water Supply Scheme. | SM/09825 | New | Construction of balance portion of Boundary Wall, Land Development, Pathway, Drain at H/W Site & 2nd T/W Site and Other allied works at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000662/2023-2024 | 3561/HUG | 06/12/2023 | 04/02/2024 | PRADIP KUMAR ADHYA | 51.59 | 25.25 | 48.94 | 80
Total | [13 empty] | 1660.39 | 1065.37 | 64.16