## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Haripal Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000227/2022-2023 | 270/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.83 | 2.84 | 100.3 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Route Survey, Design Drawing & DPR Preparation of HARIPAL ZONE-II PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000230/2022-2023 | 275/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.45 | 3.21 | 93.03 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Balance work for special repairing of UPVC pipeline damaged due to construction of road with drain of PWD at Balarampur of Ashutosh G.P. under the command area of Haripal water supply scheme under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000450/2022-2023 | 337/CHAN | 12/07/2022 | 22/07/2022 | GOUR KUMAR DAS | 3.88 | 3.05 | 78.64 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 2686/8/Hug | 01/12/2022 |  | Resource Division | 0.33 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2022-2023 | 01/02/Hug | 02/01/2023 |  | Resource Division | 11.94 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000673/2022-2023 | 1345/HUG | 29/06/2022 | 29/07/2022 | SOUMYADIP DE | 110.86 | 70.82 | 63.88 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000459/2022-2023 | 2510/HUG | 22/11/2022 | 06/01/2023 | SPG ENTERPRISES | 27.65 | 26.53 | 95.95 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | "Quotation Bill for New Service Connection at of Haripal W/S. Sch. |  |  | BILL/01913/2022-2023 | 01 | 11/04/2023 |  | WBSEDCL | 5.42 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Quotation for New Service Connection of Haripal W/S scheme(Aug),Zone-II,PH No-II Hooghly under Electrical Division PHE Dte |  |  | BILL/00730/2023-2024 | 16 | 02/05/2023 |  | WBSEDCL | 3.78 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 1383/13/Hug | 15/05/2023 |  | Resource Division | 11.2 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000448/2022-2023 | 2499/HUG | 22/11/2022 | 22/12/2022 | B.R SUPPLIERS | 13.81 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CANDANNAGORE SUB-DIVISION, PHE DTE. UNDER HOOGHLY DIVISION, PHE DTE. |  |  | BILL/00158/2023-2024 | BP-2023-24-136 | 15/06/2023 |  | GOUR KUMAR DAS | 0.77 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Chak Ananta (Part) Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6 M X 3.0M )& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000163/2022-2023 | 1563/HUG | 29/07/2022 | 12/09/2022 | M/S R.M. CONSTRUCTION | 142.15 | 88.36 | 62.16 | 70
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | REPAIRING OF ROAD FROM MAHESHPUR TO BHAUSANARA PART OF ANANTAPUR |  |  | BILL/00431/2023-2024 | BP-2023-24-361 | 12/09/2023 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 32.06 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Horizontal road crossing by trenchless method at Gopinagar More of Baidyabati- Tarakeswar Road (SH-12)and Haripal Station to Basudevpur More Road under Haripal (Zone-II) PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000484/2023-2024 | 2830/HUG | 14/09/2023 | 14/10/2023 | SOUMYADIP DE | 8.98 | 8.98 | 100 | 100
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Haripal Jagajibanpur Road Restoration |  |  | BILL/00498/2023-2024 | BP-2023-24-399 | 26/09/2023 |  | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 18.03 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS within Aminpur & Chandinagar (Part) Mouza at HARIPAL Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000442/2022-2023 | 1347/Hug | 29/06/2022 | 25/04/2023 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 183.24 | 145.88 | 79.61 | 50
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) & Aminpur Mouza & Functional Household tap Connection, Construction of Boundary Wall & Switch Room at Proposed 2nd T.W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000443/2022-2023 | 2472/HUG | 18/11/2022 | 02/01/2023 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 157.64 | 142.45 | 90.36 | 80
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2021-2022 | 157/6/Hug | 24/01/2022 |  | Resource Division | 1.03 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 1125/HUG | 06/06/2022 |  | Resource Division | 10.98 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2021-2022 | 423/3/Hug | 07/03/2022 |  | Resource Division | 25.98 | 0 | 0 | 0
23 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Haripal water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000213/2022-2023 | 840/ED | 14/02/2023 | 15/05/2023 | DAS ENTERPRISE | 32.23 | 10.71 | 33.22 | 50
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | DAMAGED PIPELINE OF PMGSY ROAD FROM NANDAKUTHI TO DALALPUR UNDER HARIPAL BLOCK |  |  | BILL/00931/2023-2024 | BP-2023-24-676 | 22/12/2023 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 16.03 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000136/2022-2023 | 1345/Hug | 29/06/2022 | 26/03/2023 | SOUMYADIP DE | 110.86 | 30.83 | 27.81 | 99
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Krishnapur, Chak Ananta(Part), Haripal, Chandinagar(Part), Kamar Chandi Mouza & Functional Household tap Connection, Rising Main at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000569/2022-2023 | 1599/HUG | 04/08/2022 | 18/09/2022 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 193.1 | 143.91 | 74.53 | 100
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) Mouza & Functional Household tap Connection, Rising Main, Construction of Boundary Wall & Switch Room at H/W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000704/2022-2023 | 426/HUG | 15/02/2023 | 01/04/2023 | SOUMYADIP DE | 128.29 | 100.99 | 78.72 | 100
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of BANIDPUR PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000072/2023-2024 | 1281/HUG | 04/05/2023 | 18/06/2023 | AYUSH ENTERPRISE | 93.94 | 88.45 | 94.15 | 100
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Gopinagar, Aminpur and Khamarchandi Village of Haripal Zone II and it's adjoining mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte [Block- Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000897/2023-2024 | 820/HUG | 11/03/2024 | 10/04/2024 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 6.63 | 0 | 0 | 0
30 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000946/2023-2024 | 1381/HMSD | 14/06/2023 | 15/12/2023 | DEBASHISH GHOSH | 0.87 | 0.84 | 96.32 | 20
31 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Renovation of existing building to make new laboratory building under CHANDANNAGAR Sub-Divn. of Hooghly Division, P.H.E. Dte. at Haripal head work site of Haripal (Zone - I) water supply scheme. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000588/2023-2024 | 3230/HUG | 03/11/2023 | 03/12/2023 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 10.53 | 0 | 0 | 100
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | REGARDING DAMAGE OF PMGSY -III ROAD NAMELY NANDAKUTHI TO DALAPATIPUR PACKAGE NO.WB 08 350 UNDER HARIPAL BLOCK CAUSED BY LAYING OF PHE PIPE LINE. |  |  | BILL/01804/2023-2024 | BP-2024-25-3 | 08/04/2024 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 21 | 0 | 0 | 0
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | REGARDING DAMAGE OF PMGSY -III ROAD NAMELY NANDAKUTHI TO DALAPATIPUR PACKAGE NO.WB 08 350 UNDER HARIPAL BLOCK CAUSED BY LAYING OF PHE PIPE LINE. |  |  | BILL/01804/2023-2024 | BP-2024-25-3 | 08/04/2024 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 21 | 0 | 0 | 0
Total | [13 empty] | 1499.84 | 867.85 | 57.86