## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Route Survey, Design Drawing & DPR Preparation of DWIPA PWSS under Chandannagar Sub Division , PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000477/2021-2022 | 169/chan | 24/03/2022 | 13/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at DWIPA PWSS (3rd & 4th Tube Well Site) of Chandannagar Sub-Division under Hooghly Division, PHE Dte. SL NO - 12 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000346/2022-2023 | 1999/HUG | 12/09/2022 | 27/10/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 26 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 2686/6/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.34 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dwipa water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000208/2022-2023 | 835/ED | 14/02/2023 | 15/05/2023 | M/S PS & ASSOCIATES | 21.49 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 1125/2/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 11.52 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2021-2022 | 423/5/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 25.98 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 01/08/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 11.94 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000294/2023-2024 | 1383/40/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.38 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000236/2022-2023 | 109/ 9/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 34.08 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-I |  |  | BILL/00904/2022-2023 | 183 | 10/03/2023 | 10/03/2023 | WBSEDCL | 0.65 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-II |  |  | BILL/00905/2022-2023 | 183 | 10/03/2023 | 10/03/2023 | WBSEDCL | 3.08 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Dwipa PWSS, Enayetpur PWSS, Haripal zone-I PWSS, Haripal zone-II PWSS, Olipur zone-I PWSS, Olipur zone-II PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000972/2023-2024 | 301/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR JANGIPARA ROAD |  |  | BILL/00668/2024-2025 | BP-2024-25-500 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 13.12 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | SM/09983 | Augmentation | Augmentation of DWIPA Water Supply Scheme with Construction of 600 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS, Switch room, Boundary wall,Rising Main,FHTC Work,Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000046/2022-2023 | 830/Hug | 20/04/2022 | 02/04/2025 | P.B. ENTERPRISE (PINTU BHADURI) | 724.25 | 0 | 0 | 80
Total | [13 empty] | 889.01 | 0 | 0