## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Route Survey, Design Drawing & DPR Preparation Beraberi PWSS under Chandannagar Sub Division , PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000476/2021-2022 | 168/chan | 24/03/2022 | 13/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 4.13 | 98.97 | 0
2 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000084/2022-2023 | 371/CMSD-II(D) | 29/07/2022 | 13/08/2022 | C.M. ENTERPRISE | 4.97 | 4.55 | 91.54 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-II, HARTIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000085/2022-2023 | 370/CMSD-II(D) | 29/07/2022 | 13/08/2022 | C.M. ENTERPRISE | 2.93 | 2.75 | 94.02 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBEWELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000086/2022-2023 | 369/CMSD-II(D) | 28/07/2022 | 12/08/2022 | C.M. ENTERPRISE | 3.52 | 2.6 | 73.84 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | SUPPLY 7 DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKKS FOR CONSTRUCTION OF TUBE WELL aUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000083/2022-2023 | 372/CMSD-II(D) | 29/07/2022 | 13/08/2022 | C.M. ENTERPRISE | 3.52 | 2.62 | 74.36 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITHJ OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000087/2022-2023 | 368/CMSD-II(D) | 28/07/2022 | 12/08/2022 | C.M. ENTERPRISE | 4.97 | 4.62 | 93.12 | 0
7 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000088/2022-2023 | 367/CMSD-II(D) | 28/07/2022 | 12/08/2022 | C.M. ENTERPRISE | 2.93 | 2.78 | 94.91 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Electricity Bill New Connection |  |  | VCH/002508/2022-2023 | null | 13/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.03 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | New Connection of Electricity |  |  | VCH/002509/2022-2023 | null | 13/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0 | 0
10 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000108/2022-2023 | 375/CMSD-II (D) | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 4.97 | 4.7 | 94.69 | 0
11 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING DRILLINGCREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000107/2022-2023 | 374/CMSD-II (D) | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 2.93 | 2.75 | 94.02 | 0
12 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000109/2022-2023 | 376/CMSD-II (D) | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 3.52 | 2.6 | 73.91 | 0
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | New Connection |  |  | VCH/002536/2022-2023 | 80 | 16/09/2022 |  | WBSEDCL | 6.36 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Quotation bill for New Connection at Beraberi W/S. Sch. PH-III |  |  | BILL/00012/2022-2023 | BP-2022-23-111 | 14/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.54 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2022-2023 | 2686/13/Hug | 01/12/2022 |  | Resource Division | 0.35 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2022-2023 | 01/09/Hug | 02/01/2023 |  | Resource Division | 11.94 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000035/2022-2023 | 1918/ED | 21/11/2022 | 19/02/2023 | GLACIER ENGINEERING CO. | 10.67 | 10.38 | 97.32 | 0
18 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | FUEL CHARGES FOR CAR NO - WB-04H-6870 |  |  | BILL/00023/2023-2024 | BP-2023-24-13 | 24/04/2023 |  | MIRA SERVICE STATION | 0.19 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000299/2023-2024 | 1383/43/Hug | 15/05/2023 |  | Resource Division | 7.81 | 0 | 0 | 0
20 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | CONTINUATION FOR HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000360/2022-2023 | 35/CMSD-II | 10/02/2023 | 25/02/2023 | ASHUTOSH PAL | 0.29 | 0.29 | 98.36 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001361/2022-2023 | 1548/ED | 20/09/2022 | 19/12/2022 | PERFECT AIRCONDITION | 9.66 | 9.4 | 97.26 | 0
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000466/2023-2024 | 3058/Hug | 11/10/2023 |  | Resource Division | 30.27 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2021-2022 | 157/4/Hug | 24/01/2022 |  | Resource Division | 2.58 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 1125/7/HUG | 06/06/2022 |  | Resource Division | 10.98 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2021-2022 | 423/3/Hug | 07/03/2022 |  | Resource Division | 25.98 | 0 | 0 | 0
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Augmentation of BERABARI Water Supply Scheme with Construction of 600 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS(S-2) & Functional Household tap Connection within Chak Kalikabari, Beraberi, Jampukur, Madhusudanpur, Khaser Bheri & Khagragachhi Mouza, Switch room, Boundary wall, Rising Main, Repairing of existing Switch Rooms at Singur Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000139/2022-2023 | 1383/Hug | 07/07/2022 | 03/05/2023 | S & P ENTERPRISE | 461.01 | 424.94 | 92.18 | 50
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001023/2023-2024 | 3379/HUG | 21/11/2023 | 05/01/2024 | OSMAN SEKH | 64.2 | 7.99 | 12.44 | 100
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Augmentation of BERABARI Water Supply Scheme with Laying Distribution System (S-1) & Functional Household Tap Connection at Baje Melia & Hijli Mouzas, Construction of Switch room at Proposed T.W Site, Boundary wall at Singur Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000682/2022-2023 | 1583/HUG | 02/08/2022 | 16/10/2022 | M/S BISWAS CONSTRUCTION | 246.26 | 204.24 | 82.94 | 50
29 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001275/2022-2023 | 1792/ED | 02/11/2022 | 31/01/2023 | ALPHA ENTERPRISE | 10.67 | 10.38 | 97.31 | 99
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Providing connection in leftout portion of beraberi mouza under Beraberi water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000052/2024-2025 | 2341/HUG | 19/06/2024 | 19/07/2024 | MAA TARA CONSTRUCTION | 31.82 | 0 | 0 | 0
31 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Quotation for new service connection at Beraberi W/S Sch. , T/W No. - V [SM/09984] , Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503614887, dt. - 12/04/2024, Application No. - 5004104119 |  |  | BILL/00188/2024-2025 | 75 | 18/04/2024 |  | WBSEDCL | 4.1 | 0 | 0 | null
32 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Quotation for new service connection at Beraberi W/S Sch. , T/W No. - V [SM/09984] , Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503614887, dt. - 12/04/2024, Application No. - 5004104119 |  |  | BILL/00188/2024-2025 | 75 | 18/04/2024 |  | WBSEDCL | 4.1 | 0 | 0 | null
33 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. V, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/002478/2023-2024 | 338/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.41 | 2.43 | 23.36 | 90
34 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BERABERI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000751/2023-2024 | 386/HUG | 08/02/2024 | 08/04/2024 | BHATTACHARJEE CONSTRUCTION | 15.56 | 6.74 | 43.29 | 100
Total | [13 empty] | 1012.51 | 710.89 | 70.21