## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Enayetpur Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000293/2021-2022 | 2204/Hug | 14/12/2021 | 12/02/2022 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 40.46 | 41.84 | 103.41 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Repairing of 3.6 mtr x 3.0 mtr size existing pump house of Enayetpur PWSS scheme under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000401/2021-2022 | 657/chan | 27/12/2021 | 26/01/2022 | SURAJIT SINGHA RAY | 2.76 | 2.67 | 96.71 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Interconnection of replacement tube wells with existing Rising main at HWS of Enayetpur Water Supply Scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000568/2021-2022 | 532/Chan | 12/11/2021 | 27/11/2021 | SWASTIK ENTERPRISE | 2.29 | 2.03 | 88.4 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000176/2021-2022 | 172/CMSD-II | 27/07/2021 | 11/08/2021 | M/S PRACHI ENGINEERING | 4.17 | 4.17 | 100 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | PROVIDING TUBE WELL MATERIALS (200 MM DIA CM PIPE) CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000168/2021-2022 | 175/CMSD-II | 27/07/2021 | 11/08/2021 | KUNDU ELECTRICAL ENTERPRISE | 4.41 | 2.3 | 52.26 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS AT ENAYATPUR PWSS TW-I UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000169/2021-2022 | 339/CMSD-II | 13/09/2021 | 28/09/2021 | S B S ENTERPRISE | 0.42 | 0.35 | 83.33 | 0
7 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000170/2021-2022 | 176/CMSD-II | 27/07/2021 | 26/08/2021 | S B S ENTERPRISE | 4.86 | 3.3 | 67.86 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Route Survey, Design Drawing & DPR Preparation of ENAYETPUR PWSS under Chandannagar Sub Division , PHE Dte. | Assistant Engineer (Civil) |  | ORD/000478/2021-2022 | 170/chan | 24/03/2022 | 13/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.84 | 4.84 | 100 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | ENAYETPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 400 cum capacity OHR with 20mtr. staging height including soil investigation work at HARIPAL Block under Chandannagar Sub- Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000419/2022-2023 | 2298/HUG | 21/10/2022 | 01/09/2025 | P.B. ENTERPRISE (PINTU BHADURI) | 918.91 | 729.36 | 79.37 | 90
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2021-2022 | 157/5/Hug | 24/01/2022 | 24/01/2022 | Resource Division | 3.1 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1125/3/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2021-2022 | 423/2/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 25.98 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Central Drilling Payment |  |  | VCH/002416/2021-2022 | C022228292462 | 09/02/2022 | 09/02/2022 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Enayetpur water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000209/2022-2023 | 836/ED | 14/02/2023 | 15/05/2023 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room, boundary wall & Repairing of Existing OHR, Switch Rooms, Boundary walls at different TW sites for Augmentation of ENAYETPUR Piped Water Supply Scheme under HARIPAL Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000040/2023-2024 | 1162/HUG | 20/04/2023 | 01/09/2025 | P.B. ENTERPRISE (PINTU BHADURI) | 70.38 | 23.04 | 32.74 | 45
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 1383/14/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 23.96 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000228/2022-2023 | 109/5/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 104.08 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR BAIDYABATI TARAKESWAR CHAMPADANGA ROAD |  |  | BILL/00666/2024-2025 | BP-2024-25-498 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 10.6 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | SM/10004 | Augmentation | Estimate for repairing and shifting damaged pipeline under culvert at Enayetpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000243/2025-2026 | 893/CHAN | 21/07/2025 | 05/08/2025 | G.K ENTERPRISE (GOUR KUMAR DAS) | 1.7 | 0 | 0 | 100
Total | [13 empty] | 1311.76 | 813.89 | 62.05