## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Champadanga PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000224/2022-2023 | 261/CHAN | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.96 | 4.96 | 99.88 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Laying of HDPE distribution pipe due to widening & construction of 4-lane of champadanga-Chanditala road under WBHDCL for providing water supply at Champadanga water supply scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000359/2022-2023 | 208/HUG | 13/04/2022 | 28/04/2022 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.67 | 4.65 | 99.63 | 0
3 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. CHAMPADANGA PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000210/2022-2023 | 382/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 4.97 | 4.31 | 86.82 | 0
4 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSUMBLES OF TUBEWELL AT AUG. OF CHAMPADANGA PWSS, TARAKESSWAR BLOCK, HOOGHLY BLOCK UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000209/2022-2023 | 383/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 4.68 | 2.64 | 56.39 | 0
5 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF CHAMPADANGA PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000207/2022-2023 | 381/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 3.34 | 3.16 | 94.76 | 0
6 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | SUPPLY & DELIVERY OF BATS AT SITE FOR MAKING APPROACH ROADS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT CHAMPADANGAPWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000211/2022-2023 | 464/CMSD-II | 27/09/2022 | 04/10/2022 | C.M. ENTERPRISE | 0.26 | 0.25 | 93.67 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 2686/3/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.33 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000279/2022-2023 | 946/ED | 22/02/2023 | 23/05/2023 | STANDARD ELECTRICALS | 21.96 | 0 | 0 | 0
9 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAMPADANGA UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000330/2022-2023 | 1677/CDD | 28/12/2022 | 27/01/2023 | C.M. ENTERPRISE | 11.34 | 9.18 | 80.93 | 0
10 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAMPADANGA, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000342/2022-2023 | 575/CMSD-I | 30/11/2022 | 07/12/2022 | C.M. ENTERPRISE | 0.98 | 0.86 | 87.5 | 0
11 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Hiring of Diesel Driven Motor Vab (BS-III & Above) (Non AC) hiving contract carriage permit along with driven for office of the Calcutta Mechanical Sub Division -I, PHE Dte. under CMSD-II (D), CDD, PHE Dte. |  |  | ORD/000425/2022-2023 | 40/CMSD-II(D) | 16/02/2023 | 16/07/2023 | SUJATA BHOWMICK | 0.87 | 2.28 | 262.02 | 51
12 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at TARAKESWAR Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000086/2022-2023 | 218/chan | 13/04/2022 | 03/05/2022 | M/S S.G. CONSTRUCTION | 4.97 | 4.97 | 100 | 0
13 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2021-2022 | 423/6/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 25.98 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1370/2/Hug | 06/07/2022 | 06/07/2022 | Resource Division | 133.19 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000208/2022-2023 | 109/ 18/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 96.26 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 01/01/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 11.94 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000278/2023-2024 | 1383/28/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.78 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | QUOTATION BILL ON ACCOUNT OF WBSEDCL FOR AUGMENTATION OF CHAMPDANGA W/S/S |  |  | BILL/00056/2022-2023 | BP-2022-23-413 | 20/12/2022 | 20/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Augmentation Of Champadanga Water Supply Scheme TW-4 |  |  | BILL/01908/2022-2023 | 250, 251 | 31/03/2023 | 31/03/2023 | WBSEDCL | 6.95 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Horizontal road crossing by trenchless method at Champadanga Pairadinghi kalitala Node(538-541), Champadanga Kalitala Node(256-260), Champadanga Mansatala Node(159-170),DVC Santhashitala(Hanuman Temple) Node(135-138),Muktarpur Electric substation Node(232-234) beside SH 15 & SH 12 under Chandannagar Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000651/2023-2024 | 3481/HUG | 29/11/2023 | 13/01/2024 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 12.41 | 24.8 | 199.87 | 100
21 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Laying of Rising main for Interconnection of Laying distribution system at Laskarpur in Champadanga Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte. (Part A). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000705/2023-2024 | 934/Chan | 30/11/2023 | 15/12/2023 | AMBIAN INFRASTRUCTURE | 0.91 | 0.7 | 77.15 | 100
22 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Laying of Rising main for Interconnection of Laying distribution system at Laskarpur in Champadanga Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte. (Part B). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000718/2023-2024 | 935/Chan | 30/11/2023 | 15/12/2023 | AMBIAN INFRASTRUCTURE | 0.63 | 0.57 | 89.49 | 100
23 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Champadanga PWSS, Naita PWSS, Purbaramnagar PWSS, Ramnaryanpur PWSS, Salepur-Duttapur zone-I PWSS, Salepur-Duttapur zone-II PWSS). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000973/2023-2024 | 302/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
24 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000966/2023-2024 | 294/Chan | 15/03/2024 | 30/03/2024 | MAHABIR CONSTRUCTION | 0.99 | 0 | 0 | 99
25 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000967/2023-2024 | 295/Chan | 15/03/2024 | 30/03/2024 | MAHABIR CONSTRUCTION | 0.95 | 0 | 0 | 95
26 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000968/2023-2024 | 298/Chan | 15/03/2024 | 30/03/2024 | MAHABIR CONSTRUCTION | 0.98 | 0 | 0 | 99
27 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Augmentation of CHAMPADANGA Water Supply Scheme with Laying Distribution System within MOKTARPUR & LASKARPUR Mouza, Construction of Switch room & Boundary wall for Proposed Switch Room-IV, Repairing of existing Switch Room-III & Boundary Wall & FHTC Work within MOKTARPUR & LASKARPUR Mouza at Tarakeswar Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000049/2022-2023 | 833/Hug | 20/04/2022 | 31/03/2025 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 348.19 | 277.19 | 79.61 | 100
28 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Augmentation of CHAMPADANGA Water Supply Scheme with Construction of 750 cum capacity OHR with 20 mtr. staging height including Soil Investigation work , Laying Distribution System Within CHAMPADANGA & SACHAK Mouza, Construction of Switch rooms at Proposed Pump House-V, Boundary wall at Proposed 5th T.W Site, Rising Main, FHTC Work, Repairing of existing Switch Rooms & Boundary Wall of Existing T.W-1 & 2 at Tarakeswar Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000499/2022-2023 | 1151/HUG | 09/06/2022 | 26/01/2026 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 687.43 | 585.19 | 85.13 | 95
29 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Left OutPortion of LDS AND FHTC Work of champadanga Water Supply Scheme under mouza champadanga and sachak Under chandannagar Sub-Division of Hooghly Division,P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000656/2023-2024 | 3522/HUG | 30/11/2023 | 16/12/2025 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 96.7 | 25.04 | 25.9 | 95
30 | HOOGHLY |  | Central Drilling | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, , Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000034/2024-2025 | 188/S&WSD | 25/09/2024 | 26/03/2025 | SUJIT DAS | 0.86 | 1.12 | 129.52 | 0
31 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Necessary Maintenance Work for Improvement of water supply in distribution system at Laskarpur & Muktarpur mouza under Champadanda Water Supply Scheme under Chandannagar Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000229/2025-2026 | 877/CHAN | 21/07/2025 | 10/08/2025 | ASHA ENTERPRISE | 1.49 | 0 | 0 | 100
32 | HOOGHLY |  | Hooghly Division | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Shifting of UVPC Pipe Line & Allied works for new culvert construction of irrigation at Laskarpur mouza under Champadanga Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000456/2025-2026 | 1004/Chan | 30/07/2025 | 09/08/2025 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 0.96 | 0 | 0 | 0
33 | HOOGHLY |  | Electrical | Augmentation of Champadanga Water Supply Scheme | SM/10005 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000237/2022-2023 | 868/ED | 14/02/2023 | 28/02/2025 | STANDARD ELECTRICALS | 21.96 | 21.95 | 99.95 | 95
Total | [13 empty] | 1520.55 | 974.77 | 64.11