## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Repairing of 5.4 mtr. x 3.4 mtr. size existing pump house of Olipur PWSS under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000594/2021-2022 | 535/CHAN | 12/11/2021 | 12/12/2021 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.58 | 3.43 | 95.89 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Repairing of 5.4 mtr x 3.6 mtr. size existing pump house of Olipur PWSS scheme under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000595/2021-2022 | 535/CHAN | 15/11/2021 | 15/12/2021 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.58 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Olipur Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000225/2022-2023 | 264/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.93 | 3.86 | 98.1 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Olipur Zone - II PWSS under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000226/2022-2023 | 265/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.02 | 94.79 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Sinking of Four Nos Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at OLIPUR (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000449/2022-2023 | 2500/HUG | 22/11/2022 | 06/01/2023 | M/S SYCHROTECH INDUSTRY | 55.58 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Augmentation of OLIPUR (ZONE-II) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS & Functional Household Tap Connection, Construction of 3 Nos.Switch Room (1No. 5.4 M x 3.6M & 2Nos. 3.6 M x 3.0M) & 2Nos. Boundary Wall at Proposed T.W. Sites & 1No. at O.H.R Site, Laying Rising Main, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000215/2022-2023 | 1720/Hug | 24/08/2022 | 01/06/2025 | S & P ENTERPRISE | 703.13 | 669.49 | 95.22 | 75
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Augmentation of OLIPUR (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS & Functional Household Tap Connection, Construction of 4 Nos.Switch Room(1No. 5.4 M x 3.6M & 3Nos. 3.6 M x 3.0M) & 3 Nos. Boundary Wall at 2nd T.W Site, Proposed T.W Site, O.H.R Site, Laying Rising Main, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Haripal Block junior Enginner,Junior Engineer (Civill) | ORD/000214/2022-2023 | 1719/Hug | 24/08/2022 | 01/06/2025 | S & P ENTERPRISE | 758.77 | 727.35 | 95.86 | 90
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2021-2022 | 157/10/Hug | 24/01/2022 | 24/01/2022 | Resource Division | 1.55 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 1125/1/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 10.98 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2021-2022 | 423/1/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 25.98 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 2686/10/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.34 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 10/08/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 44.35 | 55.13 | 100
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Olipur water supply scheme, T.W. No.- I, II, III & IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000039/2023-2024 | 1716/ED | 18/04/2023 | 17/07/2023 | D. K. ELECTRIC | 42.97 | 42.53 | 98.98 | 45
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2022-2023 | 01/10/Hug | 02/01/2023 | 02/01/2023 | Resource Division | 11.94 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 1383/29/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 10.61 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 2502/Hug | 17/08/2023 | 17/08/2023 | Resource Division | 10.8 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000326/2023-2024 | 1782/Hug | 15/06/2023 | 15/06/2023 | Resource Division | 158.24 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Quotation Bill for New Service Connection at Oilipur W/S. Sch. |  |  | BILL/00055/2023-2024 | 03 | 13/04/2023 | 13/04/2023 | WBSEDCL | 0.96 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road Restoration |  |  | BILL/00684/2023-2024 | BP-2023-24-589 | 16/11/2023 | 16/11/2023 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 13 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Quotation Bill for New Service Connection at Aug. of Olipur W/S. Sch. Z-I & II, PH-III & I |  |  | BILL/01882/2022-2023 | 220 | 27/03/2023 | 27/03/2023 | WBSEDCL | 4.54 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | QUOTATION for new Service Connection of Olipur W/S Scheme ,Zone-I,PH No-I, Block-Haripal,Dist-Hooghly under Electrical Division, PHE Dte |  |  | BILL/02000/2023-2024 | 101 | 19/07/2023 | 19/07/2023 | WBSEDCL | 3.26 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | New service connection |  |  | BILL/02598/2023-2024 | 163 | 03/08/2023 | 03/08/2023 | WBSEDCL | 11.4 | 0 | 0 | 0
23 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Quotation for New Service Connection of Olipur W/S Scheme ,Zone-I,PH No-II District-Hooghly under ED,PHE DTe |  |  | BILL/02001/2023-2024 | 100 | 19/07/2023 | 19/07/2023 | WBSEDCL | 1.93 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch room & boundary wall for OLIPUR ZONE-II Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000237/2024-2025 | 3472/HUG | 04/10/2024 | 03/12/2024 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 26.54 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for OLIPUR ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000238/2024-2025 | 3473/HUG | 04/10/2024 | 12/09/2025 | RAJMAHAL ENTERPRISE | 26.48 | 0 | 0 | 80
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | ROAD RESTORATION CHARGES |  |  | BILL/00422/2024-2025 | BP-2024-25-342 | 02/08/2024 | 02/08/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 6.11 | 0 | 0 | 0
27 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for OLIPUR water supply scheme, Zone-II, TW No. IV, Block: Haripal, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/003079/2024-2025 | 477/ED | 18/03/2025 | 16/06/2025 | SUBHRA ENTERPRISE | 11.3 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Balance Laying of Pipeline of Purba Narayanpur Mouzas (JL - 80) of Olipur Zone - II water supply scheme under Chandannagar Sub-Division P.H.E. Dte. |  |  | ORD/002243/2024-2025 | 647/HUG | 10/03/2025 | 09/04/2025 | T.K. INTERNATIONAL | 9.66 | 0 | 0 | 0
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part I) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2025-2026 | 861/CHAN | 22/07/2025 | 11/08/2025 | MAA TARA CONSTRUCTION | 4.89 | 0 | 0 | 50
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part G) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000211/2025-2026 | 859/CHAN | 22/07/2025 | 11/08/2025 | MAA TARA CONSTRUCTION | 4.94 | 0 | 0 | 50
31 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part H) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000212/2025-2026 | 860/CHAN | 22/07/2025 | 11/08/2025 | MAA TARA CONSTRUCTION | 4.89 | 0 | 0 | 50
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Repairing of pump house at Pump Hose No.II under OLIPUR ( Zone - II ) PWSS under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000231/2025-2026 | 881/CHAN | 21/07/2025 | 10/08/2025 | GOURI ENTERPRISE | 2.62 | 0 | 0 | 50
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Estiamte for Road Restoration for Olipur (Zone-II) PWSS under Chandannagar Sub - Division ( Phase - I ) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000250/2025-2026 | 900/CHAN | 21/07/2025 | 05/08/2025 | TOTON MONDAL | 4.9 | 0 | 0 | 50
34 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for OLIPUR water supply scheme, Zone-I, TW No. V, Block: Haripal, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/003082/2024-2025 | 478/ED | 18/03/2025 | 01/10/2025 | GLACIER ENGINEERING CO. | 11.76 | 0 | 0 | 50
35 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Estimate for Road Restoration for Olipur (Zone-II) PWSS under Chandannagar Sub - Division ( Phase - II ) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000315/2025-2026 | 960/CHAN | 23/07/2025 | 07/08/2025 | TOTON MONDAL | 4.94 | 0 | 0 | 50
36 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of OLIPUR PWSS within Bandipur mouza under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001789/2024-2025 | 334/HUG | 05/02/2025 | 07/03/2025 | AYUSH ENTERPRISE | 9.08 | 0 | 0 | 100
37 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000197/2025-2026 | 845/CHAN | 21/07/2025 | 10/08/2025 | MAA TARA CONSTRUCTION | 4.99 | 0 | 0 | 50
38 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000199/2025-2026 | 847/CHAN | 21/07/2025 | 10/08/2025 | MAA TARA CONSTRUCTION | 4.89 | 0 | 0 | 50
39 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part D) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000200/2025-2026 | 848/CHAN | 21/07/2025 | 10/08/2025 | MAA TARA CONSTRUCTION | 4.89 | 0 | 0 | 50
40 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part E) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000201/2025-2026 | 849/CHAN | 21/07/2025 | 10/08/2025 | MAA TARA CONSTRUCTION | 4.95 | 0 | 0 | 50
41 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part F) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000202/2025-2026 | 850/CHAN | 21/07/2025 | 10/08/2025 | MAA TARA CONSTRUCTION | 4.91 | 0 | 0 | 50
42 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part J) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000214/2025-2026 | 862/CHAN | 22/07/2025 | 11/08/2025 | MAA TARA CONSTRUCTION | 4.9 | 0 | 0 | 50
43 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part K) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000215/2025-2026 | 863/CHAN | 22/07/2025 | 11/08/2025 | MAA TARA CONSTRUCTION | 4.9 | 0 | 0 | 50
44 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000198/2025-2026 | 846/CHAN | 21/07/2025 | 10/08/2025 | MAA TARA CONSTRUCTION | 4.9 | 0 | 0 | 50
45 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Refixing of Ferrule (105 nos) from Jhaghra More to Satghari Village under Olipur (Zone - II) PWSS under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2025-2026 | 882/CHAN | 21/07/2025 | 10/08/2025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 1.16 | 0 | 0 | 50
46 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Quotation of New Service Connection for Olipur w/s Scheme,Zone-I, PH No-5 Block-Haripal,Dist-Hooghly under Electrical Division,PHE Dte.(SM/10022) Application No-5004546001, Reference Id-503846910 |  |  | BILL/02993/2024-2025 | 689 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.09 | 0 | 0 | 0
47 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | SM/10022 | Augmentation | Aditional Quotation for dedicated transformer for Olipur w/s Scheme,Zone-I, PH No-2 Block-Haripal,Dist-Hooghly under Electrical Division,PHE Dte.(SM/10022) Application No-100000140568, Reference Id-860339988 |  |  | BILL/01145/2025-2026 |  | 23/06/2025 | 23/06/2025 | WBSEDCL | 7.71 | 0 | 0 | 0
Total | [13 empty] | 2101.15 | 1495.02 | 71.15