## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Route Survey, Design Drawing & DPR Preparation of SOLEPUR-DUTTAPUR ZONE - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000228/2022-2023 | 273/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.76 | 3.23 | 85.67 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Route Survey, Design Drawing & DPR Preparation of SOLEPUR-DUTTAPUR ZONE - II PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000229/2022-2023 | 274/Chan | 31/05/2022 | 20/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.15 | 3.15 | 100 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 2686/5/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.32 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at SOLEPUR DUTTAPUR (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000457/2022-2023 | 2508/HUG | 22/11/2022 | 22/12/2022 | SPG ENTERPRISES | 13.82 | 12.23 | 88.45 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at SOLEPUR DUTTAPUR (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000458/2022-2023 | 2509/HUG | 22/11/2022 | 22/12/2022 | SPG ENTERPRISES | 13.82 | 13 | 94.07 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1690/HUG | 22/08/2022 | 22/08/2022 | Resource Division | 93.17 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000297/2023-2024 | 1383/41/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.14 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Quation Money for Salepur Duttapur PH No-I |  |  | BILL/02007/2023-2024 | 102 | 19/07/2023 | 19/07/2023 | WBSEDCL | 3.35 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Augmentation Of Solepur-Duttapur Water Supply Scheme. TW-3, Z-II |  |  | BILL/01909/2022-2023 | 248 | 30/03/2023 | 30/03/2023 | WBSEDCL | 2.82 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Salepur Duttapur water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer3 | ORD/000226/2022-2023 | 857/ED | 14/02/2023 | 15/05/2023 | ALPHA ENTERPRISE | 21.49 | 21.44 | 99.75 | 45
11 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Augmentation of SALEPURDUTTAPUR (ZONE-I)Water Supply Scheme with LDS & Functional Household tap Connection, Construction of 1 No. Switch Room(3.6 M X 3.0M)& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms & Boundary Wall at Tarakeswar Block under Chandannagar Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000338/2022-2023 | 1952/HUG | 07/09/2022 | 01/01/2025 | UNIQUE AGENCY | 288.28 | 275.2 | 95.46 | 100
12 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of SALEPUR-DUTTAPUR (ZONE-II) Water Supply Scheme with & Laying Rising Main at Tarakeswar Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000137/2022-2023 | 1346/Hug | 29/06/2022 | 25/04/2023 | DAS ENTERPRISE (SAMIR DAS) | 110.01 | 109.92 | 99.93 | 45
13 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Augmentation of SALEPUR-DUTTAPUR (ZONE - II) Water Supply Scheme with LDS & Functional Household Tap Connection, Construction of 1 No. Switch Room (3.6 M X 3.0 M) & Boundary Wall at 2nd T.W. Site, Proposed T.W. Site & O.H.R. Site, Repairing of existing Switch Rooms & Boundary Wall at Tarakswar Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000414/2022-2023 | 2236/Hug | 13/10/2022 | 11/01/2023 | S & P ENTERPRISE | 476.56 | 470.01 | 98.63 | 50
14 | HOOGHLY |  | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme | SM/10023 | Augmentation | Construction of 300 cum capacity OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of SALEPUR-DUTTAPUR (ZONE-I) Water Supply Scheme & Laying Rising Main, at Tarakeswar Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000135/2022-2023 | 1284/Hug | 23/06/2022 | 01/05/2025 | ARUN SEAL AND CO. | 96.23 | 76.33 | 79.31 | 40
Total | [13 empty] | 1131.94 | 984.5 | 86.97