## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME | SM/10131 | Retrofitting | Providing 1002 nos F.H.T.C. in Dakatiar Bheri & Dubir Bheri Village of Dubir Bheri and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | ORD/000336/2020-2021 | 408/Hug | 15/02/2021 | 17/03/2021 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 49.74 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME | SM/10131 | Retrofitting | Providing 1158 nos F.H.T.C. in Karichar Bheri, Maheswarbati & Ugly Village of Dubir Bheri and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | ORD/000337/2020-2021 | 409/Hug | 15/02/2021 | 17/03/2021 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 58.94 | 0 | 0 | 0
Total | [13 empty] | 108.68 | 0 | 0