## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | SM/10133 | Retrofitting | Providing 433 nos Functional Household Tap Connection (FHTC) within the Char Rampur, Chhera Char Krishnabati, Guptipara Char & Sabek Char Krishnabati Mouza of Natunchar Krishnabati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000457/2021-2022 | 475/Hug | 10/03/2022 | 30/03/2022 | BIMAL KUMAR HALDER | 21.7 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | SM/10133 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of NATUN CHAR KRISHNABATI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000421/2022-2023 | 2307/HUG | 28/10/2022 | 27/11/2022 | SARKAR CONSTRUCTION | 33.86 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | SM/10133 | Retrofitting | Providing 867 nos Functional Household Tap Connection (FHTC) within the Natunchar Krishnabati Mouza of Natunchar Krishnabati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000456/2021-2022 | 474/Hug | 10/03/2022 | 19/04/2022 | M/S T.K.B. CONSTRUCTION | 43.24 | 0 | 0 | 25
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | SM/10133 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000167/2021-2022 | 428/1-1/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 10.98 | 0 | 0 | 0
Total | [13 empty] | 109.78 | 0 | 0