## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10134 | Retrofitting | Providing 615 nos Functional Household Tap Connection (FHTC) within the Itagarh & Sargaria Mouzas of Itagarh Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000455/2021-2022 | 473/Hug | 10/03/2022 | 09/04/2022 | THREE MAA ENTERPRISE | 30.63 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10134 | Retrofitting | Providing 385 nos Functional Household Tap Connection (FHTC) within the Bhalki & Malancha Mouzas of Itagarh Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000454/2021-2022 | 472/Hug | 10/03/2022 | 30/03/2022 | SURAJIT SINGHA RAY | 19.2 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10134 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM in ITAGARH PWSS, Block-BALAGARH under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 04 | Assistant Engineer (Civil) |  | ORD/000372/2022-2023 | 2085/HUG | 21/09/2022 | 21/10/2022 | SWARNA ENTERPRISE | 11.4 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10134 | Retrofitting | Laying HDPE pipe and allied repairing works of Itagarh water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000509/2023-2024 | 815/CH | 31/08/2023 | 15/09/2023 | GHOSH CONSTRUCTION | 0.94 | 0 | 0 | 95
Total | [13 empty] | 62.17 | 0 | 0