## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10135 | Retrofitting | Providing 350 nos Functional Household Tap Connection (FHTC) within the Durllabhpur, Gournagar & Raninagar Mouzas of Bhabanipur Char Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000453/2021-2022 | 471/Hug | 10/03/2022 | 09/05/2022 | BOSE ENTERPRISE (RATUL BOSE) | 17.42 | 16.63 | 95.47 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10135 | Retrofitting | Providing 1350 nos Functional Household Tap Connection (FHTC) within the Bhabanipur Char Mouza of Bhabanipur Char Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000452/2021-2022 | 470/Hug | 10/03/2022 | 09/05/2022 | MALLIKA ENTERPRISE | 62.56 | 62.61 | 100.07 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | SM/10135 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BHABANIPUR CHAR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000188/2022-2023 | 1655/Hug | 16/08/2022 | 31/08/2022 | BOSE ENTERPRISE (RATUL BOSE) | 5.19 | 5.18 | 99.9 | 0
Total | [13 empty] | 85.17 | 84.42 | 99.12