## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | SM/10136 | Retrofitting | Providing 489 nos Functional Household Tap Connection (FHTC) within the Bejpara, Radhanagar & Uttar Darshan Mouzas of Shibrai Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000451/2021-2022 | 469/Hug | 10/03/2022 | 09/04/2022 | TAPAS ADHYA | 24.49 | 19.93 | 81.36 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | SM/10136 | Retrofitting | Providing 881 nos Functional Household Tap Connection (FHTC) within the Dakshin Darshan, Pakri & Shibrai Mouzas of Shibrai Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | Assistant Engineer (Civil) |  | ORD/000450/2021-2022 | 468/Hug | 10/03/2022 | 19/04/2022 | SOUMYADIP DE | 44.14 | 28.92 | 65.52 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | SM/10136 | Retrofitting | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 Shibrai PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001918/2024-2025 | 269/CH | 20/02/2025 | 02/03/2025 | AYUSH ENTERPRISE | 3.18 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | SM/10136 | Retrofitting | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site (PH-I) of Shibrai PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001917/2024-2025 | 268/CH | 20/02/2025 | 02/03/2025 | R.K. TRADERS | 4.82 | 0 | 0 | 0
Total | [13 empty] | 76.63 | 48.85 | 63.74