## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan | SM/10248 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Dhaniakhali Block (33 Nos) under Hooghly Division, P.H.E. Dte. (Total 33 Nos) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000038/2022-2023 | 808/Hug | 19/04/2022 | 03/06/2022 | MS PRADIP KUMAR PAL | 59.11 | 0 | 0 | 25
2 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan | SM/10248 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Goghat-II Block (13 Nos), Khanakul-I Block (15 Nos) & Khanakul-II Block (5 Nos) under Hooghly Division, P.H.E. Dte. (Total 33 Nos) | Assistant Engineer |  | ORD/000035/2022-2023 | 805/Hug | 19/04/2022 | 03/06/2022 | DILIP KUMAR GHOSH | 58.9 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan | SM/10248 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division |  |  | RTOR000175/2021-2022 | 510/Hug | 16/03/2022 | 16/03/2022 | Resource Division | 92.24 | 0 | 0 | 0
Total | [13 empty] | 210.24 | 0 | 0