## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Providing 105 nos. tap connection at AWC,School, health center,community centers and GP building in Tarakeswar block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000279/2021-2022 | 516/chan | 01/11/2021 | 21/11/2021 | SWASTIK ENTERPRISE | 4.36 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Providing 125 nos. tap connection at AWC,School, health center,community centers and GP building in Haripal block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000277/2021-2022 | 514/chan | 01/11/2021 | 21/11/2021 | SIKHA ENTERPRISE | 4.69 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Tarakeswar Block (10 Nos), Haripal Block (13 Nos) & Singur Block (17 Nos) under Hooghly Division, P.H.E. Dte. (Total 40 Nos) | Assistant Engineer(HQ) |  | ORD/000036/2022-2023 | 806/Hug | 19/04/2022 | 18/06/2022 | M/S R.M. CONSTRUCTION | 71.55 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Pandua Block (34 Nos) under Hooghly Division, P.H.E. Dte. (Total 34 Nos) | Assistant Engineer(HQ) |  | ORD/000037/2022-2023 | 807/Hug | 19/04/2022 | 03/06/2022 | M/S RAJKUMAR KHAN | 60.36 | 0 | 0 | 35
5 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division |  |  | RTOR000174/2021-2022 | 508/Hug | 16/03/2022 | 16/03/2022 | Resource Division | 35.78 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division |  |  | RTOR000173/2021-2022 | 509/Hug | 16/03/2022 | 16/03/2022 | Resource Division | 19.25 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division |  |  | RTOR000172/2021-2022 | 507/Hug | 16/03/2022 | 16/03/2022 | Resource Division | 35.26 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Chandital-I Block (5 Nos), Chanditala-II Block (16 Nos) & Jangipara Block (2 Nos) under Hooghly Division, P.H.E. Dte. (Total 23 Nos) | Assistant Engineer(HQ) |  | ORD/000041/2022-2023 | 822/Hug | 20/04/2022 | 04/06/2022 | MANISHA ENTERPRISE | 40.95 | 0 | 0 | 95
9 | HOOGHLY |  | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, | SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Chinsurah-Mogra Block (5 Nos) & Balagar Block (10 Nos) under Hooghly Division, P.H.E. Dte. (Total 15 Nos) | Assistant Engineer(HQ) |  | ORD/000039/2022-2023 | 809/Hug | 19/04/2022 | 19/05/2022 | SURAJIT SINGHA RAY | 26.82 | 0 | 0 | 98
Total | [13 empty] | 299.04 | 0 | 0