## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Preparation of DPR for Augmentation of Chanditala (Zone-III & IV) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000472/2021-2022 | 364/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.56 | 3.55 | 99.72 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Preparation of DPR for Augmentation of Chanditala (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000471/2021-2022 | 363/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 4.33 | 100 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II(D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000080/2022-2023 | 235/CMSD-II(D) | 20/05/2022 | 04/06/2022 | S B S ENTERPRISE | 2.79 | 2.79 | 100 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000081/2022-2023 | 238/CMSD-II(D) | 20/05/2022 | 04/06/2022 | M/S S.K.GHOSH & CO. | 1.97 | 1.71 | 86.88 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OGF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR CHANDITALA W/S SCHEME CHANDITALA -II BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000082/2022-2023 | 232/CMSD-II (D) | 20/05/2022 | 04/06/2022 | S B S ENTERPRISE | 2.4 | 2.26 | 93.87 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000079/2022-2023 | 236/CMSD-II(D) | 20/05/2022 | 04/06/2022 | S B S ENTERPRISE | 3.98 | 3.2 | 80.54 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SEAKHALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000495/2021-2022 | 623/Hug | 31/03/2022 | 31/07/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at CHANDITALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000494/2021-2022 | 622/Hug | 31/03/2022 | 31/07/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quatation Bill for Chanditala W/S. Sch. PH-X |  |  | VCH/002744/2022-2023 | null | 16/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for Chanditala W/S. Sch. |  |  | VCH/002752/2022-2023 | 109 | 18/11/2022 |  | WBSEDCL | 0.66 | 0 | 0 | 0
11 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHANDITALA PWSS, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000270/2022-2023 | 1374/CDD | 24/11/2022 | 24/12/2022 | M/S SAIKAT ENTERPRISE | 12.9 | 11.13 | 86.25 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection of WBSEDC at Chanditalaw/s scheme, T.W. No.-XII |  |  | BILL/00777/2022-2023 | 149 | 08/02/2023 |  | WBSEDCL | 0.54 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection of WBSEDC at Chanditala w/s scheme, T.W. No.-XI |  |  | BILL/00778/2022-2023 | 149 | 08/02/2023 |  | WBSEDCL | 0.54 | 0 | 0 | 0
14 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAP (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE SUPERINTENDING ENGINEER, M/E, PMU WBDWSIP UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000313/2022-2023 | 261/CMSD-I | 27/06/2022 | 12/07/2022 | SIDDHARTHA CHATTERJEE | 0.9 | 1.49 | 165.65 | 0
15 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBEWELL AT CHANDITALA, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000319/2022-2023 | 508/CMSDII | 11/11/2022 | 18/11/2022 | SUBHRA ENTERPRISE | 0.98 | 0.9 | 91.58 | 0
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chanditala water supply scheme, T.W. No. X, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000101/2022-2023 | 3529/ED | 30/12/2022 | 30/03/2023 | BISALAXMI ENTERPRISE | 10.66 | 10.65 | 99.95 | 0
17 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Providing drilling crew and other works for construction of TW (300mm x 200mm x 210 mtr. depth) by utilising Departmental machineries for Chanditala PWSS under Hooghly District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000333/2022-2023 | 1561/CDD | 08/12/2022 | 07/01/2023 | SUBHRA ENTERPRISE | 12.67 | 10.2 | 80.53 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala - II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000425/2022-2023 | 1421/HUG | 12/07/2022 | 26/08/2022 | S.B. ASSOCIATES | 78.39 | 44.01 | 56.15 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000322/2023-2024 | 1384/19/Hug | 15/05/2023 |  | Resource Division | 18.64 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanditala water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000202/2022-2023 | 829/ED | 14/02/2023 | 15/05/2023 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 19.69 | 89.31 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Chanditala Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6M X 3.0M ) and Boundary Wall at 10th T.W Site & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000894/2022-2023 | 1418/HUG | 12/07/2022 | 26/08/2022 | EVEREST CONSULTANT SERVICES (SUBRATA KUNDU) | 73.77 | 38.85 | 52.66 | 0
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Barijhati and Thero Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Barijhati) at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000895/2022-2023 | 1419/HUG | 12/07/2022 | 26/08/2022 | CHAKRABORTTI ENTERPRISE | 88.54 | 66.85 | 75.5 | 0
23 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
24 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01122/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 105.92 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Barijhati & Bledanga Mouza & Functional Household tap Connection & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000678/2022-2023 | 1538/HUG | 27/07/2022 | 10/09/2022 | M/S SHIVAM UDYOG | 56.4 | 40.37 | 71.57 | 100
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Garalgacha and Krishnapur Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Garalgacha) at Chanditala-II Block under Serampore Sub-Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000620/2022-2023 | 1539/HUG | 27/07/2022 | 25/09/2022 | DAS TRADING | 86.11 | 64.06 | 74.4 | 100
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1122/2/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 2210/1/Hug | 30/09/2022 |  | Resource Division | 30.8 | 0 | 0 | 0
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1291/2/Hug | 24/06/2022 |  | Resource Division | 9.24 | 0 | 0 | 0
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-III) Water Supply Scheme with LDS within Eklakhi and part of Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000674/2022-2023 | 1420/HUG | 12/07/2022 | 26/08/2022 | BIMAL KUMAR HALDER | 56.66 | 47.65 | 84.09 | 99
31 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augumention of Electro Mechanical Equipments and other electro mechanical accessories at Pump House under Barijhati GP and Garalgacha Gram Panchayet of Chanditala - II Block, Dist-Hooghly under Electrical Divisio, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/001480/2023-2024 | 4892/ED | 27/12/2023 | 26/03/2024 | D. K. ELECTRIC | 31.09 | 15.49 | 49.83 | 100
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000150/2022-2023 | 1421/Hug | 12/07/2022 | 26/08/2022 | S.B. ASSOCIATES | 78.39 | 8.66 | 11.05 | 20
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNARAMPUR (CHANDITALA) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000892/2023-2024 | 816/HUG | 11/03/2024 | 10/05/2024 | CHAKRABORTY ENTERPRISE | 31.68 | 0 | 0 | 0
34 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-I, P.H. No.-V, Hooghly. Application No. 5004085765 Ref ID: 503603819 |  |  | BILL/00032/2024-2025 | 20 | 05/04/2024 |  | WBSEDCL | 3.33 | 0 | 0 | null
35 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-II, P.H. No.-IV, Hooghly. Application No. 5004085812 Ref ID: 503603818 |  |  | BILL/00031/2024-2025 | 19 | 05/04/2024 |  | WBSEDCL | 6.27 | 0 | 0 | null
36 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-II, P.H. No.-IV, Hooghly. Application No. 5004085812 Ref ID: 503603818 |  |  | BILL/00031/2024-2025 | 19 | 05/04/2024 |  | WBSEDCL | 6.27 | 0 | 0 | null
37 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- III, T.W. NO- III, Dist.-Hooghly under PHE Dte. Application No- 5004091705 Reference ID- 503606735 SM Code- 10338 |  |  | BILL/00161/2024-2025 | 70 | 16/04/2024 |  | WBSEDCL | 8.21 | 0 | 0 | null
38 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system,For AUGMENTATION OF of CHANDITALA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000117/2023-2024 | 1446/HUG | 18/05/2023 | 17/06/2023 | SB ASSOCIATES | 31.08 | 14.8 | 47.62 | 70
39 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- I, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004099440 Reference ID- 503611397 SM Code- 18966 |  |  | BILL/00485/2024-2025 | 152 | 22/05/2024 |  | WBSEDCL | 3.84 | 0 | 0 | null
40 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- I, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004099440 Reference ID- 503611397 SM Code- 18966 |  |  | BILL/00485/2024-2025 | 152 | 22/05/2024 |  | WBSEDCL | 3.84 | 0 | 0 | null
41 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 06/01/2024 | SPG ENTERPRISES | 87.88 | 20.97 | 23.87 | 100
42 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 09/01/2024 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 6.71 | 14.23 | 40
43 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Piped water supply scheme at CHANDITALA PANCHGHORA NANDANKANAN area under Chanditala - II block of Hooghly Division. |  |  | ORD/000029/2024-2025 | 2286/HUG | 14/06/2024 | 13/08/2024 | AMBIAN INFRASTRUCTURE | 42.77 | 0 | 0 | 0
44 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XIV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002576/2023-2024 | 452/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 3.47 | 35.79 | 65
45 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at 3rd TW sites for CHANDITALA (PIARAPUR) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000051/2024-2025 | 2340/HUG | 19/06/2024 | 18/08/2024 | MS PRADIP KUMAR PAL | 27.85 | 0 | 0 | 0
46 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall and rising main with interconnection at Chanditala W/s Scheme (Zone-III), Chanditala-II Block under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000741/2023-2024 | 376/HUG | 08/02/2024 | 08/05/2024 | M/S SHIVAM UDYOG | 35.06 | 12.5 | 35.66 | 30
47 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Laying of Balance pipeline and allied works due to road widening work at Chanditala W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000664/2023-2024 | 3562/HUG | 05/12/2023 | 04/01/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 43.61 | 40.54 | 92.96 | 60
48 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Chanditala (Zone-III & IV), Functional Hosuehold Tap Connection at Chanditala Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000747/2023-2024 | 380/HUG | 08/02/2024 | 08/04/2024 | M/S T.K.B. CONSTRUCTION | 58.65 | 19.21 | 32.76 | 30
49 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Switch Room & Boundary Wall at H/W & 2nd TW sites, and Repairing of OHR under CHANDITALA PWSS (Borhal Z-II) under Serampore Sub-Division Of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000900/2023-2024 | 825/HUG | 11/03/2024 | 10/04/2024 | MONDAL ENTERPRISE (PIJUSH MONDAL) | 23.37 | 15.4 | 65.89 | 60
50 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Switch Room & Boundary Wall at H/W & 2nd TW sites, and Repairing of OHR under Chanditala (Borhal Z-I) PWSS under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000903/2023-2024 | 826/HUG | 11/03/2024 | 10/04/2024 | S.S. CONSULTANCY & CONSTRUCTION | 23.46 | 14.33 | 61.07 | 40
51 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XII & XIII, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002504/2023-2024 | 420/ED | 29/02/2024 | 29/05/2024 | DEY ENTERPRISE | 20.85 | 0 | 0 | 40
52 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT CHANDITALA PWSS NEAR EKLAKI UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000148/2024-2025 | 431/SER | 31/07/2024 | 15/08/2024 | SRI KRISHNA ENTERPRISE | 0.36 | 0.17 | 48.65 | 95
Total | [13 empty] | 1425.86 | 545.95 | 38.29