## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Preparation of DPR for Augmentation of Chanditala (Zone-III & IV) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000472/2021-2022 | 364/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.56 | 3.55 | 99.72 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Preparation of DPR for Augmentation of Chanditala (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000471/2021-2022 | 363/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 4.33 | 100 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SEAKHALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000495/2021-2022 | 623/Hug | 31/03/2022 | 31/07/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at CHANDITALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000494/2021-2022 | 622/Hug | 31/03/2022 | 31/07/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II(D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000080/2022-2023 | 235/CMSD-II(D) | 20/05/2022 | 04/06/2022 | S B S ENTERPRISE | 2.79 | 2.79 | 100 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000081/2022-2023 | 238/CMSD-II(D) | 20/05/2022 | 04/06/2022 | M/S S.K.GHOSH & CO. | 1.97 | 1.71 | 86.88 | 0
7 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OGF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR CHANDITALA W/S SCHEME CHANDITALA -II BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000082/2022-2023 | 232/CMSD-II (D) | 20/05/2022 | 04/06/2022 | S B S ENTERPRISE | 2.4 | 2.26 | 93.87 | 0
8 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000079/2022-2023 | 236/CMSD-II(D) | 20/05/2022 | 04/06/2022 | S B S ENTERPRISE | 3.98 | 3.2 | 80.54 | 0
9 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHANDITALA PWSS, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000270/2022-2023 | 1374/CDD | 24/11/2022 | 24/12/2022 | M/S SAIKAT ENTERPRISE | 12.9 | 11.13 | 86.25 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for Chanditala W/S. Sch. |  |  | VCH/002752/2022-2023 | 109 | 18/11/2022 | 18/11/2022 | WBSEDCL | 0.66 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quatation Bill for Chanditala W/S. Sch. PH-X |  |  | VCH/002744/2022-2023 |  | 16/11/2022 | 16/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala - II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000425/2022-2023 | 1421/HUG | 12/07/2022 | 26/08/2022 | S.B. ASSOCIATES | 78.39 | 44.01 | 56.15 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Chanditala Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6M X 3.0M ) and Boundary Wall at 10th T.W Site & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000894/2022-2023 | 1418/HUG | 12/07/2022 | 26/08/2022 | EVEREST CONSULTANT SERVICES (SUBRATA KUNDU) | 73.77 | 38.85 | 52.66 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Barijhati and Thero Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Barijhati) at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000895/2022-2023 | 1419/HUG | 12/07/2022 | 26/08/2022 | CHAKRABORTTI ENTERPRISE | 88.54 | 66.85 | 75.5 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Garalgacha and Krishnapur Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Garalgacha) at Chanditala-II Block under Serampore Sub-Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000620/2022-2023 | 1539/HUG | 27/07/2022 | 25/09/2022 | DAS TRADING | 86.11 | 64.06 | 74.4 | 100
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chanditala water supply scheme, T.W. No. X, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000101/2022-2023 | 3529/ED | 30/12/2022 | 30/03/2023 | BISALAXMI ENTERPRISE | 10.66 | 10.65 | 99.95 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Barijhati & Bledanga Mouza & Functional Household tap Connection & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000678/2022-2023 | 1538/HUG | 27/07/2022 | 10/09/2022 | M/S SHIVAM UDYOG | 56.4 | 40.37 | 71.57 | 100
18 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAP (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE SUPERINTENDING ENGINEER, M/E, PMU WBDWSIP UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000313/2022-2023 | 261/CMSD-I | 27/06/2022 | 12/07/2022 | SIDDHARTHA CHATTERJEE | 0.9 | 1.49 | 165.65 | 0
19 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBEWELL AT CHANDITALA, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000319/2022-2023 | 508/CMSDII | 11/11/2022 | 18/11/2022 | SUBHRA ENTERPRISE | 0.98 | 0.9 | 91.58 | 0
20 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Providing drilling crew and other works for construction of TW (300mm x 200mm x 210 mtr. depth) by utilising Departmental machineries for Chanditala PWSS under Hooghly District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000333/2022-2023 | 1561/CDD | 08/12/2022 | 07/01/2023 | SUBHRA ENTERPRISE | 12.67 | 10.2 | 80.53 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1122/2/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 2210/1/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1291/2/Hug | 24/06/2022 | 24/06/2022 | Resource Division | 9.24 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000322/2023-2024 | 1384/19/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 18.64 | 0 | 0 | 0
25 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection of WBSEDC at Chanditalaw/s scheme, T.W. No.-XII |  |  | BILL/00777/2022-2023 | 149 | 08/02/2023 | 08/02/2023 | WBSEDCL | 0.54 | 0 | 0 | 0
26 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection of WBSEDC at Chanditala w/s scheme, T.W. No.-XI |  |  | BILL/00778/2022-2023 | 149 | 08/02/2023 | 08/02/2023 | WBSEDCL | 0.54 | 0 | 0 | 0
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Piped water supply scheme at CHANDITALA PANCHGHORA NANDANKANAN area under Chanditala - II block of Hooghly Division. |  |  | ORD/000029/2024-2025 | 2286/HUG | 14/06/2024 | 13/08/2024 | AMBIAN INFRASTRUCTURE | 42.77 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNARAMPUR (CHANDITALA) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000892/2023-2024 | 816/HUG | 11/03/2024 | 10/05/2024 | CHAKRABORTY ENTERPRISE | 31.68 | 6.15 | 19.42 | 78
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of Boundary wall,Toilet,Plumbing arrangement,Path way and repairing of Existing Pump House at Pump house No 12ofChanditala water Supply Scheme under Serampur SubDivision;of Hooghly Division P.H.E Dte. |  |  | ORD/000437/2024-2025 | 4041/HUG | 19/12/2024 | 19/03/2025 | TOTON MONDAL | 10.75 | 0 | 0 | 0
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000150/2022-2023 | 1421/Hug | 12/07/2022 | 26/08/2022 | S.B. ASSOCIATES | 78.39 | 17.33 | 22.1 | 20
31 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanditala water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000202/2022-2023 | 829/ED | 14/02/2023 | 01/01/2025 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 19.69 | 89.31 | 95
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-III) Water Supply Scheme with LDS within Eklakhi and part of Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000674/2022-2023 | 1420/HUG | 12/07/2022 | 26/08/2022 | BIMAL KUMAR HALDER | 56.66 | 54.61 | 96.39 | 99
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system,For AUGMENTATION OF of CHANDITALA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000117/2023-2024 | 1446/HUG | 18/05/2023 | 17/06/2023 | SB ASSOCIATES | 31.08 | 14.8 | 47.62 | 70
34 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 06/01/2024 | SPG ENTERPRISES | 87.88 | 28.3 | 32.2 | 100
35 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 04/01/2025 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 23.09 | 48.95 | 40
36 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Laying of Balance pipeline and allied works due to road widening work at Chanditala W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000664/2023-2024 | 3562/HUG | 05/12/2023 | 04/01/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 43.61 | 40.54 | 92.96 | 60
37 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Augumention of Electro Mechanical Equipments and other electro mechanical accessories at Pump House under Barijhati GP and Garalgacha Gram Panchayet of Chanditala - II Block, Dist-Hooghly under Electrical Divisio, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/001480/2023-2024 | 4892/ED | 27/12/2023 | 26/03/2024 | D. K. ELECTRIC | 31.09 | 30.98 | 99.65 | 100
38 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHANDITALA I & SERAMPORE-UTTARPARA Block of Serampore Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000181/2024-2025 | 517/SER | 11/09/2024 | 16/09/2024 | JOY GURU ENTERPRISE | 3.53 | 6.99 | 198.07 | 95
39 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte.(Phase-I) for Serampore Uttarpara, Chanditala-I, Chanditala-II & Jangipara Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000184/2024-2025 | 522/SER | 12/09/2024 | 17/09/2024 | TOTON MONDAL | 4.93 | 4.93 | 100 | 95
40 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte.(Phase-II) for Serampore Uttarpara, Chanditala-I, Chanditala-II & Jangipara Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000185/2024-2025 | 523/SER | 12/09/2024 | 17/09/2024 | TOTON MONDAL | 4.93 | 4.93 | 100 | 95
41 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHANDITALA II Block of Serampore Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000182/2024-2025 | 518/SER | 11/09/2024 | 16/09/2024 | TOTON MONDAL | 4.15 | 4.12 | 99.41 | 95
42 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT CHANDITALA PWSS NEAR EKLAKI UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000148/2024-2025 | 431/SER | 31/07/2024 | 15/08/2024 | SRI KRISHNA ENTERPRISE | 0.36 | 0.35 | 97.31 | 95
43 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-I, P.H. No.-V, Hooghly. Application No. 5004085765 Ref ID: 503603819 |  |  | BILL/00032/2024-2025 | 20 | 05/04/2024 | 05/04/2024 | WBSEDCL | 3.33 | 0 | 0 | 0
44 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-II, P.H. No.-IV, Hooghly. Application No. 5004085812 Ref ID: 503603818 |  |  | BILL/00031/2024-2025 | 19 | 05/04/2024 | 05/04/2024 | WBSEDCL | 6.27 | 0 | 0 | 0
45 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- I, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004099440 Reference ID- 503611397 SM Code- 18966 |  |  | BILL/00485/2024-2025 | 152 | 22/05/2024 | 22/05/2024 | WBSEDCL | 3.84 | 0 | 0 | 0
46 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- III, T.W. NO- III, Dist.-Hooghly under PHE Dte. Application No- 5004091705 Reference ID- 503606735 SM Code- 10338 |  |  | BILL/00161/2024-2025 | 70 | 16/04/2024 | 16/04/2024 | WBSEDCL | 8.21 | 0 | 0 | 0
47 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Estimate for construction of 2 nos Toilets at Piarapur Pump House No-2 and Krishnarampur Pump Hose No-2 under Chanditala PWSS under Serampore Sub - Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001302/2024-2025 | 74/SER | 20/01/2025 | 30/01/2025 | M/S RAJKUMAR KHAN | 3.91 | 0 | 0 | 50
48 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Estimate for jack pushing of Road due to interconnection of Existing pipeline to 3rd Pump House of Krishnarampur mouza under Chanditala W/S Supply scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/001304/2024-2025 | 76/SER | 20/01/2025 | 30/01/2025 | CHAKRABORTY ENTERPRISE | 3.93 | 0 | 0 | 0
49 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at 3rd TW sites for CHANDITALA (PIARAPUR) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000051/2024-2025 | 2340/HUG | 19/06/2024 | 24/05/2025 | MS PRADIP KUMAR PAL | 27.85 | 0 | 0 | 55
50 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Estimate for Reconstruction of boundary wall, Internal Pathway and allied works Head Works Site of Seakhala under Chanditala Water Supply Scheme under Serampore sub Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000014/2025-2026 | 285/SER | 17/04/2025 | 12/05/2025 | M/S RAJKUMAR KHAN | 4.68 | 0 | 0 | 92
51 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Balance works for laying of water supply pipeline by HDD process under Chanditala Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. |  |  | ORD/002253/2024-2025 | 652/HUG | 10/03/2025 | 09/04/2025 | M/S SHIVAM UDYOG | 35.39 | 0 | 0 | 0
52 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall and rising main with interconnection at Chanditala W/s Scheme (Zone-III), Chanditala-II Block under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000741/2023-2024 | 376/HUG | 08/02/2024 | 01/01/2025 | M/S SHIVAM UDYOG | 35.06 | 12.5 | 35.66 | 30
53 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Chanditala (Zone-III & IV), Functional Hosuehold Tap Connection at Chanditala Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000747/2023-2024 | 380/HUG | 08/02/2024 | 01/01/2025 | M/S T.K.B. CONSTRUCTION | 58.65 | 19.21 | 32.76 | 30
54 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Switch Room & Boundary Wall at H/W & 2nd TW sites, and Repairing of OHR under Chanditala (Borhal Z-I) PWSS under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000903/2023-2024 | 826/HUG | 11/03/2024 | 29/11/2024 | S.S. CONSULTANCY & CONSTRUCTION | 23.46 | 14.33 | 61.07 | 99
55 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Providing Additional 80 nos. Functional Household Tap Connection (FHTC) within Jangalpara and KrishnarampurMouzas of Krishnarampur W/S Scheme under Chanditala -I Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000338/2024-2025 | 636/SER | 05/11/2024 | 06/09/2025 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.98 | 0 | 0 | 96
56 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repair & Renovation of the Office Building of the Serampore Sub-Division under Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000344/2024-2025 | 642/SER | 05/11/2024 | 12/11/2024 | MAA TARA CONSTRUCTION | 4.29 | 0 | 0 | 80
57 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of structural shed for storing Mechanical pumps and machineries at Garalgacha OHR work site under Chanditala PWSS under Serampur Sub division within Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001301/2024-2025 | 73/SER | 20/01/2025 | 30/01/2025 | JOY GURU ENTERPRISE | 4.88 | 0 | 0 | 90
58 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different mouzas (Thero) of CHANDITALA W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001351/2024-2025 | 48/SER | 20/01/2025 | 27/01/2025 | PANKAJ KUMAR MANNA | 4.85 | 4.85 | 100 | 90
59 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Construction of structural shed for storing Mechanical pumps and machineries at Chanditala OHR work site under Serampur Sub division within Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001300/2024-2025 | 72/SER | 20/01/2025 | 30/01/2025 | TOTON MONDAL | 4.88 | 0 | 0 | 80
60 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Emargency replacement of valves and allied works at Chanditala Zone -I, II & III Water Supply Scheme under Serampore sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001306/2024-2025 | 78/SER | 20/01/2025 | 30/01/2025 | TOTON MONDAL | 4.28 | 0 | 0 | 90
61 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Switch Room & Boundary Wall at H/W & 2nd TW sites, and Repairing of OHR under CHANDITALA PWSS (Borhal Z-II) under Serampore Sub-Division Of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000900/2023-2024 | 825/HUG | 11/03/2024 | 29/12/2024 | MONDAL ENTERPRISE (PIJUSH MONDAL) | 23.37 | 15.4 | 65.89 | 60
62 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XII & XIII, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002504/2023-2024 | 420/ED | 29/02/2024 | 15/09/2025 | DEY ENTERPRISE | 20.85 | 10.14 | 48.62 | 40
63 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different mouzas of Krishnarampur mouza under Chanditala W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000200/2024-2025 | 545/SER | 19/09/2024 | 25/03/2025 | GOURI ENTERPRISE | 4.84 | 4.81 | 99.28 | 95
64 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different mouzas of Jangalpara mouza under Chanditala W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000199/2024-2025 | 544/SER | 19/09/2024 | 25/03/2025 | GOURI ENTERPRISE | 4.16 | 4.06 | 97.75 | 95
65 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different mouzas (Gutul) of CHANDITALA W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001249/2024-2025 | 49/SER | 20/01/2025 | 27/01/2025 | GHOSH ENTERPRISE | 4.85 | 0 | 0 | 90
66 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different mouzas (Baksha) of BAKSHA under Chanditala W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001251/2024-2025 | 51/SER | 20/01/2025 | 27/01/2025 | JOY GURU ENTERPRISE | 4.8 | 0 | 0 | 90
67 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing & Renovation work of 2 nos Switch Room,Office Cum Godown at Seakhala under Chanditala water supply scheme Under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001293/2024-2025 | 65/SER | 20/01/2025 | 29/04/2025 | M/S RAJKUMAR KHAN | 4.14 | 0 | 0 | 90
68 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Chanditala I & II & Jangipara Block (Phase-II) in the District of Hooghly under Serampore Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000345/2024-2025 | 643/SER | 05/11/2024 | 26/03/2025 | TECHVISION | 4.94 | 4.94 | 100 | 90
69 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different Habitations of Masat Mouzas of Masat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000021/2025-2026 | 292/SER | 17/04/2025 | 01/06/2025 | DILIP KUMAR GHOSH | 4.93 | 0 | 0 | 92
70 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Repairing of Damaged Road due to FHTC Works at different Habitations of Ausbati and Banmalipur Mouzas of Masat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000022/2025-2026 | 293/SER | 17/04/2025 | 01/06/2025 | DILIP KUMAR GHOSH | 4.93 | 0 | 0 | 95
71 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Surging/Development of old tubewell using suitable air compressor to increase the yield at different Water Supply Scheme within Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (1.Chanditala T.W No-3,4,5,6,7, Chickrand Z-I) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000016/2025-2026 | 287/SER | 17/04/2025 | 27/04/2025 | G. T. AGRO CENTRE | 4.27 | 0 | 0 | 90
72 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | MINI PIPED WATER SUPPLY SCHEME FOR BELOW 100 HOUSEHOLD FOR CHANDITALA WATER SUPPLY SCHEME |  |  | BILL/00777/2024-2025 | BP-2024-25-612 | 03/10/2024 | 03/10/2024 | HOOGHLY ZILLA PARISHAD | 33.35 | 0 | 0 | 0
73 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Chanditala I & II & Jangipara Block (Phase-III) in the District of Hooghly under Serampore Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000346/2024-2025 | 644/SER | 05/11/2024 | 27/02/2026 | TECHVISION | 4.94 | 0 | 0 | 55
74 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XIV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002576/2023-2024 | 452/ED | 05/03/2024 | 24/05/2026 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
75 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | SM/10338 | Augmentation | Sinking of 01 nos. (size 100 X 40 mm dia) 154.0 Mtr. Deep, Indian Mark-II Tube well with PVC pipe & Strainer near Chanditala Police Station under Chanditala Water Supply Scheme of Hooghly Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000348/2025-2026 | 539/SER | 29/08/2025 | 08/09/2025 | PANKAJ KUMAR MANNA | 0.99 | 0 | 0 | 95
Total | [13 empty] | 1397.67 | 660.35 | 47.25