## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Preparation of DPR for Augmentation of Jangipara (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000473/2021-2022 | 365/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.91 | 4.93 | 100.4 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Preparation of DPR for Augmentation of Jangipara (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000474/2021-2022 | 366/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 2.06 | 99.06 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT JANGIPARA PWSS Z-II, HOOGHLY DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000223/2022-2023 | 550/CMSD-I | 11/11/2022 | 14/11/2022 | CHANDA ENTERPRISE | 0.43 | 0.43 | 100.79 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-II) W/S SCH, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000281/2022-2023 | 1373/CDD | 24/11/2022 | 24/12/2022 | CHANDA ENTERPRISE | 12.87 | 12.07 | 93.74 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-III), HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000282/2022-2023 | 1560/CDD | 08/12/2022 | 07/01/2023 | C.M. ENTERPRISE | 12.48 | 10.49 | 84.03 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT JANGIPARA PWSS, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000310/2022-2023 | 578/CMSD-I | 30/11/2022 | 07/12/2022 | C.M. ENTERPRISE | 0.98 | 0.95 | 96.49 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement at ProposedT/W Site of JANGIPARA ZONE-III W/S Scheme under SERAMPORE Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000008/2023-2024 | 1021/HUG | 06/04/2023 | 06/05/2023 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 5.56 | 5.36 | 96.39 | 100
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1122/3/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 2210/3/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1291/1/Hug | 24/06/2022 | 24/06/2022 | Resource Division | 9.24 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000305/2023-2024 | 1384/2/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 35.97 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2022-2023 | 79/6/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 8.04 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-III |  |  | BILL/00801/2022-2023 | 164 | 21/02/2023 | 21/02/2023 | WBSEDCL | 7.85 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-IV |  |  | BILL/00802/2022-2023 | 164 | 21/02/2023 | 21/02/2023 | WBSEDCL | 2.77 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  |  | BILL/00274/2023-2024 | BP-2023-24-233 | 31/07/2023 | 31/07/2023 | AATISH KUMAR SHAW | 0.39 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Augmentation of JANGIPARA (ZONE-III) Water Supply Scheme with LDS,FHTC, Rising Main at JANGIPARA Block Under Serampore Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000444/2022-2023 | 2481/HUG | 21/11/2022 | 31/12/2022 | MAA TARA CONSTRUCTION | 118.54 | 113.92 | 96.11 | 60
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangipara water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000217/2022-2023 | 843/ED | 14/02/2023 | 15/05/2023 | R.M.D TRADING. | 21.82 | 21.44 | 98.25 | 30
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002579/2023-2024 | 455/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 60
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000390/2024-2025 | 1474/ED | 25/07/2024 | 23/10/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 11.1 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under JANGIPARA Block of Serampore Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000183/2024-2025 | 519/SER | 11/09/2024 | 16/09/2024 | TOTON MONDAL | 4.77 | 4.72 | 99.03 | 95
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving : ¦data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe : Water Supply Scheme under Chanditala I& Il & Jangipara Block (Part-l) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000178/2024-2025 | 3211/HUG | 12/09/2024 | 27/09/2024 | TECHVISION | 4.2 | 0 | 0 | 80
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | AUGMENTATION of JANGIPARA ZONE-I Piped Water Supply Scheme with LDS, Rising Main, Repairing of Switch Room, Boundary wall of ZONE-I under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000089/2023-2024 | 1353/HUG | 12/05/2023 | 01/01/2026 | ASIA CONSTRUCTION | 350.59 | 155.1 | 44.24 | 60
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Construction of 700 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & FHTC For AUGMENTATION Of JANGIPARA ZONE-I Piped Water Supply Scheme under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000090/2023-2024 | 1354/HUG | 12/05/2023 | 01/10/2025 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 275.31 | 75.34 | 27.37 | 35
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | AUGMENTATION of JANGIPARA ZONE-II Piped Water Supply Scheme with LDS,Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under JANGIPARA BlockWithin Serampore Sub-Division Of Hooghly Division P.H.E Dte., District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000320/2023-2024 | 2410/HUG | 11/08/2023 | 02/04/2025 | BALAJI UDDYOG | 291.59 | 77.8 | 26.68 | 60
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of additional tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution at Anarbati mouza of Jangipara Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000866/2023-2024 | 748/HUG | 05/03/2024 | 04/05/2024 | BANSBERIA CONSTRUCTION CO. | 31.77 | 0 | 0 | 70
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of JANGIPARA Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000756/2023-2024 | 447/HUG | 15/02/2024 | 01/01/2026 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 31.62 | 0 | 0 | 20
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Laying of 225 MM & 250 MM pipeline by HDD process under Jangipara Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000868/2023-2024 | 743/HUG | 05/03/2024 | 15/02/2025 | ASIA CONSTRUCTION | 88.55 | 0 | 0 | 87
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of JANGIPARA ZONE-II W/S Scheme, 4th Tube Well Site of ANTPUR W/S Scheme, & 4th Tube Well Site of JANGALPARA W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000425/2024-2025 | 3522/HUG | 22/10/2024 | 03/09/2025 | WATER TECH | 29.57 | 0 | 0 | 45
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Repairing & Renovation of existing room for Chemical test of drinking water at Headwork site of Jangipara Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Block- Jangipara) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000023/2025-2026 | 266/SER | 03/04/2025 | 13/04/2025 | MAA TARA CONSTRUCTION | 4.99 | 0 | 0 | 99
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of `Two Nos Big Dia Tube Well (250 mm X 150 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at JANGIPARA ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000451/2022-2023 | 2501/HUG | 22/11/2022 | 01/03/2025 | GLOBAL CONSTRUCTION | 20.07 | 0 | 0 | 50
Total | [13 empty] | 1410.13 | 491.54 | 34.86