## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Preparation of DPR for Augmentation of Jangipara (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000473/2021-2022 | 365/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.91 | 4.93 | 100.4 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Preparation of DPR for Augmentation of Jangipara (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000474/2021-2022 | 366/SER | 17/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 2.06 | 99.06 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT JANGIPARA PWSS Z-II, HOOGHLY DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000223/2022-2023 | 550/CMSD-I | 11/11/2022 | 14/11/2022 | CHANDA ENTERPRISE | 0.43 | 0.43 | 100.79 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-II) W/S SCH, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000281/2022-2023 | 1373/CDD | 24/11/2022 | 24/12/2022 | CHANDA ENTERPRISE | 12.87 | 12.07 | 93.74 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-III), HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000282/2022-2023 | 1560/CDD | 08/12/2022 | 07/01/2023 | C.M. ENTERPRISE | 12.48 | 10.49 | 84.03 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-III |  |  | BILL/00801/2022-2023 | 164 | 21/02/2023 |  | WBSEDCL | 7.85 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-IV |  |  | BILL/00802/2022-2023 | 164 | 21/02/2023 |  | WBSEDCL | 2.77 | 0 | 0 | 0
8 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT JANGIPARA PWSS, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000310/2022-2023 | 578/CMSD-I | 30/11/2022 | 07/12/2022 | C.M. ENTERPRISE | 0.98 | 0.95 | 96.49 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000305/2023-2024 | 1384/2/Hug | 15/05/2023 |  | Resource Division | 35.97 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of `Two Nos Big Dia Tube Well (250 mm X 150 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at JANGIPARA ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000451/2022-2023 | 2501/HUG | 22/11/2022 | 06/01/2023 | GLOBAL CONSTRUCTION | 20.07 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  |  | BILL/00274/2023-2024 | BP-2023-24-233 | 31/07/2023 |  | AATISH KUMAR SHAW | 0.39 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement at ProposedT/W Site of JANGIPARA ZONE-III W/S Scheme under SERAMPORE Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000008/2023-2024 | 1021/HUG | 06/04/2023 | 06/05/2023 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 5.56 | 5.36 | 96.39 | 100
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1122/3/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 2210/3/Hug | 30/09/2022 |  | Resource Division | 0.05 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1291/1/Hug | 24/06/2022 |  | Resource Division | 9.24 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | AUGMENTATION of JANGIPARA ZONE-II Piped Water Supply Scheme with LDS,Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under JANGIPARA BlockWithin Serampore Sub-Division Of Hooghly Division P.H.E Dte., District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000320/2023-2024 | 2410/HUG | 11/08/2023 | 09/12/2023 | BALAJI UDDYOG | 291.59 | 24.61 | 8.44 | 20
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Augmentation of JANGIPARA (ZONE-III) Water Supply Scheme with LDS,FHTC, Rising Main at JANGIPARA Block Under Serampore Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000444/2022-2023 | 2481/HUG | 21/11/2022 | 31/12/2022 | MAA TARA CONSTRUCTION | 118.54 | 93.57 | 78.93 | 60
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of JANGIPARA Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000756/2023-2024 | 447/HUG | 15/02/2024 | 15/04/2024 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 31.62 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | AUGMENTATION of JANGIPARA ZONE-I Piped Water Supply Scheme with LDS, Rising Main, Repairing of Switch Room, Boundary wall of ZONE-I under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000089/2023-2024 | 1353/HUG | 12/05/2023 | 30/01/2024 | ASIA CONSTRUCTION | 350.59 | 77.55 | 22.12 | 60
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangipara water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000217/2022-2023 | 843/ED | 14/02/2023 | 15/05/2023 | R.M.D TRADING. | 21.82 | 19.93 | 91.31 | 30
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Laying of water supply pipeline by HDD process under Jangipara Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. |  |  | ORD/000864/2023-2024 | 747/HUG | 05/03/2024 | 19/04/2024 | ASIA CONSTRUCTION | 82.66 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of ANTPUR Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000866/2023-2024 | 748/HUG | 05/03/2024 | 04/05/2024 | BANSBERIA CONSTRUCTION CO. | 31.77 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Laying of 225 MM & 250 MM pipeline by HDD process under Jangipara Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. |  |  | ORD/000868/2023-2024 | 743/HUG | 05/03/2024 | 19/04/2024 | ASIA CONSTRUCTION | 88.55 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Construction of 700 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & FHTC For AUGMENTATION Of JANGIPARA ZONE-I Piped Water Supply Scheme under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000090/2023-2024 | 1354/HUG | 12/05/2023 | 06/02/2024 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 275.31 | 75.34 | 27.37 | 35
26 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002579/2023-2024 | 455/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 3.47 | 35.79 | 60
27 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000390/2024-2025 | 1474/ED | 25/07/2024 | 23/10/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 11.1 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | SM/10339 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving : ¦data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe : Water Supply Scheme under Chanditala I& Il & Jangipara Block (Part-l) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000178/2024-2025 | 3211/HUG | 12/09/2024 | 27/09/2024 | TECHVISION | 4.2 | 0 | 0 | 0
Total | [13 empty] | 1534.79 | 330.74 | 21.55