## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 2 (two) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Kamarpukur Bunglow under Arambag Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer | Junior Engineer (Civill) | ORD/000331/2021-2022 | 2089/Hug | 25/11/2021 | 26/03/2022 | PEACOCK SECURITY SERVICE | 1.69 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SODEPUR Water Supply Scheme under Arambag Sub-Division, under Hooghly Division, PHE Dte.. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer | Junior Engineer (Civill) | ORD/000498/2021-2022 | 626/Hug | 31/03/2022 | 31/07/2022 | PEACOCK SECURITY SERVICE | 4.26 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Power Connection for Saidpur W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000002/2022-2023 | 5003400960/Quot/03 | 11/07/2022 | 11/07/2023 | WBSEDCL | 13.34 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Additional survey work for preparation of DPR for Augmentation of Saidpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Saidpur Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000223/2022-2023 | 408/Arg | 07/06/2022 | 07/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.17 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Preparation of DPR for Augmentation of Saidpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Saidpur Part-A) | Assistant Engineer | Junior Engineer (Civill) | ORD/000222/2022-2023 | 407/Arg | 07/06/2022 | 07/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 6.85 | 146.32 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | SINKING OF TUBE WELL (300MMX200MMX250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR SAIDPUR W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000212/2021-2022 | 1297/CDD | 17/02/2022 | 19/03/2022 | PADMA ENGINEERING & CO. | 14.58 | 11.25 | 77.2 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Construction of approach road at 3rd Tube Well Site of Saidpur Zone-I Piped Water Supply Scheme under Arambagh Sub-Division , P.H.E.Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000368/2022-2023 | 614/Arg | 31/08/2022 | 20/09/2022 | M/S KHAMRUI CONSTRUCTION | 1.42 | 1.37 | 96.25 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Electric Supply |  |  | VCH/001994/2022-2023 | 15 | 15/07/2022 | 15/07/2022 | WBSEDCL | 13.34 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Arambag Sub-Division Office under Arambag Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | Assistant Engineer | Junior Engineer (Civill) | ORD/000330/2021-2022 | 2088/Hug | 25/11/2021 | 26/03/2022 | PEACOCK SECURITY SERVICE | 3.38 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components ofSrirumpore, Shyampur & Saidpur (Zone-I & II) W/S Scheme for the period of 01.12.22 to 31.12.22 under Arambag Sub- Division P.H.E Dte. SL-37 | Assistant Engineer |  | ORD/000521/2022-2023 | 2614/HUG | 30/11/2022 | 31/12/2022 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 0.83 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. including allied works for Saidpur W/S. Sch. Z-I, TW-III. Hooghly | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/001142/2022-2023 | 1038/ED | 28/06/2022 | 26/09/2022 | P.K. ENGINEERING | 10.19 | 9.86 | 96.72 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Repairing of Concrete Road damaged due to Laying Distribution System and Interconnection Pipeline with other allied works of SAIDPUR Zone-II Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000026/2023-2024 | 1126/HUG | 19/04/2023 | 19/05/2023 | MINTU CHAKRABORTY | 35.76 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at SAIDPUR (ZONE-I) PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL - 09 | Assistant Engineer | Junior Engineer (Civill) | ORD/000344/2022-2023 | 1957/HUG | 07/09/2022 | 07/10/2022 | OSMAN SEKH | 11.32 | 10.33 | 91.27 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SAIDPUR ZONE-II PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000454/2022-2023 | 2505/HUG | 22/11/2022 | 22/12/2022 | OSMAN SEKH | 12.72 | 12.45 | 97.84 | 100
15 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000273/2021-2022 | 72/CMSD-I | 30/03/2022 | 14/04/2022 | PADMA ENGINEERING & CO. | 4 | 2.39 | 59.61 | 0
16 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | DEFIXING, DISMOUNTING AND DISMANTLING THE MUD PUMP OIL CHAMBER, FLUID CHAMBER, PTO FOR RIG MACHINE JOHN/DR/1000 (MUD PUMP) UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000272/2021-2022 | 141/CMSD-I | 23/08/2021 | 30/08/2021 | PADMA ENGINEERING & CO. | 0.11 | 0.11 | 100 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 1124/2/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 9.24 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000256/2022-2023 | 127/27/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 39.26 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 1773/41/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 1.38 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 1590/1/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 24.64 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 1385/59/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 39.55 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Quotation Bill for New Service Connection at Aug. of Saidpur W/S. Sch. Z-II, PH-III & II |  |  | BILL/01883/2022-2023 | 218 | 27/03/2023 | 27/03/2023 | WBSEDCL | 15.33 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Augmentation of Saidpur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Pursurah Block in Arambag Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000094/2022-2023 | 1020/Hug | 27/05/2022 | 27/05/2023 | MINTU CHAKRABORTY | 602.3 | 511.77 | 84.97 | 75
24 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Saidpur water supply scheme Zone I TW No I and Zone II TW No I Block Pursurah, District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer1,Junior Engineer3 | ORD/000225/2022-2023 | 856/ED | 14/02/2023 | 15/05/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.48 | 20.91 | 97.34 | 65
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SAIDPUR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000175/2024-2025 | 3185/HUG | 11/09/2024 | 11/10/2024 | B.K ENTERPRISE | 32.31 | 0 | 0 | 0
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SAIDPUR ZONE-II (1No.), SAIDPUR ZONE-I (2Nos.) ARANDI (1 No.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000224/2024-2025 | 3435/HUG | 03/10/2024 | 01/01/2025 | T.K. INTERNATIONAL | 47.2 | 0 | 0 | 0
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 25/10/2024 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Interconnection of T.W. III with LDS for AUGMENTATION of SAIDPUR ZONE-II Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-Arambagh, District:- Hooghly | Assistant Engineer |  | ORD/000167/2024-2025 | 2417/HUG | 26/06/2024 | 26/07/2024 | MINTU CHAKRABORTY | 25.39 | 0 | 0 | 0
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Repairing of existing Switch Rooms and Construction of Boundary Wall with Internal Pathway and Drain at H/W Site for Saidpur Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, PHE Dte. |  |  | ORD/000483/2024-2025 | 4147/HUG | 26/12/2024 | 26/03/2025 | BANSBERIA CONSTRUCTION CO. | 48.83 | 0 | 0 | 0
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Repairing of existing Switch Rooms and Construction of Boundary Wall for HW & 2nd TW Site with Construction of Toilet at 2nd T/W Site for Saidpur Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, PHE Dte. |  |  | ORD/000484/2024-2025 | 4148/HUG | 26/12/2024 | 26/03/2025 | TANISA ENTERPRISE | 49.97 | 0 | 0 | 0
31 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Augmentation of Saidpur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 600 cum capacity OHR with 20 mtr. staging height including soil investigation at Pursurah Block in Arambag Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer (Civill) | ORD/000051/2022-2023 | 1182/Hug | 15/06/2022 | 27/09/2025 | BANSBERIA CONSTRUCTION CO. | 600.84 | 551.71 | 91.82 | 92
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | SM/10340 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SABALSINGHAPUR PWSS-4nos (2) BARADANGAL (Z-II) PWSS-2nos (3) SAIDPUR (Z-I) PWSS-4nos (4) SOALUK PWSS-4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002648/2024-2025 | 814/Arg | 23/08/2024 | 22/09/2024 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 1740.95 | 1138.99 | 65.42