## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Preparation of DPR for Augmentation of MALAYPUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000221/2022-2023 | 363/Arg | 19/05/2022 | 18/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.29 | 4.28 | 99.83 | 0
2 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 180 Mtrs. Depth) by utilising departmental machineries for Malaypur W/S Scheme Arambagh Block under Hooghly District, Central Drilling Division, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000484/2022-2023 | 2002/CDD | 09/02/2023 | 11/03/2023 | M/S SAIKAT ENTERPRISE | 12.54 | 10.63 | 84.78 | 100
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 150Mtrs. Depth) by utilising departmental machineries for Malaypur W/S Scheme (T/W I & II). Arambag Block under Hooghly District, Central Drilling Division, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000034/2023-2024 | 17/CDD | 04/04/2023 | 04/05/2023 | ASHUTOSH DAS & CO | 22.26 | 19.63 | 88.2 | 50
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1124/3/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 9.24 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 1773/1/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1106/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 22.16 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 1385/19/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 17.82 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1234/4/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 58.72 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | PAYMENT TO ELECTRICAL DIVISION, PHE DTE.FOR THE PAYMENT TO WBSEDCL |  |  | BILL/00490/2023-2024 | BP-2023-24-390 | 19/09/2023 | 19/09/2023 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.9 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | PAYMENT TO EXECUTIVE ENGINEER,ELECTRICAL DIVISION, PHE DTE. FOR WBSEDCL AT MALAYPUR WATER SUPPLY SCHEME. |  |  | BILL/00534/2023-2024 | BP-2023-24-438 | 06/10/2023 | 06/10/2023 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 4.78 | 0 | 0 | 0
11 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Continuation for hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of the Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2023-2024 | 120/S&WSD | 31/10/2023 | 31/12/2023 | ASHUTOSH DAS & CO | 0.29 | 0.54 | 186.33 | 15
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Sinking of 3 nos. tube-well (300 X 200 MM) by D.R. Rig method at MAYAPUR, MALAYPUR (2 NOS.) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000931/2023-2024 | 987/HUG | 16/03/2024 | 15/04/2024 | BIBHUTI SHAW | 46.75 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Construction of1 no.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site For AUGMENTATION of MALAYPPURW/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000411/2024-2025 | 3785/HUG | 25/11/2024 | 24/01/2025 | SRI KRISHNA ENTERPRISE | 10.78 | 0 | 0 | 0
14 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Hiring of diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the Calcutta Mechanical Sub Division-I, P.H.Engineering Dte. under CMSD-II(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000048/2023-2024 | 217/CMSD-II(D) | 26/09/2023 | 27/12/2023 | SUJATA BHOWMICK | 0.44 | 1.12 | 256.5 | 33
15 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 150 Mtrs. Depth) by utilising Departmental Machineries for Malaypur W/S Scheme (TW-I), under Hooghly District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000189/2023-2024 | 1434/CDD | 29/09/2023 | 29/10/2023 | ASHUTOSH DAS & CO | 10.74 | 9.06 | 84.32 | 100
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | MALAYPUR Piped Water Supply Scheme with LDS, FHTC, & Construction of 750 cum capacity OHR with 20 m. staging height including Soil Investigation work at ARAMBAG Block under ARAMBAG Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000407/2022-2023 | 2179/HUG | 29/09/2022 | 15/09/2025 | M/S PRADYUT KUMAR HAZRA | 663.67 | 542.86 | 81.8 | 90
17 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000055/2024-2025 | 379/CMSD-I | 24/12/2024 | 26/01/2025 | SIDDHARTHA CHATTERJEE | 0.16 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Malaypur water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer4 | ORD/000288/2022-2023 | 938/ED | 22/02/2023 | 16/07/2025 | MAHADEV ENTERPRISE | 21.42 | 21.12 | 98.6 | 40
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Laying Rising Main & interconnection of T.W. No.-I, II & III for AUGMENTATION of MALAYPUR Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-Arambagh, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000121/2023-2024 | 1455/HUG | 18/05/2023 | 31/05/2025 | M/S PRADYUT KUMAR HAZRA | 7.82 | 0 | 0 | 100
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply & Sanitation arrangement , Boundary Wall in Proposed T.W2 Site, Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of MALAYPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000127/2023-2024 | 1457/HUG | 18/05/2023 | 31/05/2025 | HAZRA CONSTRUCTION | 10.23 | 0 | 0 | 99
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply & Sanitation arrangement, Boundary Wall in Proposed T.W1 Site, Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of MALAYPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000122/2023-2024 | 1456/HUG | 18/05/2023 | 31/05/2025 | HAZRA CONSTRUCTION | 10.24 | 0 | 0 | 99
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Preparation of CAD-GIS Drawing and Pipe Network Design for Augmentation of Chakbense Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001202/2025-2026 | 643/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.84 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Route Survey for Augmentation of Chakbense Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001206/2025-2026 | 645/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.9 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Preparation of DPR for Augmentation of Chakbense Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001203/2025-2026 | 644/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Preparation of DPR for Augmentation of Keshabpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001285/2025-2026 | 673/Arg | 31/07/2025 | 31/08/2025 | APEX TECHNOLOGIES | 0.78 | 0 | 0 | 0
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Route Survey for Augmentation of Keshabpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001286/2025-2026 | 674/Arg | 31/07/2025 | 31/08/2025 | APEX TECHNOLOGIES | 0.9 | 0 | 0 | 0
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | SM/10341 | Augmentation | Preparation of CAD-GIS Drawing and Pipe Network Design for Augmentation of Keshabpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001284/2025-2026 | 672/Arg | 31/07/2025 | 31/08/2025 | APEX TECHNOLOGIES | 0.84 | 0 | 0 | 0
Total | [13 empty] | 943.96 | 609.25 | 64.54