## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - I | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at H/W SITE OF TANTISAL PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL NO - 11 | Assistant Engineer | Junior Engineer (Civill) | ORD/000355/2022-2023 | 2013/HUG | 13/09/2022 | 13/10/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 11.75 | 10.45 | 88.9 | 0
2 | HOOGHLY | Khanakul - I | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Quotation Bill for New Service Connection at Tantisal W/S Sch. TW-I |  |  | BILL/01894/2022-2023 | 226 | 29/03/2023 |  | WBSEDCL | 3.13 | 0 | 0 | 0
3 | HOOGHLY | Khanakul - I | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 1385/25/Hug | 15/05/2023 |  | Resource Division | 17.73 | 0 | 0 | 0
4 | HOOGHLY | Khanakul - I | Central Drilling | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for tantisal W/S Scheme (TW-I), Khanakul-II block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000019/2023-2024 | 11/CDD | 04/04/2023 | 04/05/2023 | SUNRISE ENGINEERING CORPORATION | 11.14 | 10.4 | 93.34 | 100
5 | HOOGHLY | Khanakul - I | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Quotation for New Service Connection for Tantisal water Supply Scheme,TW No-II, Block-Khanakul-I,Dist-Hooghly under ED PHE Dte. |  |  | BILL/03620/2023-2024 | 221 | 25/08/2023 |  | WBSEDCL | 3.77 | 0 | 0 | 0
6 | HOOGHLY | Khanakul - I | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
7 | HOOGHLY | Khanakul - I | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Material Requisition To Resource Division |  |  | RTOR000413/2023-2024 | 3057/44/Hug | 11/10/2023 |  | Resource Division | 17.73 | 0 | 0 | 0
8 | HOOGHLY | Khanakul - I | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Tantisal water supply scheme, T.W. No. I & II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000103/2022-2023 | 3478/ED | 30/12/2022 | 30/03/2023 | GHOSE ENGINEERING SYNDICATE | 22.37 | 21.99 | 98.31 | 60
9 | HOOGHLY | Khanakul - I | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte | SM/10357 | New | Tantisal W/S scheme with LDS Rising mainFHTC workPump House(5.9mx4.1m) with sanitary w/s arrangementsPump house(4.1mx3.5m)450 cum capacityOHR with20 mtr. staging height including soil investigation at Khanakul-IBlockin ArambaghSub-Divn, Dist-Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000003/2022-2023 | 640/Hug | 01/04/2022 | 13/04/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 464.21 | 304.23 | 65.54 | 25
Total | [13 empty] | 646.15 | 347.06 | 53.71