## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Preparation of DPR for Augmentation of Mahespur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000462/2021-2022 | 68/CH | 27/01/2022 | 03/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 4.76 | 99.96 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Additional Survey work for Preparation of Preparation of DPR for Augmentation of Mahespur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000463/2021-2022 | 69/CH | 27/01/2022 | 03/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.38 | 0.37 | 96.83 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MAHESHPUR (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 07 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000354/2022-2023 | 2012/HUG | 13/09/2022 | 13/10/2022 | OSMAN SEKH | 11.32 | 10.59 | 93.56 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1105/2/Hug | 17/04/2023 |  | Resource Division | 47.53 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000257/2023-2024 | 1386/36/Hug | 15/05/2023 |  | Resource Division | 11.14 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT MAHESHPUR (AUG.) W/S SCH., ZONE - II, P.H. NO. - III, dist. - Hooghly |  |  | BILL/00758/2023-2024 | 43 | 19/05/2023 |  | WBSEDCL | 2.71 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of MAHESHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000742/2022-2023 | 649/HUG | 09/03/2023 | 23/04/2023 | M/S PAULAMI ENTERPRISE | 5.77 | 5.77 | 100 | 100
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, HEAD QUARTER, HOOGHLY DIVISION, PHE DTE. |  |  | BILL/00275/2023-2024 | BP-2023-24-232 | 31/07/2023 |  | PRADIP KUMAR ADHYA | 3.52 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | 1st Continuation of Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising main & Other essential components of Mahespur Z-I & II W/S Scheme for the Period of 01.06.2023 to 30.06.2023 under Chinsurah Sub-Division. | Assistant Engineer (Civil) |  | ORD/000297/2023-2024 | 466/CH | 30/05/2023 | 29/06/2023 | SUDIPTA SINHA | 0.61 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. |  |  | ORD/002330/2022-2023 | 2385//HMSD | 27/12/2022 | 26/01/2023 | DEBASHISH GHOSH | 0.29 | 0.29 | 100 | 30
11 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 1123/6/HUG | 06/06/2022 |  | Resource Division | 5.5 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 1991/HUG | 12/09/2022 |  | Resource Division | 42.71 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of MAHESHPUR ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000368/2023-2024 | 2458/HUG | 12/08/2023 | 26/09/2023 | M/S BIMAL DAS AND CO. | 5.31 | 5.28 | 99.44 | 95
15 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Quotation for new service connection charge at Maheshpur PWSS, Zone-I, TW - III |  |  | BILL/04369/2023-2024 | 456 | 01/12/2023 |  | WBSEDCL | 3.32 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of MAHESHPUR ZONE-II W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000347/2023-2024 | 2440/HUG | 12/08/2023 | 26/09/2023 | BASU & SONS | 5.31 | 5.28 | 99.44 | 95
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of MAHESHPUR Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000365/2023-2024 | 2456/HUG | 12/08/2023 | 11/10/2023 | M/S S & P CONSTRUCTION | 9.75 | 4.62 | 47.34 | 80
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Baichi PWSS 2. Mahespur PWSS 3. Uttar Chandannagar PWSS 4. Bahadurpur PWSS 5. Patna BhairavpurPWSS 6. Mandra PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000834/2023-2024 | 212/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.48 | 50 | 45
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Laying Balance portion of Pipeline including other allied works at various Mouzas MAHESHPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000891/2023-2024 | 815/HUG | 11/03/2024 | 25/04/2024 | MALLIKA ENTERPRISE | 35.45 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MAHESHPUR (Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 06 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000353/2022-2023 | 2011/HUG | 13/09/2022 | 13/10/2022 | OSMAN SEKH | 11.32 | 5.61 | 49.6 | 25
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipeline for inter connection between T.W & Distribution for Augmentation of MAHESPUR ZONE-II Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within POLBA-DADPUR Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000136/2023-2024 | 1478/HUG | 19/05/2023 | 03/07/2023 | SHREEOM ENTERPRISE | 12.11 | 4.81 | 39.68 | 50
22 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Quotation for new service connection at Maheshpur (Zone - I) W/S Sch., [SM/10451] T/W No. - IV, Nr. Sugandhya Panchyate, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594865, Dt. - 02-04-2024, Application No. - 5004069700 |  |  | BILL/00075/2024-2025 | 41 | 09/04/2024 |  | WBSEDCL | 4.4 | 0 | 0 | null
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Providing FHTC in rest out portion At Sugandha of Mahespur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000840/2023-2024 | 218/CH | 29/02/2024 | 07/03/2024 | M/S BIMAL DAS AND CO. | 0.85 | 0.85 | 100 | 25
24 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Maheshpur water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000220/2022-2023 | 851/ED | 14/02/2023 | 15/05/2023 | P.K. ENGINEERING | 21.49 | 15.78 | 73.43 | 95
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | REGARDING DAMAGE OF PMGSY ROAD MAHESHPUR MORE TO BHAUSANARA PART OF ANANTPUR CMDA MAHESHPUR MORE IN POLBA DADPUR BLOCK HOOGHLY DISTRICT. |  |  | BILL/01097/2023-2024 | BP-2023-24-788 | 29/01/2024 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 17.94 | 0 | 0 | 0
26 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | REGARDING DAMAGE OF PMGSY ROAD MAHESHPUR MORE TO BHAUSANARA PART OF ANANTPUR CMDA MAHESHPUR MORE IN POLBA DADPUR BLOCK HOOGHLY DISTRICT. |  |  | BILL/01097/2023-2024 | BP-2023-24-788 | 29/01/2024 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 17.94 | 0 | 0 | 0
27 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Providing FHTC in rest out portion At Amarpur Paschim Para of Mahespur Z-I PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001030/2023-2024 | 273/CH | 14/03/2024 | 21/03/2024 | M/S BIMAL DAS AND CO. | 0.98 | 0.98 | 100 | 80
28 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Providing FHTC in rest out portion At Choto Pachrakhi of Mahespur Z-I PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001031/2023-2024 | 274/CH | 14/03/2024 | 21/03/2024 | M/S BIMAL DAS AND CO. | 0.66 | 0 | 0 | 80
29 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas MAHESHPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000888/2023-2024 | 812/HUG | 11/03/2024 | 10/04/2024 | SWARNA ENTERPRISE | 27.22 | 20.29 | 74.52 | 65
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of MAHESHPUR Zone-II PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000367/2023-2024 | 2457/HUG | 12/08/2023 | 11/10/2023 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 9 | 4.4 | 48.86 | 75
31 | HOOGHLY |  | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAHESHPUR PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000377/2024-2025 | 1464/ED | 25/07/2024 | 23/10/2024 | MAA TARA ENTERPRISE. | 11.1 | 0 | 0 | 0
32 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Construction of Protection Work at Maheshpur Zone - I under Chinsurah Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000851/2023-2024 | 735/HUG | 05/03/2024 | 04/04/2024 | SHREEOM ENTERPRISE | 7.63 | 6.47 | 84.89 | 70
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room ,boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at different TW sites for Augmentation of DHARAMPUR (Maheshpur) Piped Water Supply Scheme, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001027/2023-2024 | 3594/HUG | 05/12/2023 | 03/02/2024 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 27.85 | 21.94 | 78.79 | 40
34 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Augmentation of MAHESHPUR (ZONE-II) Water Supply Scheme with LDS, FHTC, Rising Main at POLBA-DADPUR Block under Chinsurah Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000212/2022-2023 | 1717/Hug | 24/08/2022 | 23/10/2022 | M/S S.G. CONSTRUCTION | 207.78 | 173.54 | 83.52 | 75
35 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | ROAD RESTORATION CHARGES |  |  | BILL/00423/2024-2025 | BP-2024-25-343 | 02/08/2024 |  | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 3.89 | 0 | 0 | 0
36 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | SM/10451 | Augmentation | Augmentation of MAHESHPUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main at POLBA-DADPUR Block Under Chinsurah Sub-Division of Hooghly Division, PHE Dte. [2nd call of NIeT No. WBPHE/EE/10/HUG/2022-23 Sl No. 02] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000803/2022-2023 | 961/Hug | 31/03/2023 | 29/06/2023 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 266.8 | 42.01 | 15.75 | 100
Total | [13 empty] | 934.65 | 334.11 | 35.75