## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Preparation of DPR for Augmentation of Chanparai Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000464/2021-2022 | 128/CH | 17/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.38 | 3.38 | 99.9 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at CHANPARAI PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 03 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000351/2022-2023 | 2009/HUG | 13/09/2022 | 28/10/2022 | OSMAN SEKH | 22.63 | 11.03 | 48.73 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe line for inter connection between T.W & Distribution System for Augmentation of CHANPARAI Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within CHINSURAH-MOGRA Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000135/2023-2024 | 1477/HUG | 19/05/2023 | 03/07/2023 | SRI KRISHNA ENTERPRISE | 11.81 | 11.25 | 95.28 | 100
4 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 1123/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 5.5 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 1991/1/HUG | 12/09/2022 | 12/09/2022 | Resource Division | 7.86 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1105/Hug | 17/04/2023 | 17/04/2023 | Resource Division | 7.86 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHANPARAI W/S SCH., P.H. NO. - III |  |  | BILL/00782/2023-2024 | 53 | 31/05/2023 | 31/05/2023 | WBSEDCL | 3.17 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Augmentation of CHANPARAI Water Supply Scheme with LDS, FHTC, Rising Main at CHINSURAH MOGRA Block of Chinsurah Sub-Division under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000405/2022-2023 | 2178/HUG | 29/09/2022 | 13/12/2022 | RAJ CONSTRUCTION | 251.9 | 230.86 | 91.65 | 10
9 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at PH-2 of Chanparai Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000008/2025-2026 | 490/CH | 04/04/2025 | 14/04/2025 | RAJ CONSTRUCTION | 1.97 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Chanparui Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000006/2025-2026 | 488/CH | 04/04/2025 | 14/04/2025 | RAJ CONSTRUCTION | 4.79 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | Augmentation of Chanparai Water Supply Scheme | SM/10467 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanparai water supply scheme, T.W. No.- I, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000203/2022-2023 | 830/ED | 14/02/2023 | 31/10/2023 | NITESH MANAGEMENT | 10.73 | 10.4 | 96.84 | 97
Total | [13 empty] | 331.61 | 266.91 | 80.49