## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000543/2021-2022 | 143/CH | 21/02/2022 | 28/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.76 | 99.99 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Additional Survey Work for Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000544/2021-2022 | 144/CH | 21/02/2022 | 28/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0.4 | 98.08 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at POLBA (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 04 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000352/2022-2023 | 2010/HUG | 13/09/2022 | 28/10/2022 | OSMAN SEKH | 22.63 | 21.12 | 93.33 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Augmentation of POLBA (ZONE-I) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. SL NO - 04 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000250/2022-2023 | 1885/HUG | 01/09/2022 | 30/11/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 411.46 | 386.09 | 93.83 | 65
5 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Augmentation of POLBA (ZONE-II) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2022-2023 | 1718/Hug | 24/08/2022 | 03/10/2022 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 110.96 | 102.3 | 92.19 | 85
6 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of 450 cum capacity of POLBA Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 02 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000284/2022-2023 | 1905/HUG | 05/09/2022 | 05/10/2022 | M/S T.K.B. CONSTRUCTION | 9.49 | 9.49 | 99.99 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 1991/3/HUG | 12/09/2022 | 12/09/2022 | Resource Division | 20.25 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site Of POLBA ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000706/2022-2023 | 443/HUG | 16/02/2023 | 17/04/2023 | MAA JAGADHATRI CONSTRUCTION | 12.24 | 12.24 | 100 | 55
9 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Polba water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000221/2022-2023 | 852/ED | 14/02/2023 | 09/02/2024 | S.P. CONSTRUCTION | 21.49 | 20.78 | 96.67 | 98
10 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of POLBA ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000364/2023-2024 | 2455/HUG | 12/08/2023 | 26/09/2023 | SUDIPTA DAS | 9.47 | 9.44 | 99.6 | 100
11 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 5.4 m X 3.6 m Switch Roomwith Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of POLBA Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000660/2023-2024 | 3525/HUG | 30/11/2023 | 21/02/2025 | WATER TECH | 32.11 | 0 | 0 | 50
12 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000259/2023-2024 | 1386/38/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.98 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000539/2023-2024 | 3059/30/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 24.79 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1105/4/Hug | 17/04/2023 | 17/04/2023 | Resource Division | 14.69 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Quotation bill for security money of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-II |  |  | BILL/00799/2022-2023 | 163 | 20/02/2023 | 20/02/2023 | WBSEDCL | 2.81 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Road Restoration |  |  | BILL/00683/2023-2024 | BP-2023-24-591 | 16/11/2023 | 16/11/2023 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 93 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Pandua Polba Road Restoration |  |  | BILL/00496/2023-2024 | BP-2023-24-397 | 26/09/2023 | 26/09/2023 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 33.08 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Quotation bill for new service connection charges of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-I |  |  | BILL/00800/2022-2023 | 163 | 20/02/2023 | 20/02/2023 | WBSEDCL | 12.44 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Pawan Ochai Road Restoration |  |  | BILL/00495/2023-2024 | BP-2023-24-396 | 26/09/2023 | 26/09/2023 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 6.79 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Sinking of 1 No. tube-well, Rising Main for inter connection between T.W & Distribution, construction of boundary wall at PUINAN mouza of POLBA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/002927/2024-2025 | 4144/HUG | 24/12/2024 | 23/01/2025 | BANSBERIA CONSTRUCTION CO. | 20.34 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall at GOSWAMIMALIPARA mouza of POLBA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/002928/2024-2025 | 4145/HUG | 24/12/2024 | 07/02/2025 | BANSBERIA CONSTRUCTION CO. | 26.48 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Construction of Guard Room at Polba (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000772/2023-2024 | 128/CH | 16/02/2024 | 02/03/2024 | MAA BUNAMATA ENTERPRISE | 3.76 | 3.75 | 99.83 | 15
23 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Dubir Bheri village under Polba Dadpur Block, Dakshin Babnan village of Polba Dadpur Block and Chanda village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000994/2023-2024 | 268/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
24 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in POLBA GP of POLBA-DADPUR Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000925/2023-2024 | 245/CH | 12/03/2024 | 11/04/2024 | R.K. TRADERS | 4.98 | 4.96 | 99.59 | 75
25 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Birpala village under Polba Dadpur Block, Gopalnagar village of Polba Dadpur Block and Kasemaligar village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000990/2023-2024 | 264/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
26 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sonatikri village under Polba Dadpur Block, Banshdarun village of Polba Dadpur Block and Arzi Jatchandi village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000992/2023-2024 | 266/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
27 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Meghsar village under Polba Dadpur Block, Baral Malimpur village of Polba Dadpur Block and Sangrampur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000996/2023-2024 | 270/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
28 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Meghsar PWSS 2. Polba PWSS 3. Sudarshan PWSS 4. Paunan PWSS 5. Ektarpur PWSS 6. Puinan PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000824/2023-2024 | 202/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 50
29 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Banseya village under Polba Dadpur Block, Barunanpara village of Polba Dadpur Block and Ramnagar Bheri village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000993/2023-2024 | 267/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
30 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DADPUR GP of POLBA-DADPUR Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000923/2023-2024 | 243/CH | 12/03/2024 | 11/04/2024 | SHREEOM ENTERPRISE | 4.98 | 1.31 | 26.37 | 70
31 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Laying C.I/D.I pipes & specials for interconnection between T.W No. -I & II with distribution pipe line at Polba (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000041/2024-2025 | 543/CH | 18/06/2024 | 25/06/2024 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.66 | 2.59 | 97.51 | 50
32 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Khurigachi village under Polba Dadpur Block, Musar village of Polba Dadpur Block and Nonadanga village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000995/2023-2024 | 269/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
33 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for POLBA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/000379/2024-2025 | 1465/ED | 25/07/2024 | 23/10/2024 | COOLING CARE CENTER | 11.1 | 10.81 | 97.38 | 95
34 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Resifting of Departmental pipes from Different H/W sites to Polba Store under Chinsurah sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000462/2024-2025 | 1734/CH | 23/12/2024 | 10/02/2025 | M/S BIMAL DAS AND CO. | 4.73 | 0 | 0 | 50
35 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under POLBA Block (Existing scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000271/2024-2025 | 930/CH | 05/11/2024 | 10/11/2024 | R.K. TRADERS | 4.85 | 4.68 | 96.44 | 90
36 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under POLBA Block (New scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000272/2024-2025 | 934/CH | 11/11/2024 | 16/11/2024 | TAPAS ADHYA | 2.12 | 2.12 | 99.99 | 90
37 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of 6 Nos. Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites / HGJ villages for awareness generation among the people in Barunnapara, Ramnagar, Amnan, Araji Jotchandi, Dubuirbheri & Maheswarbati villages under Polba Dadpur Block of Hooghly District under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001577/2023-2024 | 353/CH | 27/03/2024 | 03/04/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 100
38 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of 6 Nos. Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites / HGJ villages for awareness generation among the people in Goaljor, Khatni, Paunan, Birpala, Gopalnagar and Malipara villages under Polba Dadpur Block of Hooghly District under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001579/2023-2024 | 347/CH | 22/03/2024 | 29/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 100
39 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of 6 Nos. Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites / HGJ villages for awareness generation among the people in Manipur, Prasadpur, Sonatikri, Khurigachi, Saranpur and Baral Malimpur villages under Polba Dadpur Block of Hooghly District under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001580/2023-2024 | 344/CH | 22/03/2024 | 29/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 100
40 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of 6 Nos. Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites / HGJ villages for awareness generation among the people in Pandua Block of Hooghly District under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001581/2023-2024 | 345/CH | 22/03/2024 | 29/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 100
41 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Quotation for new service connection at Polba[SM/10468] W/S Sch. , Zone - I, T/W No. - IV, (Nr. Kasundipara primary school), Block - Polba-Dadpur, under Polba CCC, WBSEDCL, Ref. Id. - 503595736, Dt. - 05/04/2024, Application No. - 5004071216, |  |  | BILL/00121/2024-2025 | 35 | 09/04/2024 | 09/04/2024 | WBSEDCL | 7.13 | 0 | 0 | 0
42 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Providing Functional House hold tap connection (FHTC) under JJM within left out mouzas/habitations of differet PWSS under Polba Dadpur Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | Assistant Engineer (Civil) |  | ORD/001852/2024-2025 | 231/CH | 19/02/2025 | 01/03/2025 | M/S BIMAL DAS AND CO. | 2.86 | 0 | 0 | 0
43 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Carriage for Chlorine From Polba Store to different Pump Houses at Polba Dadpur Block under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000708/2024-2025 | 59/CH | 10/01/2025 | 15/01/2025 | M/S BIMAL DAS AND CO. | 0.3 | 0 | 0 | 50
44 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Carriage for Chlorine From Polba Store to different Pump Houses at Dhanniakhali Block under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000710/2024-2025 | 60/CH | 10/01/2025 | 15/01/2025 | MAA BUNAMATA ENTERPRISE | 0.3 | 0.3 | 100 | 50
Total | [13 empty] | 950.97 | 602.87 | 63.39