## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000543/2021-2022 | 143/CH | 21/02/2022 | 28/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.76 | 99.99 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Additional Survey Work for Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000544/2021-2022 | 144/CH | 21/02/2022 | 28/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0.4 | 98.08 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of 450 cum capacity of POLBA Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 02 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000284/2022-2023 | 1905/HUG | 05/09/2022 | 05/10/2022 | M/S T.K.B. CONSTRUCTION | 9.49 | 9.49 | 99.99 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Quotation bill for new service connection charges of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-I |  |  | BILL/00800/2022-2023 | 163 | 20/02/2023 |  | WBSEDCL | 12.44 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Quotation bill for security money of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-II |  |  | BILL/00799/2022-2023 | 163 | 20/02/2023 |  | WBSEDCL | 2.81 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at POLBA (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 04 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000352/2022-2023 | 2010/HUG | 13/09/2022 | 28/10/2022 | OSMAN SEKH | 22.63 | 21.12 | 93.33 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000259/2023-2024 | 1386/38/Hug | 15/05/2023 |  | Resource Division | 0.98 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Pawan Ochai Road Restoration |  |  | BILL/00495/2023-2024 | BP-2023-24-396 | 26/09/2023 |  | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 6.79 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Pandua Polba Road Restoration |  |  | BILL/00496/2023-2024 | BP-2023-24-397 | 26/09/2023 |  | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 33.08 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site Of POLBA ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000706/2022-2023 | 443/HUG | 16/02/2023 | 17/04/2023 | MAA JAGADHATRI CONSTRUCTION | 12.24 | 12.24 | 100 | 55
11 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000539/2023-2024 | 3059/30/Hug | 11/10/2023 |  | Resource Division | 24.79 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of POLBA ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000364/2023-2024 | 2455/HUG | 12/08/2023 | 26/09/2023 | SUDIPTA DAS | 9.47 | 9.44 | 99.6 | 100
13 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Augmentation of POLBA (ZONE-I) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. SL NO - 04 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000250/2022-2023 | 1885/HUG | 01/09/2022 | 30/11/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 411.46 | 386.09 | 93.83 | 65
14 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 1991/3/HUG | 12/09/2022 |  | Resource Division | 20.25 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Polba water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000221/2022-2023 | 852/ED | 14/02/2023 | 15/05/2023 | S.P. CONSTRUCTION | 21.49 | 10.39 | 48.33 | 98
16 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 8TH Continuation of Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.01.2024 to 31.01.2024 | Assistant Engineer (Civil) |  | ORD/000816/2023-2024 | 1143/CH | 27/12/2023 | 27/01/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Augmentation of POLBA (ZONE-II) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2022-2023 | 1718/Hug | 24/08/2022 | 03/10/2022 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 110.96 | 92.59 | 83.44 | 85
18 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DADPUR GP of POLBA-DADPUR Block | Assistant Engineer (Civil) |  | ORD/000923/2023-2024 | 243/CH | 12/03/2024 | 11/04/2024 | SHREEOM ENTERPRISE | 4.98 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Birpala village under Polba Dadpur Block, Gopalnagar village of Polba Dadpur Block and Kasemaligar village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000990/2023-2024 | 264/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
20 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sonatikri village under Polba Dadpur Block, Banshdarun village of Polba Dadpur Block and Arzi Jatchandi village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000992/2023-2024 | 266/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
21 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Banseya village under Polba Dadpur Block, Barunanpara village of Polba Dadpur Block and Ramnagar Bheri village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000993/2023-2024 | 267/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
22 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Dubir Bheri village under Polba Dadpur Block, Dakshin Babnan village of Polba Dadpur Block and Chanda village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000994/2023-2024 | 268/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
23 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Khurigachi village under Polba Dadpur Block, Musar village of Polba Dadpur Block and Nonadanga village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000995/2023-2024 | 269/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
24 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Meghsar village under Polba Dadpur Block, Baral Malimpur village of Polba Dadpur Block and Sangrampur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000996/2023-2024 | 270/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
25 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Quotation for new service connection at Polba[SM/10468] W/S Sch. , Zone - I, T/W No. - IV, (Nr. Kasundipara primary school), Block - Polba-Dadpur, under Polba CCC, WBSEDCL, Ref. Id. - 503595736, Dt. - 05/04/2024, Application No. - 5004071216, |  |  | BILL/00121/2024-2025 | 35 | 09/04/2024 |  | WBSEDCL | 7.13 | 0 | 0 | null
26 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 9TH Continuation of Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.02.2024 to 29.02.2024 | Assistant Engineer (Civil) |  | ORD/001024/2023-2024 | 80/CH | 29/01/2024 | 27/02/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.81 | 0 | 0 | 0
27 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Road Restoration |  |  | BILL/00683/2023-2024 | BP-2023-24-591 | 16/11/2023 |  | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 93 | 0 | 0 | 0
28 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Road Restoration |  |  | BILL/00683/2023-2024 | BP-2023-24-591 | 16/11/2023 |  | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 93 | 0 | 0 | 0
29 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 10th Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.03.2024 to 31.03.2024 | Assistant Engineer (Civil) |  | ORD/001431/2023-2024 | 186/CH | 29/02/2024 | 31/03/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
30 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 11TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.04.2024 to 30.04.2024. | Assistant Engineer (Civil) |  | ORD/001433/2023-2024 | 368/CH | 28/03/2024 | 27/04/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.84 | 0 | 0 | 0
31 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Laying C.I/D.I pipes & specials for interconnection between T.W No. -I & II with distribution pipe line at Polba (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000041/2024-2025 | 543/CH | 18/06/2024 | 25/06/2024 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.66 | 0 | 0 | 0
32 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Construction of Guard Room at Polba (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000772/2023-2024 | 128/CH | 16/02/2024 | 02/03/2024 | MAA BUNAMATA ENTERPRISE | 3.76 | 3.75 | 99.83 | 15
33 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 12TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.05.2024 to 31.05.2024. | Assistant Engineer (Civil) |  | ORD/000066/2024-2025 | 416/CH | 29/04/2024 | 30/05/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
34 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 13TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.06.2024 to 30.06.2024. | Assistant Engineer (Civil) |  | ORD/000068/2024-2025 | 486/CH | 30/05/2024 | 29/06/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.84 | 0 | 0 | 0
35 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in POLBA GP of POLBA-DADPUR Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000925/2023-2024 | 245/CH | 12/03/2024 | 11/04/2024 | R.K. TRADERS | 4.98 | 4.96 | 99.59 | 75
36 | HOOGHLY |  | Electrical | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for POLBA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/000379/2024-2025 | 1465/ED | 25/07/2024 | 23/10/2024 | COOLING CARE CENTER | 11.1 | 5.41 | 48.69 | 95
37 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 14TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.07.2024 to 31.07.2024 | Assistant Engineer (Civil) |  | ORD/000084/2024-2025 | 572/CH | 27/06/2024 | 28/07/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
38 | HOOGHLY |  | Hooghly Division | Augmentation of Polba Water Supply Scheme | SM/10468 | Augmentation | 15TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at POLBA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.08.2024 to 31.08.2024 | Assistant Engineer (Civil) |  | ORD/000176/2024-2025 | 668/CH | 29/07/2024 | 29/08/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
Total | [13 empty] | 937.23 | 566.36 | 60.43