## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Bainchi Mouza of Bainchi Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) |  | ORD/000021/2022-2023 | 722/Hug | 07/04/2022 | 17/05/2022 | TOTON MONDAL | 50.96 | 50.95 | 99.98 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BAINCHI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000415/2022-2023 | 2275/HUG | 19/10/2022 | 28/11/2022 | M/S T.K.B. CONSTRUCTION | 45.7 | 45.54 | 99.64 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | Retrofitting | BAINCHIPOTA (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) |  | ORD/000740/2022-2023 | 613/HUG | 02/03/2023 | 27/11/2023 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 491.76 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Batika & Chau Bera Mouza of Bainchi Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) |  | ORD/000022/2022-2023 | 723/Hug | 07/04/2022 | 17/05/2022 | M/S ASHA CONSTRUCTION. | 48.21 | 43.01 | 89.21 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 1123/5/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 5.5 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | SM/11002 | Retrofitting | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB DIVISION, PHE DTE. |  |  | BILL/00367/2022-2023 | BP-2022-23-630 | 22/03/2023 | 22/03/2023 | AATISH KUMAR SHAW | 0.4 | 0 | 0 | 0
Total | [13 empty] | 642.53 | 139.49 | 21.71