## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11003 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within Kanaipur, Gohalisanra & Bali Village of Bali Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000247/2022-2023 | 711/HUG | 07/04/2022 | 27/05/2022 | S.D ENTERPRISE (SAMIR KR. DAS) | 2.37 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11003 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1124/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11003 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BALI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000486/2024-2025 | 4150/HUG | 26/12/2024 | 26/03/2025 | M/S T.K.B. CONSTRUCTION | 17.12 | 0 | 0 | 0
Total | [13 empty] | 31.81 | 0 | 0