## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of DUMURDAHA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000416/2022-2023 | 2276/HUG | 19/10/2022 | 03/11/2022 | TAPAS ADHYA | 10.76 | 0 | 0 | 0
2 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Hiring of diesel drive motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000502/2022-2023 | 45/CMSD-II(D) | 27/02/2023 | 27/08/2023 | SIDDHARTHA CHATTERJEE | 0.9 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dadpur, Kamalpur, Sija & Ramnagar Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) |  | ORD/000024/2022-2023 | 725/Hug | 07/04/2022 | 17/05/2022 | DAS ENTERPRISE (SAMIR DAS) | 51.08 | 0 | 0 | 0
4 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing drilling crew and other allied works for construction of Tube Well (300mmx200mmx150Mtrs) by utilisiling departmental rig machineries for Durmurdaha W/S Scheme, balagarh Block under Hooghly Division, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000027/2023-2024 | 62/CDD | 06/04/2023 | 06/05/2023 | UNIVERSAL ENTERPRISES | 11.38 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dumurdaha dham & Aschitpur Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) |  | ORD/000023/2022-2023 | 724/Hug | 07/04/2022 | 17/05/2022 | MS PRADIP KUMAR PAL | 51.01 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1123/3/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 11 | 0 | 0 | 0
7 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000098/2023-2024 | 209/CMSD-II(D) | 25/08/2023 | 25/12/2023 | SIDDHARTHA CHATTERJEE | 0.94 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | SM/11165 | Retrofitting | Repairing of Existing O.H.R at H/W site of Dumurdaha Zone- II Water supply scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Balagarh, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000796/2023-2024 | 536/HUG | 20/02/2024 | 05/04/2024 | DAS ENTERPRISE (SAMIR DAS) | 8.36 | 0 | 0 | 100
Total | [13 empty] | 145.44 | 0 | 0