## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SOMRA Water Supply Scheme under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000490/2021-2022 | 616/Hug | 31/03/2022 | 31/07/2022 | S.K. GHOSH | 3.41 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at POLBA Water Supply Scheme under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000491/2021-2022 | 619/Hug | 31/03/2022 | 31/07/2022 | S.K. GHOSH | 3.41 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Preparation of DPR for Augmentation of Dhaniakhali Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000541/2021-2022 | 131/CH | 17/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.82 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | PAYMENT TO WBSEDCL |  |  | VCH/001350/2022-2023 |  | 11/11/2022 | 11/11/2022 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.2 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at DHANIAKHALI (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL - 05 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000341/2022-2023 | 1955/HUG | 07/09/2022 | 22/10/2022 | OSMAN SEKH | 22.63 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of 182 cum capacity of Dhaniakhali Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 01 | Assistant Engineer (Civil) |  | ORD/000283/2022-2023 | 1904/HUG | 05/09/2022 | 05/10/2022 | ROY ENTERPRISE | 7.45 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Augmentation of DHANIAKHALI (ZONE-I) Water Supply Scheme with LDS & FHTC At Dhaniakhali Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2022-2023 | 1657 | 16/08/2022 | 05/10/2022 | SUJATA CONSTRUCTION | 177.27 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1123/2/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 11 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 2211/1/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 1386/53/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 15.68 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1105/1/Hug | 17/04/2023 | 17/04/2023 | Resource Division | 60.84 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Quotation Bill for New Service Connection at DhaniakhaliZ-II, PH-II |  |  | BILL/00805/2023-2024 | 57 | 02/06/2023 | 02/06/2023 | WBSEDCL | 5.86 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Quotation Bill for New Service Connection at Dhaniakhali W/S. Sch. W/S. Sch. Z-I |  |  | BILL/02592/2023-2024 | 155 | 03/08/2023 | 03/08/2023 | WBSEDCL | 4.72 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | HIRE CHARGES BILL EXECUTIVE ENGINEER, HOOGHLY DIVISION, PHE DTE. |  |  | BILL/00041/2022-2023 | BP-2022-23-405 | 15/12/2022 | 15/12/2022 | PRADIP KUMAR ADHYA | 2.07 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000206/2022-2023 | 833/ED | 14/02/2023 | 15/05/2023 | A.G. ENTERPRISE | 21.49 | 0 | 0 | 59
16 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of DHANIAKHALI ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000749/2022-2023 | 650/Hug | 10/03/2023 | 09/05/2023 | SOME ENTERPRISE | 6.08 | 0 | 0 | 95
17 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Construction of 1 No. switch-room at Proposed TW site of DHANIAKHALI ZONE-II Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000088/2023-2024 | 1342/HUG | 11/05/2023 | 10/06/2023 | SOMNATH ADHYA | 6.15 | 0 | 0 | 100
18 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Replacing of Sluice Valve and allied works at Head Work Site of Dhaniakhali Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000692/2023-2024 | 1114/CH | 15/12/2023 | 22/12/2023 | M/S BIMAL DAS AND CO. | 0.95 | 0 | 0 | 100
19 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme underDhaniakhali Block (Part-II) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000082/2024-2025 | 696/CH | 09/08/2024 | 24/08/2024 | TECHVISION | 4.2 | 0 | 0 | 100
20 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under DHANIAKHALI Block (New scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000270/2024-2025 | 929/CH | 05/11/2024 | 10/11/2024 | M/S BIMAL DAS AND CO. | 2.82 | 0 | 0 | 90
21 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under DHANIAKHALI Block (Existing scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000269/2024-2025 | 928/CH | 05/11/2024 | 10/11/2024 | TOTON MONDAL | 4.85 | 0 | 0 | 90
22 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-I) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000081/2024-2025 | 695/CH | 09/08/2024 | 24/08/2024 | TECHVISION | 4.2 | 0 | 0 | 90
23 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | SM/11166 | Augmentation | AUGMENTATION of DHANIAKHALI ZONE-II Piped Water Supply Scheme with LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000261/2023-2024 | 2225/HUG | 31/07/2023 | 18/10/2025 | PRADIP KUMAR ADHYA | 409.01 | 0 | 0 | 30
Total | [13 empty] | 812.93 | 0 | 0