## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Preparation of DPR for Augmentation of Madhusudanpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000542/2021-2022 | 133/CH | 17/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.01 | 2.96 | 98.55 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MADHUSUDANPUR PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 08 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000342/2022-2023 | 1956/HUG | 07/09/2022 | 07/10/2022 | OSMAN SEKH | 11.32 | 11.23 | 99.27 | 25
3 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1123/4/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 11 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 2211/2/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 1991/2/HUG | 12/09/2022 | 12/09/2022 | Resource Division | 21.16 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, Rising Main, FHTC For AUGMENTATION of MADHUSUDANPUR Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block CHINSURAH MOGRA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000103/2023-2024 | 1421/Hug | 17/05/2023 | 01/04/2025 | SUBHANKAR GUHA | 166.98 | 51.52 | 30.85 | 30
7 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Madhusudanpur water supply scheme TW No I Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000218/2022-2023 | 850/ED | 14/02/2023 | 03/09/2024 | AMIT DAS | 10.75 | 10.45 | 97.29 | 90
8 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | AUGMENTATION of MADHUSUDANPUR Piped Water Supply Scheme with Repairing of Switch Room & Boundary wall, Construction Of Switch Room, Boundary Wall & LDS, under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block-CHINSURAH MOGRA, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000006/2023-2024 | 1016/HUG | 06/04/2023 | 05/07/2023 | M/S T.K.B. CONSTRUCTION | 128.94 | 105.86 | 82.1 | 100
9 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2023-2024 | 1386/14/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.35 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Quotation for new service connection at Madhusudanpur(S.Aug.) W/S Sch. , T/W No. -III (Nr. Tissu Bus stand) [SM/11167] under Mogra CCC, WBSEDCL, Ref Id. - 503586680, Dt. - 16/04/2024, Application No. - 5004053256, |  |  | BILL/00192/2024-2025 | 80 | 19/04/2024 | 19/04/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Providing Functional House hold tap connection (FHTC) under JJM within Digirpara & Naapara of Madhusudanpur PWSS under Chinsurah Mogra Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | Assistant Engineer (Civil) |  | ORD/001844/2024-2025 | 221/CH | 19/02/2025 | 21/03/2025 | M/S T.K.B. CONSTRUCTION | 4.29 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | SM/11167 | Augmentation | Construction of Boundary Wall in Head Work Site for MADHUSUDANPUR Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within CHINSURAH - MOGRA Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001468/2024-2025 | 132/CH | 29/01/2025 | 01/04/2025 | M/S T.K.B. CONSTRUCTION | 4.81 | 0 | 0 | 50
Total | [13 empty] | 409.1 | 182.03 | 44.49