## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11225 | Retrofitting | Providing 155 nos Functional Household Tap Connection (FHTC) within the command area of JAGATPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000444/2021-2022 | 462/Hug | 10/03/2022 | 25/03/2022 | M/S TANISA ENTERPRISE | 11.7 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11225 | Retrofitting | Providing 1487 nos F.H.T.C. in the villages of Sudarsan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba Dadpur] | Assistant Engineer | Junior Engineer (Civill) | ORD/000886/2020-2021 | 242/HUG | 02/02/2021 | 14/03/2021 | M/S BISWAS CONSTRUCTION | 69.94 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11225 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000885/2020-2021 | 467/HUG | 26/02/2021 | 28/03/2021 | TAPAS ADHYA | 44.33 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11225 | Retrofitting | Sinking of 1(one) No Big dia tube well (300 mm x 200mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 4th TW site of JAGATPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000124/2022-2023 | 1274/HUG | 23/06/2022 | 23/07/2022 | KAMIRUL SK AND CO | 9.96 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | SM/11225 | Retrofitting | Sinking of 1(one) No Big dia tube well (300 mm x 200mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 5th TW site of JAGATPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000125/2022-2023 | 1275/HUG | 23/06/2022 | 23/07/2022 | KAMIRUL SK AND CO | 9.96 | 0 | 0 | 100
Total | [13 empty] | 145.88 | 0 | 0