## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 2471/2/Hug | 18/11/2022 |  | Resource Division | 12.06 | 0 | 0 | 0
2 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Route Survey, Design Drawing & DPR Preparation of Astara PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000408/2022-2023 | 510/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 4.07 | 4.07 | 100 | 0
3 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Material Requisition To Resource Division |  |  | RTOR000159/2022-2023 | 01/05/Hug | 02/01/2023 |  | Resource Division | 12.06 | 0 | 0 | 0
4 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Material Requisition To Resource Division |  |  | RTOR000216/2022-2023 | 109/ 22/Hug | 10/01/2023 |  | Resource Division | 27.67 | 0 | 0 | 0
5 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Material Requisition To Resource Division |  |  | RTOR000286/2023-2024 | 1383/32/Hug | 15/05/2023 |  | Resource Division | 12.27 | 0 | 0 | 0
6 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000784/2022-2023 | 878/HUG | 27/03/2023 | 11/05/2023 | MS D.PALIT AND CO. | 62.24 | 0 | 0 | 100
7 | HOOGHLY | Tarakeswar | Electrical | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
8 | HOOGHLY | Tarakeswar | Electrical | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Astara w/s scheme,P H No-1 |  |  | BILL/03938/2023-2024 | 313 | 27/09/2023 |  | WBSEDCL | 5.81 | 0 | 0 | 0
9 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Material Requisition To Resource Division |  |  | RTOR000444/2023-2024 | 3058/40/Hug | 11/10/2023 |  | Resource Division | 12.06 | 0 | 0 | 0
10 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of ASTARA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000751/2022-2023 | 652/Hug | 10/03/2023 | 09/05/2023 | APEX ENGINEERING | 12.25 | 6.13 | 50 | 100
11 | HOOGHLY | Tarakeswar | Electrical | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Quotation for new service connection for ASTARA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004031983 Ref. ID- 503573554 SM/11286 |  |  | BILL/06196/2023-2024 | 804 | 27/02/2024 |  | WBSEDCL | 6.23 | 0 | 0 | null
12 | HOOGHLY | Tarakeswar | Electrical | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Astara water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer3 | ORD/000075/2022-2023 | 3457/ED | 30/12/2022 | 30/03/2023 | S S ENTERPRISES | 23.02 | 19.73 | 85.74 | 65
13 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Astara PWSS, Baligori Z-I PWSS, Baligori Z-II PWSS, Talpur PWSS, Kulteghori PWSS, Santoshpur PWSS) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000980/2023-2024 | 308/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 100
14 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000203/2023-2024 | 1818/HUG | 22/06/2023 | 06/08/2023 | OSMAN SEKH | 80.85 | 15.61 | 19.31 | 100
15 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | "ASTARA" Piped Water Supply Scheme With LDS, FHTC & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000402/2022-2023 | 2168/HUG | 28/09/2022 | 27/03/2023 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 399.41 | 263.55 | 65.99 | 75
16 | HOOGHLY | Tarakeswar | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME | SM/11286 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for ASTARA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000353/2023-2024 | 2445/HUG | 12/08/2023 | 11/10/2023 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 44.85 | 9.42 | 21.02 | 100
Total | [13 empty] | 810.12 | 318.52 | 39.32