## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Laying Distribution System, Laying D.I Pipes & Specials for Rising Main Pipe Line, Construction of 1No 3.6M X 3.0 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at T.W Site including providing FHTC in BHAGABATIPUR Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division. | Assistant Engineer (Civil) | Haripal Block junior Enginner | ORD/000418/2022-2023 | 2280/Hug | 19/10/2022 | 03/12/2022 | BABUSONA CONSTRUCTION | 46.12 | 0 | 0 | 55
2 | HOOGHLY | Haripal | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BHAGABATIPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000769/2022-2023 | 752/HUG | 15/03/2023 | 14/04/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 0 | 100
3 | HOOGHLY | Haripal | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Supply and delivery of 300 mm dia UPVC pipe (CD) at Bhagabatipur Water Supply Scheme under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) |  | ORD/000382/2023-2024 | 615/Chan | 21/08/2023 | 28/08/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 0.89 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Material Requisition To Resource Division |  |  | RTOR000199/2022-2023 | 109/ 13/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 1.75 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Material Requisition To Resource Division |  |  | RTOR000165/2022-2023 | 79/1/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 59.68 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 1383/1/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.11 | 0 | 0 | 0
7 | HOOGHLY | Haripal | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Additional Quotation of New Service Connection for Bhagabatipur w/s Scheme,Tw no-I,Block-Haripal,Dist-Hooghly under Electrical Division PHE Dte |  |  | BILL/03884/2023-2024 | 296 | 21/09/2023 | 21/09/2023 | WBSEDCL | 0.48 | 0 | 0 | 0
8 | HOOGHLY | Haripal | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Quotation for new service connection of Bhagabatipur W/s Scheme, PH No-I Dist-Hooghly under Electrical Division ,PHE Dte |  |  | BILL/02003/2023-2024 | 103 | 19/07/2023 | 19/07/2023 | WBSEDCL | 2.6 | 0 | 0 | 0
9 | HOOGHLY | Haripal | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000077/2022-2023 | 3459/ED | 30/12/2022 | 30/03/2023 | NITESH MANAGEMENT | 10.16 | 0 | 0 | 40
10 | HOOGHLY | Haripal | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/11287 | New | Quotation Bill for New Service Connection at Bhagabatipur W/S. Sch. |  |  | BILL/06152/2023-2024 | 793 | 22/02/2024 | 22/02/2024 | WBSEDCL | 12.75 | 0 | 0 | 0
Total | [13 empty] | 147.99 | 0 | 0