## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Route Survey, Design Drawing & DPR Preparation of Bhanjipur PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000410/2022-2023 | 512/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 4.78 | 4.78 | 100 | 0
2 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Material Requisition To Resource Division |  |  | RTOR000218/2022-2023 | 109/ 23/Hug | 10/01/2023 |  | Resource Division | 23.69 | 0 | 0 | 0
3 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 1383/10/Hug | 15/05/2023 |  | Resource Division | 15.6 | 0 | 0 | 0
4 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of BHANJIPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000659/2022-2023 | 156/HUG | 16/01/2023 | 02/03/2023 | SURAJIT SINGHA RAY | 28.4 | 27.33 | 96.23 | 100
5 | HOOGHLY | Tarakeswar | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme, PH No.-II |  |  | BILL/03686/2023-2024 | 227 | 01/09/2023 |  | WBSEDCL | 4.93 | 0 | 0 | 0
6 | HOOGHLY | Tarakeswar | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme PH-I |  |  | BILL/03689/2023-2024 | 228 | 01/09/2023 |  | WBSEDCL | 4.65 | 0 | 0 | 0
7 | HOOGHLY | Tarakeswar | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01117/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 94.34 | 0 | 0 | 0
8 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Material Requisition To Resource Division |  |  | RTOR000367/2023-2024 | 3005/5/Hug | 05/10/2023 |  | Resource Division | 19.24 | 0 | 0 | 0
9 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Material Requisition To Resource Division |  |  | RTOR000407/2023-2024 | 3058/38/Hug | 11/10/2023 |  | Resource Division | 15.33 | 0 | 0 | 0
10 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of BHANJIPUR Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000711/2022-2023 | 448/HUG | 16/02/2023 | 17/04/2023 | AMBIAN INFRASTRUTTURE | 12.25 | 6.13 | 50 | 100
11 | HOOGHLY | Tarakeswar | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Quotation Bill for New Service Connection at Bhanjipur W/S. Sch. PH-I |  |  | BILL/04415/2023-2024 | 493 | 07/12/2023 |  | WBSEDCL | 0.1 | 0 | 0 | 0
12 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Horizontal Auger boring with water jet system Including Approach Road at BHANJIPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000506/2023-2024 | 2904/HUG | 21/09/2023 | 21/10/2023 | M/S. NANDY ENTERPRISE | 8.83 | 4.4 | 49.89 | 100
13 | HOOGHLY | Tarakeswar | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhanjipur water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer3 | ORD/000078/2022-2023 | 3460/ED | 30/12/2022 | 30/03/2023 | M.S. ENTERPRISE | 22.27 | 11.12 | 49.92 | 100
14 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for BHANJIPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000354/2023-2024 | 2446/HUG | 12/08/2023 | 11/10/2023 | R.K.CONSTRUCTION | 40.9 | 6.05 | 14.79 | 50
15 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Gouribati PWSS, Bhanjipur PWSS, Shibrambati zone-II PWSS, Aymachapsara PWSS, Balarambati PWSS, Chandanpur PWSS). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000974/2023-2024 | 310/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.48 | 50 | 100
16 | HOOGHLY | Tarakeswar | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME | SM/11288 | New | BHANJIPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000607/2022-2023 | 2899/HUG | 22/12/2022 | 20/06/2023 | M/S. NANDY ENTERPRISE | 457.97 | 202.92 | 44.31 | 60
Total | [13 empty] | 754.24 | 263.21 | 34.9