## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Route Survey, Design Drawing & DPR Preparation of Gouribati PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000406/2022-2023 | 509/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 2.93 | 2.93 | 100 | 0
2 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of GAURIBATI W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000660/2022-2023 | 157/HUG | 16/01/2023 | 02/03/2023 | SAMIRON GHOSH | 28.9 | 25.39 | 87.84 | 100
3 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of GAURIBATI Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000710/2022-2023 | 447/HUG | 16/02/2023 | 17/04/2023 | AMBIAN INFRASTRUTTURE | 12.23 | 12.23 | 100 | 100
4 | HOOGHLY | Tarakeswar | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gauribati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000081/2022-2023 | 3463/ED | 30/12/2022 | 30/03/2023 | POLYCON ENGINEERS | 22.28 | 22.27 | 99.95 | 100
5 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Material Requisition To Resource Division |  |  | RTOR000272/2022-2023 | 902/8/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 8.54 | 0 | 0 | 0
6 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Material Requisition To Resource Division |  |  | RTOR000216/2023-2024 | 1383/18/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 8.44 | 0 | 0 | 0
7 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Material Requisition To Resource Division |  |  | RTOR000421/2023-2024 | 3058/37/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 8.29 | 0 | 0 | 0
8 | HOOGHLY | Tarakeswar | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Quation Money for Gauribati w/s scheme P.H.No-II |  |  | BILL/02005/2023-2024 | 104 | 19/07/2023 | 19/07/2023 | WBSEDCL | 3.78 | 0 | 0 | 0
9 | HOOGHLY | Tarakeswar | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Gauribati water supply scheme,PHNo-I |  |  | BILL/02305/2023-2024 | 140 | 25/07/2023 | 25/07/2023 | WBSEDCL | 3.83 | 0 | 0 | 0
10 | HOOGHLY | Tarakeswar | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Quotation Bill for New Service Connection at Gouribati W/S. Sch. TW-III |  |  | BILL/05984/2023-2024 | 733 | 05/02/2024 | 05/02/2024 | WBSEDCL | 6.9 | 0 | 0 | 0
11 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | "GAURIBATI" Piped Water Supply Scheme With LDS, FHTC & Construction of 250 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000475/2022-2023 | 2558/HUG | 25/11/2022 | 01/12/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 305.74 | 230.46 | 75.38 | 30
12 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work Including Approach Road at Head Work site for GOURIBATI Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000350/2023-2024 | 2442/HUG | 12/08/2023 | 11/08/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 69.4 | 0 | 0 | 100
13 | HOOGHLY | Tarakeswar | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Laying of Rising main with necessary interconnection with 3rdT.W. & Distribution System, Construction of switch-room at 3rd T.W & boundary walls at 2nd & 3rdTW site for GOURIBATI Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000351/2023-2024 | 2443/HUG | 12/08/2023 | 12/08/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 25.05 | 0 | 0 | 70
14 | HOOGHLY | Tarakeswar | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME | SM/11289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gouribati water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002481/2023-2024 | 341/ED | 21/02/2024 | 01/06/2026 | J.K. ENGINEERING CO. | 10.74 | 7.71 | 71.82 | 40
Total | [13 empty] | 517.06 | 300.99 | 58.21