## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Route Survey, Design Drawing & DPR Preparation of Harat PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000409/2022-2023 | 511/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 4.21 | 4.21 | 100 | 0
2 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Material Requisition To Resource Division |  |  | RTOR000200/2022-2023 | 109/ 15/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 31.12 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 1383/5/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 11.78 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Material Requisition To Resource Division |  |  | RTOR000399/2023-2024 | 3058/1/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 116.86 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Quotation of New Service Connection for Harat Water Supply Scheme,TW No-II,Block-Haripal, Dist-Hooghly under ED,PHE Dte |  |  | BILL/03621/2023-2024 | 224 | 28/08/2023 | 28/08/2023 | WBSEDCL | 5.57 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | New Service Connection at Harat Piped W/S. Sch. TW-II |  |  | BILL/02741/2023-2024 | 170 | 09/08/2023 | 09/08/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
7 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | NEW SERVICE CONNECTION |  |  | BILL/02746/2023-2024 |  | 08/08/2023 | 08/08/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
8 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Additional Quotation Of New Service Connection for Harat w/s Scheme,PH No-I,Block-Haripal,Dist-Hooghly under ED,PHE Dte |  |  | BILL/04079/2023-2024 | 349 | 11/10/2023 | 11/10/2023 | WBSEDCL | 0.1 | 0 | 0 | 0
9 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000083/2022-2023 | 3465/ED | 30/12/2022 | 30/03/2023 | M/S A.K BANERJEE | 21.49 | 19.62 | 91.3 | 30
10 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1No 3.6M x 3.0M Switch Room without Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in HARAT Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Haripal Block junior Enginner | ORD/000618/2022-2023 | 42/HUG | 04/01/2023 | 31/10/2023 | TITAS CONSTRUCTION | 450.61 | 161.88 | 35.93 | 20
11 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000200/2023-2024 | 1804/HUG | 21/06/2023 | 05/08/2023 | OSMAN SEKH | 80.84 | 32.51 | 40.21 | 100
12 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Rambati 2nd T/W site & Harat 2nd T/W Site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000937/2023-2024 | 282/Chan | 15/03/2024 | 30/03/2024 | SUDIPTA SINHA | 0.88 | 0.82 | 93.46 | 100
13 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Quotation of New Service Connection for Harat w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/11290) Application No-5003979859 Reference Id-503541273 |  |  | BILL/06474/2023-2024 | 902 | 19/03/2024 | 19/03/2024 | WBSEDCL | 3.73 | 0 | 0 | 0
14 | HOOGHLY | Haripal | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of HARAT Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Haripal Block junior Enginner,Junior Engineer (Civill) | ORD/000752/2023-2024 | 387/HUG | 08/02/2024 | 27/03/2025 | BIMAL KUMAR HALDER | 31.63 | 0 | 0 | 100
15 | HOOGHLY | Haripal | Electrical | HARAT PIPED WATER SUPPLY SCHEME | SM/11290 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. III, Block: Haripal, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002480/2023-2024 | 340/ED | 21/02/2024 | 01/03/2026 | MOITRA ENGINEERING CO. | 10.74 | 10.44 | 97.21 | 10
Total | [13 empty] | 776.71 | 229.49 | 29.55