## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Route Survey, Design Drawing & DPR Preparation of Naita PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000411/2022-2023 | 513/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 5.15 | 5.15 | 100 | 0
2 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of NAITA W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000661/2022-2023 | 158/HUG | 16/01/2023 | 02/03/2023 | M/S SYCHROTECH INDUSTRY | 28.77 | 0 | 0 | 0
3 | HOOGHLY | Tarakeswar | Central Drilling | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x180 Mtrs.) byn utilising departmental rig machineries for naita W/S Scheme (TW-I & II), Tarakeswar Block under Hooghly District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000030/2023-2024 | 873/CDD | 11/07/2023 | 10/08/2023 | CHANDA ENTERPRISE | 24.62 | 11.57 | 47 | 50
4 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Material Requisition To Resource Division |  |  | RTOR000219/2022-2023 | 109/ 24/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 40.3 | 0 | 0 | 0
5 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Material Requisition To Resource Division |  |  | RTOR000274/2022-2023 | 902/11/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 13.29 | 0 | 0 | 0
6 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 1383/35/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 4.49 | 0 | 0 | 0
7 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Material Requisition To Resource Division |  |  | RTOR000368/2023-2024 | 3003/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 41.04 | 0 | 0 | 0
8 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Material Requisition To Resource Division |  |  | RTOR000449/2023-2024 | 3058/36/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.24 | 0 | 0 | 0
9 | HOOGHLY | Tarakeswar | Electrical | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Naita w/s scheme,P H No -I |  |  | BILL/03902/2023-2024 | 307 | 26/09/2023 | 26/09/2023 | WBSEDCL | 4.39 | 0 | 0 | 0
10 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of NAITA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000752/2022-2023 | 653/Hug | 10/03/2023 | 09/05/2023 | GOURI ENTERPRISE | 12.25 | 12.25 | 100 | 50
11 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001023/2023-2024 | 3379/HUG | 21/11/2023 | 05/01/2024 | OSMAN SEKH | 64.2 | 31.65 | 49.3 | 100
12 | HOOGHLY | Tarakeswar | Electrical | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Quotation for new service connection for NAITA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004032139 Ref. ID- 503573584 SM/11291 |  |  | BILL/06195/2023-2024 | 803 | 27/02/2024 | 27/02/2024 | WBSEDCL | 6.57 | 0 | 0 | 0
13 | HOOGHLY | Tarakeswar | Electrical | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Naita water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2,Junior Engineer3 | ORD/000088/2022-2023 | 3470/ED | 30/12/2022 | 19/03/2025 | GOENKA ENTERPRISE | 21.49 | 15.43 | 71.77 | 70
14 | HOOGHLY | Tarakeswar | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME | SM/11291 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for NAITA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2023-2024 | 2447/HUG | 12/08/2023 | 01/04/2025 | SWASTIK ENTERPRISE | 42.33 | 18.16 | 42.9 | 25
Total | [13 empty] | 322.13 | 94.21 | 29.25