## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Route Survey, Design Drawing & DPR Preparation of Panrra PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000412/2022-2023 | 514/Chan | 29/09/2022 | 14/10/2022 | ENVIROTECH SOLUTIONS | 6.22 | 6.22 | 100 | 0
2 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Material Requisition To Resource Division |  |  | RTOR000201/2022-2023 | 109/ 16/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 80.63 | 0 | 0 | 0
3 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 1383/11/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 18.47 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Material Requisition To Resource Division |  |  | RTOR000408/2023-2024 | 3058/35/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 18.14 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Quotation of New Service Connection Charge for Pannra w/S Scheme,TW No-II, Block-Haripal Dist-Hooghly under ED,PHE Dte |  |  | BILL/03766/2023-2024 | 258 | 05/09/2023 | 05/09/2023 | WBSEDCL | 3.16 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1No 3.6M x 3.0M Switch Room without Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in PANRRA Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000001/2023-2024 | 988/Hug | 04/04/2023 | 29/01/2024 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 611.8 | 281.67 | 46.04 | 80
7 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Horizontal Auger boring with water jet system Including Approach road at Panrra W/S Scheme under Chandannagar Sub - Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000759/2023-2024 | 451/HUG | 15/02/2024 | 16/03/2024 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 20.55 | 0 | 0 | 0
8 | HOOGHLY | Haripal | Electrical | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Panrra water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000090/2022-2023 | 3472/ED | 30/12/2022 | 30/03/2023 | SANKAR PRASAD DUTTA & CO. | 23 | 20.88 | 90.77 | 30
9 | HOOGHLY | Haripal | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000200/2023-2024 | 1804/HUG | 21/06/2023 | 05/08/2023 | OSMAN SEKH | 80.84 | 32.25 | 39.89 | 100
10 | HOOGHLY | Haripal | Electrical | PANRRA PIPED WATER SUPPLY SCHEME | SM/11292 | New | Quotation for New Service Connection at Pantra W/S. Sch. TW-I |  |  | BILL/04613/2023-2024 | 612 | 14/03/2024 | 14/03/2024 | WBSEDCL | 4.96 | 0 | 0 | 0
Total | [13 empty] | 867.78 | 341.02 | 39.3