## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | "RAMBATI" Piped Water Supply Scheme With LDS, FHTC & Construction of 150 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000476/2022-2023 | 2559/HUG | 25/11/2022 | 02/12/2025 | BAPPADITYA BANERJEE | 230.53 | 186.6 | 80.95 | 45
2 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rambati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer2 | ORD/000092/2022-2023 | 3474/ED | 30/12/2022 | 30/05/2026 | S.G. TECHNICAL SERVICES | 20.35 | 17.05 | 83.79 | 90
3 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of RAMBATI W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000663/2022-2023 | 159/HUG | 16/01/2023 | 02/03/2023 | SAMIRON GHOSH | 28.9 | 28.86 | 99.86 | 100
4 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of RAMBATI Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000712/2022-2023 | 449/HUG | 16/02/2023 | 17/04/2023 | RITAM ENTERPRISE | 12.29 | 12.29 | 100 | 50
5 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work of Head Work & 2nd T.W Site of RAMBATI Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000352/2023-2024 | 2444/HUG | 12/08/2023 | 12/04/2025 | BAPPADITYA BANERJEE | 40.64 | 0 | 0 | 100
6 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Material Requisition To Resource Division |  |  | RTOR000273/2022-2023 | 902/14/Hug | 27/03/2023 | 27/03/2023 | Resource Division | 5.33 | 0 | 0 | 0
7 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Material Requisition To Resource Division |  |  | RTOR000292/2023-2024 | 1383/38/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.43 | 0 | 0 | 0
8 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme PH-I |  |  | BILL/03688/2023-2024 | 230 | 01/09/2023 | 01/09/2023 | WBSEDCL | 9.37 | 0 | 0 | 0
9 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  |  | BILL/00737/2023-2024 |  | 06/11/2023 | 06/11/2023 | AATISH KUMAR SHAW | 0.8 | 0 | 0 | 0
10 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme, PH No.-II |  |  | BILL/03687/2023-2024 | 229 | 01/09/2023 | 01/09/2023 | WBSEDCL | 6.25 | 0 | 0 | 0
11 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Revised Quotation Bill for New Service Connection at Rambati W/S. Sch. PH-I |  |  | BILL/04076/2023-2024 | 345 | 11/10/2023 | 11/10/2023 | WBSEDCL | 0 | 0 | 0 | 0
12 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle - II, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000285/2024-2025 | 2871/HMSD | 04/06/2024 | 03/12/2024 | DEBASHISH GHOSH | 0.86 | 0.12 | 13.44 | 0
13 | HOOGHLY | Tarakeswar | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | ROAD RESTORATION OF PMGSY ROAD NAMELY NANDAPUKUR TO DAULAPUR |  |  | BILL/00576/2024-2025 | BP-2024-25-435 | 12/09/2024 | 12/09/2024 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 31.13 | 0 | 0 | 0
14 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Fuel Charges for Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of September, 2024. |  |  | BILL/04725/2025-2026 |  | 08/12/2025 | 08/12/2025 | DEBASHISH GHOSH | 0.09 | 0 | 0 | 0
15 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Fuel Charges for Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of October, 2024. |  |  | BILL/04729/2025-2026 |  | 08/12/2025 | 08/12/2025 | DEBASHISH GHOSH | 0.04 | 0 | 0 | 0
16 | HOOGHLY | Tarakeswar | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI | SM/11293 | New | Fuel Charges for Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of August,2024. |  |  | BILL/04727/2025-2026 |  | 08/12/2025 | 08/12/2025 | DEBASHISH GHOSH | 0.01 | 0 | 0 | 0
Total | [13 empty] | 392.02 | 244.92 | 62.47