## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of Lakshmipur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000244/2021-2022 | 1995/Hug | 12/11/2021 | 12/12/2021 | S. B. CONSTRUCTION | 11.36 | 4.84 | 42.62 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000340/2021-2022 | 17/Hug | 04/01/2022 | 03/02/2022 | S.M. ENTERPRISE | 8.23 | 8.47 | 102.95 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Preparation of DPR for Augmentation of Lakshmipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000243/2022-2023 | 364/Arg | 19/05/2022 | 18/06/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.24 | 3.2 | 98.81 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Quotation of New Service Connection for Lakshmipur w/s scheme,TW No-3 District-Hooghly under ED,PHE Dte |  |  | BILL/02128/2023-2024 | 118 | 20/07/2023 |  | WBSEDCL | 3.52 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Quotation of New service Connection for Lakshmipur W/s Scheme, TW No-4, Block-Goghat-I, Dist-hooghly Under ED,PHE Dte |  |  | BILL/02477/2023-2024 | 150 | 01/08/2023 |  | WBSEDCL | 2.69 | 0 | 0 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Lakshmipur W/S Scheme (TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000008/2023-2024 | 18/CDD | 04/04/2023 | 04/05/2023 | CHANDA ENTERPRISE | 30.35 | 12.81 | 42.2 | 42
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 1773/22/Hug | 29/08/2022 |  | Resource Division | 0.69 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 2209/2/Hug | 30/09/2022 |  | Resource Division | 30.8 | 0 | 0 | 0
10 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | ADDITIONAL WORK FOR CONSTRUCTION OF TUBE WELL AT LAKSHMIPUR PWSS TW-I, ARAMBAG BLOCK, UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000510/2022-2023 | 66/CMSD-I | 14/03/2023 | 24/03/2023 | CHANDA ENTERPRISE | 0.86 | 0.43 | 50 | 100
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Repairing Of Switch Room, Boundary wall of T.W-1 & T.W-2 for Augemntation Of LAKSHMIPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer | Junior Engineer (Civill) | ORD/000348/2023-2024 | 2439/HUG | 12/08/2023 | 26/09/2023 | SADHUKHAN ENTERPRISE | 9.47 | 3.66 | 38.61 | 95
12 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Loading unloading & Shifting of Drilling Accessories , Supporting Vehicles along with Rig Machine JOHN DR 1500-I from Lakshmipur PWSS , Block ¿ Goghat-I, Hooghly District to PANCHLA Store Howrah under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000079/2023-2024 | 170/CMSD-II(D) | 30/06/2023 | 15/07/2023 | UTTAM KUMAR CHATTERJEE | 0.51 | 0.23 | 44.76 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Augmentation of LAKSHMIPUR Water Supply Scheme with Laying of Distribution System at Goghat -I Block under Arambagh Sub-Division of Hooghly Division, PHE Dte. Hooghly. Sl no - 04 | Assistant Engineer | Junior Engineer (Civill) | ORD/000246/2022-2023 | 1800/HUG | 01/09/2022 | 16/10/2022 | M/S RAJKUMAR KHAN | 112.72 | 105.68 | 93.75 | 96
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For AUGMENTATION OF of LAKSHMIPUR W/S Scheme under ARAMBAGH Sub - Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000118/2023-2024 | 1447/HUG | 18/05/2023 | 17/06/2023 | M/S KHAMRUI CONSTRUCTION | 31.29 | 14.16 | 45.25 | 100
15 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11461 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Lakshmipur water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer4 | ORD/000215/2022-2023 | 849/ED | 14/02/2023 | 15/05/2023 | PRADIP KUMAR DHABAL | 21.51 | 10.73 | 49.87 | 40
Total | [13 empty] | 356.6 | 164.19 | 46.04