## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Preparation of DPR for Augmentation of Baradangal Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000241/2022-2023 | 337/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.01 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Additional work for Preparation of DPR for Augmentation of Baradangal Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. Part-B | Assistant Engineer | Junior Engineer (Civill) | ORD/000391/2022-2023 | 624/Arg | 01/09/2022 | 01/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.3 | 0 | 0 | 0
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Baradangal W/S Scheme (Z-II, TW-I&II), Arambag block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000459/2022-2023 | 2329/CDD | 30/03/2023 | 29/04/2023 | ASHUTOSH DAS & CO | 22.73 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1773/3/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 1385/62/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 6.84 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1234/8/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 26.55 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-II District-Hooghly Under ED,PHE Dte |  |  | BILL/01918/2023-2024 | 92 | 13/07/2023 | 13/07/2023 | WBSEDCL | 4.6 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-I Dist-Hooghly under ED, PHE Dte. |  |  | BILL/01917/2023-2024 | 91 | 13/07/2023 | 13/07/2023 | WBSEDCL | 5.05 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Augmentation of BARADANGAL ZONE-II PWSS with LDS, FHTC, Rising Main and Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at Arambagh Block under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000581/2022-2023 | 2827/HUG | 15/12/2022 | 07/07/2023 | JAHANGIR ALAM | 266.1 | 0 | 0 | 60
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir Of BARADANGAL Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000362/2023-2024 | 2454/HUG | 12/08/2023 | 11/10/2023 | TANISA ENTERPRISE | 7.86 | 0 | 0 | 95
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Augmentation of BARADANGAL ZONE-I Water Supply Scheme with Laying Distribution System including providing Functional Household Tap Connection (FHTC) at Arambagh Block under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000216/2022-2023 | 1702/Hug | 22/08/2022 | 21/10/2022 | M/S CARE | 193.77 | 0 | 0 | 99
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Construction of 2 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary Wall at BARADANGAL Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000788/2023-2024 | 540/HUG | 20/02/2024 | 20/04/2025 | DIAMOND ENGINEERS CO OP AND CONSTRUCTION SOCIETY LTD | 27.35 | 0 | 0 | 70
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | SM/11462 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baradangal water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000198/2022-2023 | 825/ED | 14/02/2023 | 28/08/2025 | OSMAN SEKH | 21.5 | 0 | 0 | 70
Total | [13 empty] | 588.35 | 0 | 0