## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Additional survey work for preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. (Bhadur Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000240/2022-2023 | 335/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.46 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I].(Bhadur Part-A) | Assistant Engineer | Junior Engineer (Civill) | ORD/000239/2022-2023 | 334/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work for Augmentation of BHADUR (ZONE-II) Water Supply Scheme at Goghat-I Block under Armabag Sub- Division of Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/000386/2023-2024 | 2568/HUG | 24/08/2023 | 08/10/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.91 | 0 | 0 | 0
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Bhadur W/S Scheme (Z-II, TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. |  |  | ORD/000466/2022-2023 | 2298/CDD | 30/03/2023 | 29/04/2023 | CHANDA ENTERPRISE | 30.35 | 0 | 0 | 31
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 2211/3/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 1688/4/HUG | 22/08/2022 | 22/08/2022 | Resource Division | 120.14 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 1773/13/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 1.03 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1590/3/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 15.4 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1106/5/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 23.22 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 1385/15/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 14.32 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000330/2023-2024 | 2607/3/Hug | 29/08/2023 | 29/08/2023 | Resource Division | 18.58 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000372/2023-2024 | 3002/3/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 20.89 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000278/2022-2023 | 1105/5/Hug | 17/04/2023 | 17/04/2023 | Resource Division | 86.37 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1234/5/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 3.72 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, ARAMBAGH SUB-DIVISION, PHE DTE. |  |  | BILL/00228/2022-2023 | BP-2022-23-547 | 21/02/2023 | 21/02/2023 | M/S PRADYUT KUMAR HAZRA | 1.15 | 0 | 0 | 0
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Quotation of New Service Connection for Bhadur w/s Scheme,Zone-I,TW No-III Dist-Hooghly Under ED,PHE Dte |  |  | BILL/02130/2023-2024 | 116 | 20/07/2023 | 20/07/2023 | WBSEDCL | 6.86 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Quotation of New Service Connection for Bhadur w/s scheme,zone-II,TW No-II Dist-Hooghly under ED,PHE Dte |  |  | BILL/02129/2023-2024 | 119 | 20/07/2023 | 20/07/2023 | WBSEDCL | 2.8 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Providing Functional Household Tap Connection in BHADUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6M X 3.0M Switch Room & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 4 | Assistant Engineer | Junior Engineer (Civill) | ORD/000233/2022-2023 | 1782/HUG | 30/08/2022 | 14/10/2022 | THREE MAA ENTERPRISE | 78.11 | 0 | 0 | 75
19 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Augmentation of BHADUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under Arambagh Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000619/2022-2023 | 43/HUG | 04/01/2023 | 31/10/2023 | TITAS CONSTRUCTION | 411.57 | 0 | 0 | 55
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Protection works and other allied works at Head Work Site of BHADUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000476/2024-2025 | 4055/HUG | 19/12/2024 | 19/03/2025 | AYUSH ENTERPRISE | 23.83 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Laying Distribution System of BHADUR (Zone-II) Piped Water Supply Scheme within Bhadur, Mandalganti & Adra Mouza including Repairing of existing Switch rooms, Boundary walls of BHADUR (Zone-I & Zone-II) Water Supply Scheme at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000464/2022-2023 | 2525/HUG | 23/11/2022 | 07/01/2023 | M/S S & P CONSTRUCTION | 85 | 0 | 0 | 95
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhadur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000200/2022-2023 | 827/ED | 14/02/2023 | 15/05/2023 | C.M.S. ENGINEERING CONCERN | 21.95 | 0 | 0 | 20
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 100
24 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Additional Quotation of Bhadur w/s Scheme,Zone-I,PH No-3 Block-Goghat-I Dist-Hooghly under Electrical division,PHE Dte.(SM/11463) Reference Id-860301435 |  |  | BILL/00622/2024-2025 | 183 | 03/06/2024 | 03/06/2024 | WBSEDCL | 1.61 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS within Sekati(Part) Mouza for Augmentation of Bhadur (Zone-II) Water Supply Scheme at Goghat-I Block under Armabag Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000160/2022-2023 | 1422/Hug | 12/07/2022 | 02/05/2025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 98.87 | 0 | 0 | 50
Total | [13 empty] | 1107.61 | 0 | 0