## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Preparation of DPR for Augmentation of Anandapur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000238/2022-2023 | 333/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000395/2022-2023 | 123/HUG | 26/09/2022 | 21/10/2022 | M/S ROY CONSTRUCTION AND CO. | 15.22 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Laying Distribution System for ANANDAPUR (Zone-I) Piped Water Supply Scheme including Repairing of existing Switch rooms, Boundary walls (Zone-I & Zone-II) at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. SL NO - 01 | Assistant Engineer | Junior Engineer (Civill) | ORD/000231/2022-2023 | 1780/HUG | 30/08/2022 | 14/10/2022 | TAPAS ADHYA | 76.59 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Laying Distribution System of ANANDAPUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6 M X 3.0 M Switch Rooms & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO-02 | Assistant Engineer | Junior Engineer (Civill) | ORD/000232/2022-2023 | 1781/HUG | 30/08/2022 | 14/10/2022 | SARKAR CONSTRUCTION | 69.19 | 0 | 0 | 25
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at ANANDAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000460/2022-2023 | 2511/HUG | 22/11/2022 | 06/01/2023 | MS D.PALIT AND CO. | 27.59 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 2209/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 30.8 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 1773/32/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 1590/5/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 15.4 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 1385/18/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.49 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000259/2022-2023 | 127/2/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 9.57 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1234/7/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 0.32 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Quotation Bill for New Service Connection at Anandapur W/S. Sch. TW-III & IV, Hooghly |  |  | BILL/01816/2022-2023 | 205 | 21/03/2023 | 21/03/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anandapur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000048/2023-2024 | 1734/ED | 19/04/2023 | 18/07/2023 | P.K. ENGINEERING | 21.49 | 0 | 0 | 70
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 100
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11464 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ANANDAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000487/2024-2025 | 4151/HUG | 26/12/2024 | 26/03/2025 | M/S RAJKUMAR KHAN | 17.7 | 0 | 0 | 0
Total | [13 empty] | 291.72 | 0 | 0